## README
IntelCost Earthwork Production Starter Data (accepted as drafted, 23 Oct 2026)
Starter activities, production tiers (from 200 per day upward), spreads and default production for the Earthwork production settings. Split method: Cut lines excavate and load; Fill lines place and compact.
How to read it
1. Activities: the 13 activities, their unit and which Calculate line types they price (Line mapping has the full list).
2. Tiers: one row per production range with its spread. Machine and crew detail is in Tier machines and Tier crew; edit there.
3. Default production: the production per day a company normally gets, by total job quantity. This picks the tier.
4. Catalog gaps: machines in the spreads whose catalog data is incomplete, and what to enter. Rows marked "Optional (catalog gap)" are left out of the spread until filled.
5. Old sheet: what was kept from Crew_Assemley_DE_LLC V12 and what was dropped.
6. Catalog ref and Catalog production: the catalog values the other sheets look up (copied as published).
Assumptions (edit on Settings; blue = input)
- Production per day assumes a 10-hour work day (the old sheet's basis). Set the workspace "hours per work day" to 10, or scale the productions down for 8-hour days.
- Common earth (loam): 1 BCY = 1.25 LCY = 0.90 CCY (catalog Factors sheet, FM 5-434). Place and compact defaults are kept in step with Excavate and load at 0.90.
- Haul trucks: hired operated tri-axles (DT-OP-3AXLE, $106.14/hr incl. driver and fuel, catalog A). Counts assume about 140 LCY per truck per day (~10 loads of 14 LCY on a ~1 hr round trip, roughly 10 miles each way). Longer hauls need more trucks.
- Foreman: 0.5 on Excavate and load + 0.5 on Place and compact = the one foreman of the old combined spread.
- Operator rows follow machine counts automatically in the app (rule 5). They are listed on Tier crew for review only; do not add them twice.
- Every machine is a catalog size class (Equip_ID); rates are the national catalog rates. Pickups are left out (no catalog rate).
What is mine and what is yours
- Tiers marked "Old sheet" are anchored to your V12 spreads, translated to catalog classes. Tiers marked "Draft" are my proposal between and beyond those anchors. Please review every Draft row.
- Capacity check (Tiers sheet): catalog production x count x hours per day, for the machine group that limits the spread (excavators; dozers; rollers; loader vs trucks). "OK" means the spread can reach the top of the tier on paper. It is a sanity check, not a production rate. Hired trucks use the Settings truck-day assumption. Tamping compactors, breakers, graders, trench boxes and pipe crews have no usable catalog figure, so those tiers show "Not checked".
- Nothing here changes the catalog. When approved, this file is loaded as release data for Settings > Equipment library > Earthwork production.

## Settings
Setting | Value | Note
Hours per work day | 10 | Old sheet basis (10-hr day). Drives the capacity check only.
Bank to loose (common earth) | 1.25 | Catalog Factors, Loam, FM 5-434
Bank to compacted (common earth) | 0.9 | Catalog Factors, Loam, FM 5-434
Tri-axle LCY per truck-day | 140 | Assumption: ~10 loads x 14 LCY, ~1 hr round trip. Haul tiers are sized at 140 (one tier per truck count); if you change this, change the tier ranges too. The capacity check follows this cell.

## Activities
ID | Activity | Unit | Prices these Calculate lines | Notes | Tiers
A1 | Excavate and load (on-site haul) | BCY | cut; over-excavation; stockpile (cut to stock) | Excavator loads off-road trucks that haul to the fill or stockpile on site. Pairs with A3 on the Fill lines. | 9
A2 | Excavate and load (direct to haul-off trucks) | BCY | undercut (default); use for cut on export-heavy sites | Excavator only: it loads the haul-off trucks priced on the Haul off line (A7). Avoids paying on-site trucks AND highway trucks for the same material. | 4
A3 | Place and compact | CCY | fill; undercut_replace; undercut_native; replacement fill | Dozer spreads, roller compacts. Default production kept in step with A1 (0.90 CCY per BCY, common earth). | 8
A4 | Strip topsoil (push to stockpile) | BCY | strip | Dozer only. Hauling the stripped topsoil away is A6 on the Haul Off line. | 5
A5 | Respread topsoil (from stockpile) | BCY | strip_reuse_topsoil | Load from stockpile, haul on site, spread. | 4
A6 | Load and haul off (from stockpile) | LCY | strip_haul; spoils_export | Loader plus hired operated tri-axles (driver and fuel in the truck rate). | 11
A7 | Haul off (loaded by excavator) | LCY | soil_export; undercut_haul | Hired operated tri-axles only; the excavator that loads them is on the Cut/Undercut line. | 11
A8 | Haul in (import) | LCY | soil_import | Hired operated tri-axles. If the material is bought delivered, map soil_import to none and price it as delivered material. | 11
A9 | Rock excavation (break and load) | BCY | rock_hard_dig | Excavator with hydraulic breaker. Rock starts below 200/day by nature. | 4
A10 | Rip rock (dozer) | BCY | (not mapped; alternative to A9 for rippable rock) | D8 class with ripper. | 2
A11 | Fine grade / subgrade prep | SF | prep | Grader, roller, part-time backhoe. | 4
A12 | Pipe crew, gravity storm/sewer (excavate, lay, backfill) | LF | utility_pipe | One crew prices the whole pipe run, so the trench excavation, backfill and bedding lines map to none (bedding stone stays a material by hand). | 4
A13 | Trench box with pipe crew | LF | trench_protection | Box moves with the pipe crew: give it the same production per day as A12 so the days match. | 2

## Tiers
Activity | Tier | From /day | To /day | Unit | Spread (machines) | Crew | Capacity check /day | Check | Source
A1 | 1 | 200 | 349 | BCY | 1 x 16-18 t (~38,000-40,000 lb) [EX-CRAWL-17T] *pacing; 1 x 26.5 t payload [ADT-25T] | 0.25 Foreman; 2 Operator (auto: follows machine count) | 1534.9783 | OK | Draft
A1 | 2 | 350 | 599 | BCY | 1 x 20-25 t (~48,500-62,800 lb) [EX-CRAWL-20T] *pacing; 2 x 26.5 t payload [ADT-25T] | 0.5 Foreman; 3 Operator (auto: follows machine count) | 1633.44 | OK | Draft
A1 | 3 | 600 | 899 | BCY | 1 x 20-25 t (~48,500-62,800 lb) [EX-CRAWL-20T] *pacing; 2 x 30 t payload [ADT-30T] | 0.5 Foreman; 3 Operator (auto: follows machine count) | 1633.44 | OK | Draft
A1 | 4 | 900 | 1399 | BCY | 1 x 30-36 t (~68,000-81,000 lb) [EX-CRAWL-30T] *pacing; 2 x 30 t payload [ADT-30T] | 0.5 Foreman; 3 Operator (auto: follows machine count); 0.5 Laborer | 3107.52 | OK | Old sheet: Cut to Fill 0-42,000 CY at 1,000/day (CAT 330 + 2 x 30 t ADT)
A1 | 5 | 1400 | 2199 | BCY | 1 x 30-36 t (~68,000-81,000 lb) [EX-CRAWL-30T] *pacing; 3 x 30 t payload [ADT-30T] | 0.5 Foreman; 4 Operator (auto: follows machine count); 0.5 Laborer | 3107.52 | OK | Draft
A1 | 6 | 2200 | 3199 | BCY | 1 x 45-55 t (~105,000-108,000 lb) [EX-CRAWL-50T] *pacing; 3 x 30 t payload [ADT-30T] | 0.5 Foreman; 4 Operator (auto: follows machine count); 0.5 Laborer; 0.5 Grade checker | 5109.0816 | OK | Old sheet: 42,000-84,000 CY at 2,275/day (CAT 345 + 2 x 40 t ADT; 40 t has no fuel in the catalog, so 3 x 30 t)
A1 | 7 | 3200 | 4499 | BCY | 1 x 45-55 t (~105,000-108,000 lb) [EX-CRAWL-50T] *pacing; 4 x 30 t payload [ADT-30T] | 0.5 Foreman; 5 Operator (auto: follows machine count); 0.5 Laborer; 0.5 Grade checker | 5109.0816 | OK | Draft
A1 | 8 | 4500 | 6999 | BCY | 2 x 45-55 t (~105,000-108,000 lb) [EX-CRAWL-50T] *pacing; 6 x 30 t payload [ADT-30T] | 0.5 Foreman; 8 Operator (auto: follows machine count); 0.5 Laborer; 0.5 Grade checker | 10218.1632 | OK | Old sheet: 84,000-126,000 CY at 5,275/day (2 x CAT 345 + 4 x 40 t + 1 x 30 t)
A1 | 9 | 7000 |  | BCY | 2 x 65-75 t (~145,000-163,000 lb) [EX-CRAWL-70T] *pacing; 9 x 30 t payload [ADT-30T] | 1 Foreman; 11 Operator (auto: follows machine count); 1 Laborer; 1 Grade checker | 15936 | OK | Draft (old >126,000 CY tab was unfinished)
A2 | 1 | 200 | 599 | BCY | 1 x 20-25 t (~48,500-62,800 lb) [EX-CRAWL-20T] *pacing | 0.25 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer (spotter) | 1633.44 | OK | Draft
A2 | 2 | 600 | 1399 | BCY | 1 x 30-36 t (~68,000-81,000 lb) [EX-CRAWL-30T] *pacing | 0.25 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer (spotter) | 3107.52 | OK | Old sheet: Cut to Offsite 1,500/day (CAT 330)
A2 | 3 | 1400 | 2999 | BCY | 1 x 45-55 t (~105,000-108,000 lb) [EX-CRAWL-50T] *pacing | 0.5 Foreman; 1 Operator (auto: follows machine count); 1 Laborer (spotter) | 5109.0816 | OK | Draft
A2 | 4 | 3000 |  | BCY | 2 x 45-55 t (~105,000-108,000 lb) [EX-CRAWL-50T] *pacing | 0.5 Foreman; 2 Operator (auto: follows machine count); 1 Laborer (spotter) | 10218.1632 | OK | Old sheet: Export 2 x PC-400 at 2,501/day
A3 | 1 | 200 | 329 | CCY | 1 x D3 class (~100-104 hp, 20-24k lb) [DZ-CRAWL-D3] *pacing; 1 x 84 in smooth [CP-SD-84-SM]; 0.25 x 4,000 gal (6x4) [WT-4000] (optional, catalog gap) | 0.25 Foreman; 2 Operator (auto: follows machine count) | 2651.684 | OK | Draft
A3 | 2 | 330 | 599 | CCY | 1 x D5 class (~170 hp, ~40k lb) [DZ-CRAWL-D5] *pacing; 1 x 84 in smooth [CP-SD-84-SM]; 0.5 x 4,000 gal (6x4) [WT-4000] (optional, catalog gap) | 0.5 Foreman; 2 Operator (auto: follows machine count) | 2651.684 | OK | Draft
A3 | 3 | 600 | 849 | CCY | 1 x D6 class (~215-240 hp, ~50k lb) [DZ-CRAWL-D6] *pacing; 1 x 84 in smooth [CP-SD-84-SM]; 0.5 x 4,000 gal (6x4) [WT-4000] (optional, catalog gap) | 0.5 Foreman; 2 Operator (auto: follows machine count); 0.5 Laborer | 2651.684 | OK | Draft
A3 | 4 | 850 | 1299 | CCY | 1 x D6 class (~215-240 hp, ~50k lb) [DZ-CRAWL-D6] *pacing; 1 x GPS/machine-control kit for dozer [AT-GPS-DOZER]; 1 x D5 class (~170 hp, ~40k lb) [DZ-CRAWL-D5]; 1 x 84 in smooth [CP-SD-84-SM]; 0.5 x 4,000 gal (6x4) [WT-4000] (optional, catalog gap) | 0.5 Foreman; 3 Operator (auto: follows machine count); 0.5 Laborer | 2651.684 | OK | Old sheet: Cut to Fill 1,000/day placing side (D6R GPS + D5N + roller + 1/2 water truck)
A3 | 5 | 1300 | 1999 | CCY | 1 x D6 class (~215-240 hp, ~50k lb) [DZ-CRAWL-D6] *pacing; 1 x GPS/machine-control kit for dozer [AT-GPS-DOZER]; 1 x Cat 815 (~249 hp) [CP-TAMP-815]; 0.5 x 4,000 gal (6x4) [WT-4000] (optional, catalog gap) | 0.5 Foreman; 2 Operator (auto: follows machine count); 2 Laborer |  | Not checked | Old sheet: Import Place & Compact 1,800/day (815 + D6R GPS + 1/2 water truck, 2 laborers)
A3 | 6 | 2000 | 2999 | CCY | 1 x D6 class (~215-240 hp, ~50k lb) [DZ-CRAWL-D6] *pacing; 1 x GPS/machine-control kit for dozer [AT-GPS-DOZER]; 2 x D5 class (~170 hp, ~40k lb) [DZ-CRAWL-D5]; 1 x Cat 815 (~249 hp) [CP-TAMP-815]; 1 x 4,000 gal (6x4) [WT-4000] (optional, catalog gap) | 0.5 Foreman; 4 Operator (auto: follows machine count); 0.5 Grade checker |  | Not checked | Old sheet: 2,275/day placing side (D6R GPS + 2 x D5N + 815 + water truck)
A3 | 7 | 3000 | 5999 | CCY | 2 x D6 class (~215-240 hp, ~50k lb) [DZ-CRAWL-D6] *pacing; 2 x GPS/machine-control kit for dozer [AT-GPS-DOZER]; 0.5 x D8 class (~363 hp) [DZ-CRAWL-D8]; 0.5 x D5 class (~170 hp, ~40k lb) [DZ-CRAWL-D5]; 2 x Cat 815 (~249 hp) [CP-TAMP-815]; 1 x 8,000 gal ADT-based [WT-8000-ADT] (optional, catalog gap) | 0.5 Foreman; 5 Operator (auto: follows machine count); 0.5 Grade checker |  | Not checked | Old sheet: 5,275/day placing side (2 x D6R GPS + 1/2 D8T + 1/2 D5N + 2 x 815 + water truck)
A3 | 8 | 6000 |  | CCY | 2 x D8 class (~363 hp) [DZ-CRAWL-D8] *pacing; 1 x D6 class (~215-240 hp, ~50k lb) [DZ-CRAWL-D6]; 1 x GPS/machine-control kit for dozer [AT-GPS-DOZER]; 2 x Cat 825 (~405 hp) [CP-TAMP-825]; 2 x 8,000 gal ADT-based [WT-8000-ADT] (optional, catalog gap) | 1 Foreman; 5 Operator (auto: follows machine count); 1 Grade checker |  | Not checked | Draft
A4 | 1 | 200 | 499 | BCY | 1 x D3 class (~100-104 hp, 20-24k lb) [DZ-CRAWL-D3] *pacing | 0.25 Foreman; 1 Operator (auto: follows machine count) | 1162.653 | OK | Draft
A4 | 2 | 500 | 999 | BCY | 1 x D5 class (~170 hp, ~40k lb) [DZ-CRAWL-D5] *pacing | 0.25 Foreman; 1 Operator (auto: follows machine count) | 1870.0013 | OK | Draft
A4 | 3 | 1000 | 1999 | BCY | 1 x D6 class (~215-240 hp, ~50k lb) [DZ-CRAWL-D6] *pacing | 0.25 Foreman; 1 Operator (auto: follows machine count) | 3048.9152 | OK | Old sheet: Strip 1,500/day (dozer side: D6R)
A4 | 4 | 2000 | 3499 | BCY | 1 x D6 class (~215-240 hp, ~50k lb) [DZ-CRAWL-D6] *pacing; 1 x D5 class (~170 hp, ~40k lb) [DZ-CRAWL-D5] | 0.5 Foreman; 2 Operator (auto: follows machine count) | 4918.9165 | OK | Old sheet: Strip with highway trucks 2,300/day (dozer side: D6M + D5N)
A4 | 5 | 3500 |  | BCY | 1 x D8 class (~363 hp) [DZ-CRAWL-D8] *pacing; 1 x D6 class (~215-240 hp, ~50k lb) [DZ-CRAWL-D6] | 0.5 Foreman; 2 Operator (auto: follows machine count) | 8524.7668 | OK | Draft
A5 | 1 | 200 | 499 | BCY | 1 x ROC >3,000 lb [CTL-LARGE] *pacing; 1 x D3 class (~100-104 hp, 20-24k lb) [DZ-CRAWL-D3] | 0.25 Foreman; 2 Operator (auto: follows machine count); 1 Laborer | 560.1504 | OK | Draft
A5 | 2 | 500 | 999 | BCY | 1 x 3-3.2 yd (~170 hp) [WL-SMALL-3Y] *pacing; 1 x 26.5 t payload [ADT-25T]; 1 x D4 class (~130 hp, ~30k lb) [DZ-CRAWL-D4] | 0.25 Foreman; 3 Operator (auto: follows machine count); 0.5 Laborer | 2346.576 | OK | Old sheet: Respread 500/day (used CAT 330 + D6M + 40 t truck; loader used here)
A5 | 3 | 1000 | 1999 | BCY | 1 x 4.5 yd (~225-250 hp) [WL-MED-45Y] *pacing; 2 x 30 t payload [ADT-30T]; 1 x D5 class (~170 hp, ~40k lb) [DZ-CRAWL-D5] | 0.5 Foreman; 4 Operator (auto: follows machine count); 0.5 Laborer | 3406.32 | OK | Draft
A5 | 4 | 2000 |  | BCY | 1 x 4.5 yd (~225-250 hp) [WL-MED-45Y] *pacing; 3 x 30 t payload [ADT-30T]; 1 x D6 class (~215-240 hp, ~50k lb) [DZ-CRAWL-D6] | 0.5 Foreman; 5 Operator (auto: follows machine count); 0.5 Laborer | 3406.32 | OK | Draft
A6 | 1 | 200 | 280 | LCY | 1 x 3-3.2 yd (~170 hp) [WL-SMALL-3Y] *pacing; 2 x 3-axle (tri-axle), operated [DT-OP-3AXLE] | 0.25 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer (spotter) | 280 | OK | Draft; 2 trucks x 140 LCY per truck-day
A6 | 2 | 281 | 420 | LCY | 1 x 3-3.2 yd (~170 hp) [WL-SMALL-3Y] *pacing; 3 x 3-axle (tri-axle), operated [DT-OP-3AXLE] | 0.25 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer (spotter) | 420 | OK | Draft; 3 trucks x 140 LCY per truck-day
A6 | 3 | 421 | 560 | LCY | 1 x 3-3.2 yd (~170 hp) [WL-SMALL-3Y] *pacing; 4 x 3-axle (tri-axle), operated [DT-OP-3AXLE] | 0.25 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer (spotter) | 560 | OK | Draft; 4 trucks x 140 LCY per truck-day
A6 | 4 | 561 | 700 | LCY | 1 x 3-3.2 yd (~170 hp) [WL-SMALL-3Y] *pacing; 5 x 3-axle (tri-axle), operated [DT-OP-3AXLE] | 0.25 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer (spotter) | 700 | OK | Draft; 5 trucks x 140 LCY per truck-day
A6 | 5 | 701 | 840 | LCY | 1 x 3-3.2 yd (~170 hp) [WL-SMALL-3Y] *pacing; 6 x 3-axle (tri-axle), operated [DT-OP-3AXLE] | 0.25 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer (spotter) | 840 | OK | Draft; 6 trucks x 140 LCY per truck-day
A6 | 6 | 841 | 1120 | LCY | 1 x 3-3.2 yd (~170 hp) [WL-SMALL-3Y] *pacing; 8 x 3-axle (tri-axle), operated [DT-OP-3AXLE] | 0.25 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer (spotter) | 1120 | OK | Draft; 8 trucks x 140 LCY per truck-day
A6 | 7 | 1121 | 1400 | LCY | 1 x 4.5 yd (~225-250 hp) [WL-MED-45Y] *pacing; 10 x 3-axle (tri-axle), operated [DT-OP-3AXLE] | 0.5 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer (spotter) | 1400 | OK | Draft; 10 trucks x 140 LCY per truck-day
A6 | 8 | 1401 | 1680 | LCY | 1 x 4.5 yd (~225-250 hp) [WL-MED-45Y] *pacing; 12 x 3-axle (tri-axle), operated [DT-OP-3AXLE] | 0.5 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer (spotter) | 1680 | OK | Draft; 12 trucks x 140 LCY per truck-day
A6 | 9 | 1681 | 2100 | LCY | 1 x 4.5 yd (~225-250 hp) [WL-MED-45Y] *pacing; 15 x 3-axle (tri-axle), operated [DT-OP-3AXLE] | 0.5 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer (spotter) | 2100 | OK | Draft; 15 trucks x 140 LCY per truck-day
A6 | 10 | 2101 | 2520 | LCY | 1 x 4.5 yd (~225-250 hp) [WL-MED-45Y] *pacing; 18 x 3-axle (tri-axle), operated [DT-OP-3AXLE] | 0.5 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer (spotter) | 2520 | OK | Draft; 18 trucks x 140 LCY per truck-day
A6 | 11 | 2521 |  | LCY | 1 x 4.5 yd (~225-250 hp) [WL-MED-45Y] *pacing; 22 x 3-axle (tri-axle), operated [DT-OP-3AXLE] | 0.5 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer (spotter) | 3080 | OK | Draft; 22 trucks x 140 LCY per truck-day
A7 | 1 | 200 | 280 | LCY | 2 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (spotter) | 280 | OK | Draft; 2 trucks x 140 LCY per truck-day
A7 | 2 | 281 | 420 | LCY | 3 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (spotter) | 420 | OK | Draft; 3 trucks x 140 LCY per truck-day
A7 | 3 | 421 | 560 | LCY | 4 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (spotter) | 560 | OK | Draft; 4 trucks x 140 LCY per truck-day
A7 | 4 | 561 | 700 | LCY | 5 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (spotter) | 700 | OK | Draft; 5 trucks x 140 LCY per truck-day
A7 | 5 | 701 | 840 | LCY | 6 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (spotter) | 840 | OK | Draft; 6 trucks x 140 LCY per truck-day
A7 | 6 | 841 | 1120 | LCY | 8 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (spotter) | 1120 | OK | Draft; 8 trucks x 140 LCY per truck-day
A7 | 7 | 1121 | 1400 | LCY | 10 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (spotter) | 1400 | OK | Draft; 10 trucks x 140 LCY per truck-day
A7 | 8 | 1401 | 1680 | LCY | 12 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (spotter) | 1680 | OK | Draft; 12 trucks x 140 LCY per truck-day
A7 | 9 | 1681 | 2100 | LCY | 15 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (spotter) | 2100 | OK | Draft; 15 trucks x 140 LCY per truck-day
A7 | 10 | 2101 | 2520 | LCY | 18 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (spotter) | 2520 | OK | Draft; 18 trucks x 140 LCY per truck-day
A7 | 11 | 2521 |  | LCY | 22 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (spotter) | 3080 | OK | Draft; 22 trucks x 140 LCY per truck-day
A8 | 1 | 200 | 280 | LCY | 2 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (dump spotter) | 280 | OK | Draft; 2 trucks x 140 LCY per truck-day
A8 | 2 | 281 | 420 | LCY | 3 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (dump spotter) | 420 | OK | Draft; 3 trucks x 140 LCY per truck-day
A8 | 3 | 421 | 560 | LCY | 4 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (dump spotter) | 560 | OK | Draft; 4 trucks x 140 LCY per truck-day
A8 | 4 | 561 | 700 | LCY | 5 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (dump spotter) | 700 | OK | Draft; 5 trucks x 140 LCY per truck-day
A8 | 5 | 701 | 840 | LCY | 6 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (dump spotter) | 840 | OK | Draft; 6 trucks x 140 LCY per truck-day
A8 | 6 | 841 | 1120 | LCY | 8 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (dump spotter) | 1120 | OK | Draft; 8 trucks x 140 LCY per truck-day
A8 | 7 | 1121 | 1400 | LCY | 10 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (dump spotter) | 1400 | OK | Draft; 10 trucks x 140 LCY per truck-day
A8 | 8 | 1401 | 1680 | LCY | 12 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (dump spotter) | 1680 | OK | Draft; 12 trucks x 140 LCY per truck-day
A8 | 9 | 1681 | 2100 | LCY | 15 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (dump spotter) | 2100 | OK | Draft; 15 trucks x 140 LCY per truck-day
A8 | 10 | 2101 | 2520 | LCY | 18 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (dump spotter) | 2520 | OK | Draft; 18 trucks x 140 LCY per truck-day
A8 | 11 | 2521 |  | LCY | 22 x 3-axle (tri-axle), operated [DT-OP-3AXLE] *pacing | 0.5 Laborer (dump spotter) | 3080 | OK | Draft; 22 trucks x 140 LCY per truck-day
A9 | 1 | 30 | 79 | BCY | 1 x 20-25 t (~48,500-62,800 lb) [EX-CRAWL-20T] *pacing; 1 x Hydraulic breaker for 20-30 t excavator [AT-BRK-20T] | 0.25 Foreman; 1 Operator (auto: follows machine count); 0.5 Laborer |  | Not checked | Old sheet: Hammer Hoe 50/day
A9 | 2 | 80 | 149 | BCY | 1 x 30-36 t (~68,000-81,000 lb) [EX-CRAWL-30T] *pacing; 1 x Hydraulic breaker for ~36 t excavator (HB-3100) [AT-BRK-36T]; 1 x 20-25 t (~48,500-62,800 lb) [EX-CRAWL-20T] | 0.5 Foreman; 2 Operator (auto: follows machine count); 0.5 Laborer |  | Not checked | Draft
A9 | 3 | 150 | 299 | BCY | 2 x 30-36 t (~68,000-81,000 lb) [EX-CRAWL-30T] *pacing; 2 x Hydraulic breaker for ~36 t excavator (HB-3100) [AT-BRK-36T]; 1 x 30-36 t (~68,000-81,000 lb) [EX-CRAWL-30T] | 0.5 Foreman; 3 Operator (auto: follows machine count); 1 Laborer |  | Not checked | Draft
A9 | 4 | 300 |  | BCY | 3 x 30-36 t (~68,000-81,000 lb) [EX-CRAWL-30T] *pacing; 3 x Hydraulic breaker for ~36 t excavator (HB-3100) [AT-BRK-36T]; 1 x 45-55 t (~105,000-108,000 lb) [EX-CRAWL-50T] | 1 Foreman; 4 Operator (auto: follows machine count); 1 Laborer |  | Not checked | Draft
A10 | 1 | 200 | 599 | BCY | 1 x D8 class (~363 hp) [DZ-CRAWL-D8] *pacing | 1 Operator (auto: follows machine count); 0.25 Foreman | 3000 | OK | Old sheet: Ripping Rock 400/day (D8R)
A10 | 2 | 600 |  | BCY | 2 x D8 class (~363 hp) [DZ-CRAWL-D8] *pacing | 2 Operator (auto: follows machine count); 0.5 Foreman | 6000 | OK | Draft
A11 | 1 | 2000 | 7999 | SF | 1 x ROC >3,000 lb [CTL-LARGE] *pacing; 0.5 x 84 in smooth [CP-SD-84-SM] | 0.25 Foreman; 1.5 Operator (auto: follows machine count); 2 Laborer |  | Not checked | Draft
A11 | 2 | 8000 | 19999 | SF | 1 x 12 ft (Cat 140) [GR-12FT-140] *pacing; 0.5 x 84 in smooth [CP-SD-84-SM]; 0.25 x 4,000 gal (6x4) [WT-4000] (optional, catalog gap) | 0.5 Foreman; 1.5 Operator (auto: follows machine count); 2 Laborer; 0.5 Grade checker |  | Not checked | Draft
A11 | 3 | 20000 | 44999 | SF | 1 x 12 ft (Cat 140) [GR-12FT-140] *pacing; 0.5 x 84 in smooth [CP-SD-84-SM]; 0.5 x Standard 14-15 ft dig (90-103 hp) [BH-STD-14FT]; 0.5 x 4,000 gal (6x4) [WT-4000] (optional, catalog gap) | 1 Foreman; 2 Operator (auto: follows machine count); 2 Laborer |  | Not checked | Old sheet: Finegrade Crew 30,000 SF/day (grader + 1/2 roller + 1/2 backhoe + 1/2 water truck)
A11 | 4 | 45000 |  | SF | 1 x 14 ft (Cat 160) [GR-14FT-160] *pacing; 1 x 84 in smooth [CP-SD-84-SM]; 0.5 x Standard 14-15 ft dig (90-103 hp) [BH-STD-14FT]; 0.5 x 4,000 gal (6x4) [WT-4000] (optional, catalog gap) | 1 Foreman; 2.5 Operator (auto: follows machine count); 2 Laborer; 1 Grade checker |  | Not checked | Draft
A12 | 1 | 60 | 119 | LF | 1 x 20-25 t (~48,500-62,800 lb) [EX-CRAWL-20T] *pacing; 1 x ~1-1.25 yd (~68-75 hp) [WL-COMPACT-1Y]; 1 x ~32-33 in, ~3,200 lb [CP-TRENCH-ROLLER] (optional, catalog gap); 1 x ~800-1,100 lb reversible plate [CP-PLATE-REV] (optional, catalog gap) | 1 Foreman; 2 Operator (auto: follows machine count); 2 Pipelayer; 2 Laborer |  | Not checked | Draft
A12 | 2 | 120 | 199 | LF | 1 x 30-36 t (~68,000-81,000 lb) [EX-CRAWL-30T] *pacing; 1 x ~1-1.25 yd (~68-75 hp) [WL-COMPACT-1Y]; 1 x ~32-33 in, ~3,200 lb [CP-TRENCH-ROLLER] (optional, catalog gap); 1 x ~800-1,100 lb reversible plate [CP-PLATE-REV] (optional, catalog gap) | 1 Foreman; 2 Operator (auto: follows machine count); 4 Laborer |  | Not checked | Old sheet: Storm slow 120 / fast 200 LF/day (PC-300 + IT28 loader + trench roller + plate, 4 laborers)
A12 | 3 | 200 | 349 | LF | 1 x 30-36 t (~68,000-81,000 lb) [EX-CRAWL-30T] *pacing; 1 x 20-25 t (~48,500-62,800 lb) [EX-CRAWL-20T]; 1 x ~1-1.25 yd (~68-75 hp) [WL-COMPACT-1Y]; 1 x D3 class (~100-104 hp, 20-24k lb) [DZ-CRAWL-D3]; 1 x ~32-33 in, ~3,200 lb [CP-TRENCH-ROLLER] (optional, catalog gap); 1 x ~800-1,100 lb reversible plate [CP-PLATE-REV] (optional, catalog gap) | 1 Foreman; 4 Operator (auto: follows machine count); 5 Laborer |  | Not checked | Old sheet: Sewer 2 hoes 250 LF/day (PC220 + CAT 325 + IT28 + D4 + trench roller + plate, 5 laborers)
A12 | 4 | 350 |  | LF | 2 x 30-36 t (~68,000-81,000 lb) [EX-CRAWL-30T] *pacing; 1 x 2-2.5 yd (~110 hp) [WL-COMPACT-2Y]; 1 x D4 class (~130 hp, ~30k lb) [DZ-CRAWL-D4]; 1 x ~32-33 in, ~3,200 lb [CP-TRENCH-ROLLER] (optional, catalog gap); 1 x ~800-1,100 lb reversible plate [CP-PLATE-REV] (optional, catalog gap) | 1 Foreman; 4 Operator (auto: follows machine count); 6 Laborer |  | Not checked | Draft
A13 | 1 | 60 | 199 | LF | 1 x Steel trench box 8x20 [TB-STL-8x20] *pacing |  |  | Not checked | Draft
A13 | 2 | 200 |  | LF | 2 x Steel trench box 8x20 [TB-STL-8x20] *pacing |  |  | Not checked | Draft

## Default production
Activity | Activity name | Job quantity from | Job quantity to | Unit | Default production /day | Tier it lands in
A1 | Excavate and load (on-site haul) | 0 | 999 | BCY | 250 | 1
A1 | Excavate and load (on-site haul) | 1000 | 2999 | BCY | 400 | 2
A1 | Excavate and load (on-site haul) | 3000 | 7999 | BCY | 700 | 3
A1 | Excavate and load (on-site haul) | 8000 | 19999 | BCY | 1000 | 4
A1 | Excavate and load (on-site haul) | 20000 | 41999 | BCY | 1500 | 5
A1 | Excavate and load (on-site haul) | 42000 | 83999 | BCY | 2500 | 6
A1 | Excavate and load (on-site haul) | 84000 | 125999 | BCY | 5000 | 8
A1 | Excavate and load (on-site haul) | 126000 |  | BCY | 8000 | 9
A2 | Excavate and load (direct to haul-off trucks) | 0 | 999 | BCY | 250 | 1
A2 | Excavate and load (direct to haul-off trucks) | 1000 | 2999 | BCY | 400 | 1
A2 | Excavate and load (direct to haul-off trucks) | 3000 | 7999 | BCY | 700 | 2
A2 | Excavate and load (direct to haul-off trucks) | 8000 | 19999 | BCY | 1000 | 2
A2 | Excavate and load (direct to haul-off trucks) | 20000 | 41999 | BCY | 1500 | 3
A2 | Excavate and load (direct to haul-off trucks) | 42000 | 83999 | BCY | 2500 | 3
A2 | Excavate and load (direct to haul-off trucks) | 84000 |  | BCY | 4000 | 4
A3 | Place and compact | 0 | 899 | CCY | 225 | 1
A3 | Place and compact | 900 | 2699 | CCY | 360 | 2
A3 | Place and compact | 2700 | 7199 | CCY | 630 | 3
A3 | Place and compact | 7200 | 17999 | CCY | 900 | 4
A3 | Place and compact | 18000 | 37799 | CCY | 1350 | 5
A3 | Place and compact | 37800 | 75599 | CCY | 2250 | 6
A3 | Place and compact | 75600 | 113399 | CCY | 4500 | 7
A3 | Place and compact | 113400 |  | CCY | 7200 | 8
A4 | Strip topsoil (push to stockpile) | 0 | 999 | BCY | 300 | 1
A4 | Strip topsoil (push to stockpile) | 1000 | 4999 | BCY | 700 | 2
A4 | Strip topsoil (push to stockpile) | 5000 | 14999 | BCY | 1500 | 3
A4 | Strip topsoil (push to stockpile) | 15000 |  | BCY | 2300 | 4
A5 | Respread topsoil (from stockpile) | 0 | 999 | BCY | 300 | 1
A5 | Respread topsoil (from stockpile) | 1000 | 4999 | BCY | 600 | 2
A5 | Respread topsoil (from stockpile) | 5000 | 14999 | BCY | 1200 | 3
A5 | Respread topsoil (from stockpile) | 15000 |  | BCY | 2000 | 4
A6 | Load and haul off (from stockpile) | 0 | 499 | LCY | 250 | 1
A6 | Load and haul off (from stockpile) | 500 | 2999 | LCY | 420 | 2
A6 | Load and haul off (from stockpile) | 3000 | 9999 | LCY | 700 | 4
A6 | Load and haul off (from stockpile) | 10000 | 29999 | LCY | 1120 | 6
A6 | Load and haul off (from stockpile) | 30000 | 59999 | LCY | 1680 | 8
A6 | Load and haul off (from stockpile) | 60000 |  | LCY | 2520 | 10
A7 | Haul off (loaded by excavator) | 0 | 499 | LCY | 250 | 1
A7 | Haul off (loaded by excavator) | 500 | 2999 | LCY | 420 | 2
A7 | Haul off (loaded by excavator) | 3000 | 9999 | LCY | 700 | 4
A7 | Haul off (loaded by excavator) | 10000 | 29999 | LCY | 1120 | 6
A7 | Haul off (loaded by excavator) | 30000 | 59999 | LCY | 1680 | 8
A7 | Haul off (loaded by excavator) | 60000 |  | LCY | 2520 | 10
A8 | Haul in (import) | 0 | 499 | LCY | 250 | 1
A8 | Haul in (import) | 500 | 2999 | LCY | 420 | 2
A8 | Haul in (import) | 3000 | 9999 | LCY | 700 | 4
A8 | Haul in (import) | 10000 | 29999 | LCY | 1120 | 6
A8 | Haul in (import) | 30000 | 59999 | LCY | 1680 | 8
A8 | Haul in (import) | 60000 |  | LCY | 2520 | 10
A9 | Rock excavation (break and load) | 0 | 199 | BCY | 50 | 1
A9 | Rock excavation (break and load) | 200 | 999 | BCY | 100 | 2
A9 | Rock excavation (break and load) | 1000 |  | BCY | 200 | 3
A10 | Rip rock (dozer) | 0 |  | BCY | 400 | 1
A11 | Fine grade / subgrade prep | 0 | 9999 | SF | 5000 | 1
A11 | Fine grade / subgrade prep | 10000 | 49999 | SF | 15000 | 2
A11 | Fine grade / subgrade prep | 50000 | 199999 | SF | 30000 | 3
A11 | Fine grade / subgrade prep | 200000 |  | SF | 50000 | 4
A12 | Pipe crew, gravity storm/sewer (excavate, lay, backfill) | 0 | 249 | LF | 100 | 1
A12 | Pipe crew, gravity storm/sewer (excavate, lay, backfill) | 250 | 999 | LF | 150 | 2
A12 | Pipe crew, gravity storm/sewer (excavate, lay, backfill) | 1000 |  | LF | 250 | 3
A13 | Trench box with pipe crew | 0 | 249 | LF | 100 | 1
A13 | Trench box with pipe crew | 250 | 999 | LF | 150 | 1
A13 | Trench box with pipe crew | 1000 |  | LF | 250 | 2
Tier it lands in = 0 means the default production falls outside every tier: fix before loading.

## Line mapping
Calculate line type (code key) | Unit | Activity | Activity name | Note
cut | BCY | A1 | Excavate and load (on-site haul) | Calculate (confirmed overnight)
fill | CCY | A3 | Place and compact | Calculate (confirmed)
strip | BCY | A4 | Strip topsoil (push to stockpile) | Calculate (confirmed)
strip_haul | LCY | A6 | Load and haul off (from stockpile) | Calculate (confirmed)
strip_reuse_topsoil | BCY | A5 | Respread topsoil (from stockpile) | Calculate (confirmed; BCY, not LCY)
undercut | BCY | A2 | Excavate and load (direct to haul-off trucks) | Calculate (confirmed)
undercut_haul | LCY | A7 | Haul off (loaded by excavator) | Calculate (confirmed)
undercut_native | CY | A3 | Place and compact | Calculate (confirmed)
undercut_replace | CCY | A3 | Place and compact | Calculate (confirmed)
soil_export | LCY | A7 | Haul off (loaded by excavator) | Calculate (confirmed)
soil_import | LCY | A8 | Haul in (import) | Calculate (confirmed)
spoils_export | LCY | A6 | Load and haul off (from stockpile) | Calculate (confirmed)
rock_hard_dig | BCY | A9 | Rock excavation (break and load) | Calculate (confirmed)
prep | SF | A11 | Fine grade / subgrade prep | Calculate (confirmed)
utility_pipe | LF | A12 | Pipe crew, gravity storm/sewer (excavate, lay, backfill) | Calculate (confirmed)
trench_protection | LF | A13 | Trench box with pipe crew | Calculate (confirmed)
utility_trench_excavation | BCY | none | (not priced automatically) | Inside the pipe crew (A12)
utility_backfill | CCY | none | (not priced automatically) | Inside the pipe crew (A12)
utility_bedding_pipe_zone | CCY | none | (not priced automatically) | Inside the pipe crew; bedding stone as material by hand
stabilize / stabilize_mix | SY | none | (not priced automatically) | Usually subcontracted; the catalog reclaimer (PV-STABILIZER-WR2400) has no rate
stabilize_agent_1 / _2 | TON | none | (not priced automatically) | Material (cement, fly ash, lime)
dewatering | LF | none | (not priced automatically) | Job-specific; price by hand
over-excavation | BCY | A1 | Excavate and load (on-site haul) | Key name to confirm in code
replacement fill | CCY | A3 | Place and compact | Key name to confirm in code
stockpile | BCY | A1 | Excavate and load (on-site haul) | Key name to confirm in code
geosynthetics | SY | none | (not priced automatically) | Material and labour by hand; key name to confirm
Export-heavy site: switch "cut" to A2 so the cut is not paid with on-site trucks and haul-off trucks.

## Tier machines
Activity | Tier | Equip_ID | Size class | Count | Pacing | Capacity group | Optional (catalog gap) | Capacity activity | Catalog production /hr | Unit | Capacity per day (activity unit) | Rent day | Fuel gal/hr med | Mob one way @50 mi
A1 | 1 | EX-CRAWL-17T | 16-18 t (~38,000-40,000 lb) | 1 | Y | main |  | EW-CUTLOAD | 153.4978 | BCY/hr | 1534.9783 | 855 | 2.97 | 550
A1 | 1 | ADT-25T | 26.5 t payload | 1 | [7 empty] | 1882 | 4.56 | 1800
A1 | 2 | EX-CRAWL-20T | 20-25 t (~48,500-62,800 lb) | 1 | Y | main |  | EW-CUTLOAD | 163.344 | BCY/hr | 1633.44 | 1040 | 2.78 | 550
A1 | 2 | ADT-25T | 26.5 t payload | 2 | [7 empty] | 1882 | 4.56 | 1800
A1 | 3 | EX-CRAWL-20T | 20-25 t (~48,500-62,800 lb) | 1 | Y | main |  | EW-CUTLOAD | 163.344 | BCY/hr | 1633.44 | 1040 | 2.78 | 550
A1 | 3 | ADT-30T | 30 t payload | 2 | [7 empty] | 2126 | 4.38 | 1800
A1 | 4 | EX-CRAWL-30T | 30-36 t (~68,000-81,000 lb) | 1 | Y | main |  | EW-CUTLOAD | 310.752 | BCY/hr | 3107.52 | 1424 | 4.5 | 1800
A1 | 4 | ADT-30T | 30 t payload | 2 | [7 empty] | 2126 | 4.38 | 1800
A1 | 5 | EX-CRAWL-30T | 30-36 t (~68,000-81,000 lb) | 1 | Y | main |  | EW-CUTLOAD | 310.752 | BCY/hr | 3107.52 | 1424 | 4.5 | 1800
A1 | 5 | ADT-30T | 30 t payload | 3 | [7 empty] | 2126 | 4.38 | 1800
A1 | 6 | EX-CRAWL-50T | 45-55 t (~105,000-108,000 lb) | 1 | Y | main |  | EW-CUTLOAD | 510.9082 | BCY/hr | 5109.0816 | 2250 | 8.02 | 1913
A1 | 6 | ADT-30T | 30 t payload | 3 | [7 empty] | 2126 | 4.38 | 1800
A1 | 7 | EX-CRAWL-50T | 45-55 t (~105,000-108,000 lb) | 1 | Y | main |  | EW-CUTLOAD | 510.9082 | BCY/hr | 5109.0816 | 2250 | 8.02 | 1913
A1 | 7 | ADT-30T | 30 t payload | 4 | [7 empty] | 2126 | 4.38 | 1800
A1 | 8 | EX-CRAWL-50T | 45-55 t (~105,000-108,000 lb) | 2 | Y | main |  | EW-CUTLOAD | 510.9082 | BCY/hr | 10218.1632 | 2250 | 8.02 | 1913
A1 | 8 | ADT-30T | 30 t payload | 6 | [7 empty] | 2126 | 4.38 | 1800
A1 | 9 | EX-CRAWL-70T | 65-75 t (~145,000-163,000 lb) | 2 | Y | main |  | EW-CUTLOAD | 796.8 | BCY/hr | 15936 | 3950 | 9.95 | 1913
A1 | 9 | ADT-30T | 30 t payload | 9 | [7 empty] | 2126 | 4.38 | 1800
A2 | 1 | EX-CRAWL-20T | 20-25 t (~48,500-62,800 lb) | 1 | Y | main |  | EW-CUTLOAD | 163.344 | BCY/hr | 1633.44 | 1040 | 2.78 | 550
A2 | 2 | EX-CRAWL-30T | 30-36 t (~68,000-81,000 lb) | 1 | Y | main |  | EW-CUTLOAD | 310.752 | BCY/hr | 3107.52 | 1424 | 4.5 | 1800
A2 | 3 | EX-CRAWL-50T | 45-55 t (~105,000-108,000 lb) | 1 | Y | main |  | EW-CUTLOAD | 510.9082 | BCY/hr | 5109.0816 | 2250 | 8.02 | 1913
A2 | 4 | EX-CRAWL-50T | 45-55 t (~105,000-108,000 lb) | 2 | Y | main |  | EW-CUTLOAD | 510.9082 | BCY/hr | 10218.1632 | 2250 | 8.02 | 1913
A3 | 1 | DZ-CRAWL-D3 | D3 class (~100-104 hp, 20-24k lb) | 1 | Y | [6 empty] | 875 | 1.93 | 550
A3 | 1 | CP-SD-84-SM | 84 in smooth | 1 |  | main |  | EW-COMP-SOIL-8 | 265.1684 | CCY/hr | 2651.684 | 700 | 2.91 | 550
A3 | 1 | WT-4000 | 4,000 gal (6x4) | 0.25 |  |  | Y |  |  |  |  | 1057 | 0 | 0
A3 | 2 | DZ-CRAWL-D5 | D5 class (~170 hp, ~40k lb) | 1 | Y | [6 empty] | 1554 | 4.12 | 550
A3 | 2 | CP-SD-84-SM | 84 in smooth | 1 |  | main |  | EW-COMP-SOIL-8 | 265.1684 | CCY/hr | 2651.684 | 700 | 2.91 | 550
A3 | 2 | WT-4000 | 4,000 gal (6x4) | 0.5 |  |  | Y |  |  |  |  | 1057 | 0 | 0
A3 | 3 | DZ-CRAWL-D6 | D6 class (~215-240 hp, ~50k lb) | 1 | Y | [6 empty] | 2111 | 4.82 | 550
A3 | 3 | CP-SD-84-SM | 84 in smooth | 1 |  | main |  | EW-COMP-SOIL-8 | 265.1684 | CCY/hr | 2651.684 | 700 | 2.91 | 550
A3 | 3 | WT-4000 | 4,000 gal (6x4) | 0.5 |  |  | Y |  |  |  |  | 1057 | 0 | 0
A3 | 4 | DZ-CRAWL-D6 | D6 class (~215-240 hp, ~50k lb) | 1 | Y | [6 empty] | 2111 | 4.82 | 550
A3 | 4 | AT-GPS-DOZER | GPS/machine-control kit for dozer | 1 | [7 empty] | 560 | 0 | 400
A3 | 4 | DZ-CRAWL-D5 | D5 class (~170 hp, ~40k lb) | 1 | [7 empty] | 1554 | 4.12 | 550
A3 | 4 | CP-SD-84-SM | 84 in smooth | 1 |  | main |  | EW-COMP-SOIL-8 | 265.1684 | CCY/hr | 2651.684 | 700 | 2.91 | 550
A3 | 4 | WT-4000 | 4,000 gal (6x4) | 0.5 |  |  | Y |  |  |  |  | 1057 | 0 | 0
A3 | 5 | DZ-CRAWL-D6 | D6 class (~215-240 hp, ~50k lb) | 1 | Y | [6 empty] | 2111 | 4.82 | 550
A3 | 5 | AT-GPS-DOZER | GPS/machine-control kit for dozer | 1 | [7 empty] | 560 | 0 | 400
A3 | 5 | CP-TAMP-815 | Cat 815 (~249 hp) | 1 | [7 empty] | 2629 | 6.84 | 1800
A3 | 5 | WT-4000 | 4,000 gal (6x4) | 0.5 |  |  | Y |  |  |  |  | 1057 | 0 | 0
A3 | 6 | DZ-CRAWL-D6 | D6 class (~215-240 hp, ~50k lb) | 1 | Y | [6 empty] | 2111 | 4.82 | 550
A3 | 6 | AT-GPS-DOZER | GPS/machine-control kit for dozer | 1 | [7 empty] | 560 | 0 | 400
A3 | 6 | DZ-CRAWL-D5 | D5 class (~170 hp, ~40k lb) | 2 | [7 empty] | 1554 | 4.12 | 550
A3 | 6 | CP-TAMP-815 | Cat 815 (~249 hp) | 1 | [7 empty] | 2629 | 6.84 | 1800
A3 | 6 | WT-4000 | 4,000 gal (6x4) | 1 |  |  | Y |  |  |  |  | 1057 | 0 | 0
A3 | 7 | DZ-CRAWL-D6 | D6 class (~215-240 hp, ~50k lb) | 2 | Y | [6 empty] | 2111 | 4.82 | 550
A3 | 7 | AT-GPS-DOZER | GPS/machine-control kit for dozer | 2 | [7 empty] | 560 | 0 | 400
A3 | 7 | DZ-CRAWL-D8 | D8 class (~363 hp) | 0.5 | [7 empty] | 4170 | 8.59 | 1800
A3 | 7 | DZ-CRAWL-D5 | D5 class (~170 hp, ~40k lb) | 0.5 | [7 empty] | 1554 | 4.12 | 550
A3 | 7 | CP-TAMP-815 | Cat 815 (~249 hp) | 2 | [7 empty] | 2629 | 6.84 | 1800
A3 | 7 | WT-8000-ADT | 8,000 gal ADT-based | 1 |  |  | Y |  |  |  |  | 2810 | 0 | 1800
A3 | 8 | DZ-CRAWL-D8 | D8 class (~363 hp) | 2 | Y | [6 empty] | 4170 | 8.59 | 1800
A3 | 8 | DZ-CRAWL-D6 | D6 class (~215-240 hp, ~50k lb) | 1 | [7 empty] | 2111 | 4.82 | 550
A3 | 8 | AT-GPS-DOZER | GPS/machine-control kit for dozer | 1 | [7 empty] | 560 | 0 | 400
A3 | 8 | CP-TAMP-825 | Cat 825 (~405 hp) | 2 | [7 empty] | 4034 | 10.06 | 1800
A3 | 8 | WT-8000-ADT | 8,000 gal ADT-based | 2 |  |  | Y |  |  |  |  | 2810 | 0 | 1800
A4 | 1 | DZ-CRAWL-D3 | D3 class (~100-104 hp, 20-24k lb) | 1 | Y | main |  | EW-PUSH-100 | 145.3316 | LCY/hr | 1162.653 | 875 | 1.93 | 550
A4 | 2 | DZ-CRAWL-D5 | D5 class (~170 hp, ~40k lb) | 1 | Y | main |  | EW-PUSH-100 | 233.7502 | LCY/hr | 1870.0013 | 1554 | 4.12 | 550
A4 | 3 | DZ-CRAWL-D6 | D6 class (~215-240 hp, ~50k lb) | 1 | Y | main |  | EW-PUSH-100 | 381.1144 | LCY/hr | 3048.9152 | 2111 | 4.82 | 550
A4 | 4 | DZ-CRAWL-D6 | D6 class (~215-240 hp, ~50k lb) | 1 | Y | main |  | EW-PUSH-100 | 381.1144 | LCY/hr | 3048.9152 | 2111 | 4.82 | 550
A4 | 4 | DZ-CRAWL-D5 | D5 class (~170 hp, ~40k lb) | 1 |  | main |  | EW-PUSH-100 | 233.7502 | LCY/hr | 1870.0013 | 1554 | 4.12 | 550
A4 | 5 | DZ-CRAWL-D8 | D8 class (~363 hp) | 1 | Y | main |  | EW-PUSH-100 | 684.4815 | LCY/hr | 5475.8516 | 4170 | 8.59 | 1800
A4 | 5 | DZ-CRAWL-D6 | D6 class (~215-240 hp, ~50k lb) | 1 |  | main |  | EW-PUSH-100 | 381.1144 | LCY/hr | 3048.9152 | 2111 | 4.82 | 550
A5 | 1 | CTL-LARGE | ROC >3,000 lb | 1 | Y | main |  | EW-LOAD-TRK | 70.0188 | LCY/hr | 560.1504 | 500 | 3.3 | 500
A5 | 1 | DZ-CRAWL-D3 | D3 class (~100-104 hp, 20-24k lb) | 1 | [7 empty] | 875 | 1.93 | 550
A5 | 2 | WL-SMALL-3Y | 3-3.2 yd (~170 hp) | 1 | Y | main |  | EW-LOAD-TRK | 293.322 | LCY/hr | 2346.576 | 825 | 2.11 | 550
A5 | 2 | ADT-25T | 26.5 t payload | 1 | [7 empty] | 1882 | 4.56 | 1800
A5 | 2 | DZ-CRAWL-D4 | D4 class (~130 hp, ~30k lb) | 1 | [7 empty] | 1142 | 2.85 | 550
A5 | 3 | WL-MED-45Y | 4.5 yd (~225-250 hp) | 1 | Y | main |  | EW-LOAD-TRK | 425.79 | LCY/hr | 3406.32 | 1473 | 3.02 | 550
A5 | 3 | ADT-30T | 30 t payload | 2 | [7 empty] | 2126 | 4.38 | 1800
A5 | 3 | DZ-CRAWL-D5 | D5 class (~170 hp, ~40k lb) | 1 | [7 empty] | 1554 | 4.12 | 550
A5 | 4 | WL-MED-45Y | 4.5 yd (~225-250 hp) | 1 | Y | main |  | EW-LOAD-TRK | 425.79 | LCY/hr | 3406.32 | 1473 | 3.02 | 550
A5 | 4 | ADT-30T | 30 t payload | 3 | [7 empty] | 2126 | 4.38 | 1800
A5 | 4 | DZ-CRAWL-D6 | D6 class (~215-240 hp, ~50k lb) | 1 | [7 empty] | 2111 | 4.82 | 550
A6 | 1 | WL-SMALL-3Y | 3-3.2 yd (~170 hp) | 1 | Y | load |  | EW-LOAD-TRK | 293.322 | LCY/hr | 2933.22 | 825 | 2.11 | 550
A6 | 1 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 2 |  | haul |  | assumption | 14 | LCY/hr | 280 | 0 | 0 | 0
A6 | 2 | WL-SMALL-3Y | 3-3.2 yd (~170 hp) | 1 | Y | load |  | EW-LOAD-TRK | 293.322 | LCY/hr | 2933.22 | 825 | 2.11 | 550
A6 | 2 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 3 |  | haul |  | assumption | 14 | LCY/hr | 420 | 0 | 0 | 0
A6 | 3 | WL-SMALL-3Y | 3-3.2 yd (~170 hp) | 1 | Y | load |  | EW-LOAD-TRK | 293.322 | LCY/hr | 2933.22 | 825 | 2.11 | 550
A6 | 3 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 4 |  | haul |  | assumption | 14 | LCY/hr | 560 | 0 | 0 | 0
A6 | 4 | WL-SMALL-3Y | 3-3.2 yd (~170 hp) | 1 | Y | load |  | EW-LOAD-TRK | 293.322 | LCY/hr | 2933.22 | 825 | 2.11 | 550
A6 | 4 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 5 |  | haul |  | assumption | 14 | LCY/hr | 700 | 0 | 0 | 0
A6 | 5 | WL-SMALL-3Y | 3-3.2 yd (~170 hp) | 1 | Y | load |  | EW-LOAD-TRK | 293.322 | LCY/hr | 2933.22 | 825 | 2.11 | 550
A6 | 5 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 6 |  | haul |  | assumption | 14 | LCY/hr | 840 | 0 | 0 | 0
A6 | 6 | WL-SMALL-3Y | 3-3.2 yd (~170 hp) | 1 | Y | load |  | EW-LOAD-TRK | 293.322 | LCY/hr | 2933.22 | 825 | 2.11 | 550
A6 | 6 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 8 |  | haul |  | assumption | 14 | LCY/hr | 1120 | 0 | 0 | 0
A6 | 7 | WL-MED-45Y | 4.5 yd (~225-250 hp) | 1 | Y | load |  | EW-LOAD-TRK | 425.79 | LCY/hr | 4257.9 | 1473 | 3.02 | 550
A6 | 7 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 10 |  | haul |  | assumption | 14 | LCY/hr | 1400 | 0 | 0 | 0
A6 | 8 | WL-MED-45Y | 4.5 yd (~225-250 hp) | 1 | Y | load |  | EW-LOAD-TRK | 425.79 | LCY/hr | 4257.9 | 1473 | 3.02 | 550
A6 | 8 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 12 |  | haul |  | assumption | 14 | LCY/hr | 1680 | 0 | 0 | 0
A6 | 9 | WL-MED-45Y | 4.5 yd (~225-250 hp) | 1 | Y | load |  | EW-LOAD-TRK | 425.79 | LCY/hr | 4257.9 | 1473 | 3.02 | 550
A6 | 9 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 15 |  | haul |  | assumption | 14 | LCY/hr | 2100 | 0 | 0 | 0
A6 | 10 | WL-MED-45Y | 4.5 yd (~225-250 hp) | 1 | Y | load |  | EW-LOAD-TRK | 425.79 | LCY/hr | 4257.9 | 1473 | 3.02 | 550
A6 | 10 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 18 |  | haul |  | assumption | 14 | LCY/hr | 2520 | 0 | 0 | 0
A6 | 11 | WL-MED-45Y | 4.5 yd (~225-250 hp) | 1 | Y | load |  | EW-LOAD-TRK | 425.79 | LCY/hr | 4257.9 | 1473 | 3.02 | 550
A6 | 11 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 22 |  | haul |  | assumption | 14 | LCY/hr | 3080 | 0 | 0 | 0
A7 | 1 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 2 | Y | haul |  | assumption | 14 | LCY/hr | 280 | 0 | 0 | 0
A7 | 2 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 3 | Y | haul |  | assumption | 14 | LCY/hr | 420 | 0 | 0 | 0
A7 | 3 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 4 | Y | haul |  | assumption | 14 | LCY/hr | 560 | 0 | 0 | 0
A7 | 4 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 5 | Y | haul |  | assumption | 14 | LCY/hr | 700 | 0 | 0 | 0
A7 | 5 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 6 | Y | haul |  | assumption | 14 | LCY/hr | 840 | 0 | 0 | 0
A7 | 6 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 8 | Y | haul |  | assumption | 14 | LCY/hr | 1120 | 0 | 0 | 0
A7 | 7 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 10 | Y | haul |  | assumption | 14 | LCY/hr | 1400 | 0 | 0 | 0
A7 | 8 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 12 | Y | haul |  | assumption | 14 | LCY/hr | 1680 | 0 | 0 | 0
A7 | 9 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 15 | Y | haul |  | assumption | 14 | LCY/hr | 2100 | 0 | 0 | 0
A7 | 10 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 18 | Y | haul |  | assumption | 14 | LCY/hr | 2520 | 0 | 0 | 0
A7 | 11 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 22 | Y | haul |  | assumption | 14 | LCY/hr | 3080 | 0 | 0 | 0
A8 | 1 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 2 | Y | haul |  | assumption | 14 | LCY/hr | 280 | 0 | 0 | 0
A8 | 2 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 3 | Y | haul |  | assumption | 14 | LCY/hr | 420 | 0 | 0 | 0
A8 | 3 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 4 | Y | haul |  | assumption | 14 | LCY/hr | 560 | 0 | 0 | 0
A8 | 4 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 5 | Y | haul |  | assumption | 14 | LCY/hr | 700 | 0 | 0 | 0
A8 | 5 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 6 | Y | haul |  | assumption | 14 | LCY/hr | 840 | 0 | 0 | 0
A8 | 6 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 8 | Y | haul |  | assumption | 14 | LCY/hr | 1120 | 0 | 0 | 0
A8 | 7 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 10 | Y | haul |  | assumption | 14 | LCY/hr | 1400 | 0 | 0 | 0
A8 | 8 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 12 | Y | haul |  | assumption | 14 | LCY/hr | 1680 | 0 | 0 | 0
A8 | 9 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 15 | Y | haul |  | assumption | 14 | LCY/hr | 2100 | 0 | 0 | 0
A8 | 10 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 18 | Y | haul |  | assumption | 14 | LCY/hr | 2520 | 0 | 0 | 0
A8 | 11 | DT-OP-3AXLE | 3-axle (tri-axle), operated | 22 | Y | haul |  | assumption | 14 | LCY/hr | 3080 | 0 | 0 | 0
A9 | 1 | EX-CRAWL-20T | 20-25 t (~48,500-62,800 lb) | 1 | Y | [6 empty] | 1040 | 2.78 | 550
A9 | 1 | AT-BRK-20T | Hydraulic breaker for 20-30 t excavator | 1 | [7 empty] | 1050 | 0 | 400
A9 | 2 | EX-CRAWL-30T | 30-36 t (~68,000-81,000 lb) | 1 | Y | [6 empty] | 1424 | 4.5 | 1800
A9 | 2 | AT-BRK-36T | Hydraulic breaker for ~36 t excavator (HB-3100) | 1 | [7 empty] | 1600 | 0 | 400
A9 | 2 | EX-CRAWL-20T | 20-25 t (~48,500-62,800 lb) | 1 | [7 empty] | 1040 | 2.78 | 550
A9 | 3 | EX-CRAWL-30T | 30-36 t (~68,000-81,000 lb) | 2 | Y | [6 empty] | 1424 | 4.5 | 1800
A9 | 3 | AT-BRK-36T | Hydraulic breaker for ~36 t excavator (HB-3100) | 2 | [7 empty] | 1600 | 0 | 400
A9 | 3 | EX-CRAWL-30T | 30-36 t (~68,000-81,000 lb) | 1 | [7 empty] | 1424 | 4.5 | 1800
A9 | 4 | EX-CRAWL-30T | 30-36 t (~68,000-81,000 lb) | 3 | Y | [6 empty] | 1424 | 4.5 | 1800
A9 | 4 | AT-BRK-36T | Hydraulic breaker for ~36 t excavator (HB-3100) | 3 | [7 empty] | 1600 | 0 | 400
A9 | 4 | EX-CRAWL-50T | 45-55 t (~105,000-108,000 lb) | 1 | [7 empty] | 2250 | 8.02 | 1913
A10 | 1 | DZ-CRAWL-D8 | D8 class (~363 hp) | 1 | Y | main |  | EW-RIP | 300 | BCY/hr | 3000 | 4170 | 8.59 | 1800
A10 | 2 | DZ-CRAWL-D8 | D8 class (~363 hp) | 2 | Y | main |  | EW-RIP | 300 | BCY/hr | 6000 | 4170 | 8.59 | 1800
A11 | 1 | CTL-LARGE | ROC >3,000 lb | 1 | Y | [6 empty] | 500 | 3.3 | 500
A11 | 1 | CP-SD-84-SM | 84 in smooth | 0.5 | [7 empty] | 700 | 2.91 | 550
A11 | 2 | GR-12FT-140 | 12 ft (Cat 140) | 1 | Y | [6 empty] | 1949 | 3.53 | 550
A11 | 2 | CP-SD-84-SM | 84 in smooth | 0.5 | [7 empty] | 700 | 2.91 | 550
A11 | 2 | WT-4000 | 4,000 gal (6x4) | 0.25 |  |  | Y |  |  |  |  | 1057 | 0 | 0
A11 | 3 | GR-12FT-140 | 12 ft (Cat 140) | 1 | Y | [6 empty] | 1949 | 3.53 | 550
A11 | 3 | CP-SD-84-SM | 84 in smooth | 0.5 | [7 empty] | 700 | 2.91 | 550
A11 | 3 | BH-STD-14FT | Standard 14-15 ft dig (90-103 hp) | 0.5 | [7 empty] | 500 | 1.46 | 550
A11 | 3 | WT-4000 | 4,000 gal (6x4) | 0.5 |  |  | Y |  |  |  |  | 1057 | 0 | 0
A11 | 4 | GR-14FT-160 | 14 ft (Cat 160) | 1 | Y | [6 empty] | 2085 | 4.45 | 550
A11 | 4 | CP-SD-84-SM | 84 in smooth | 1 | [7 empty] | 700 | 2.91 | 550
A11 | 4 | BH-STD-14FT | Standard 14-15 ft dig (90-103 hp) | 0.5 | [7 empty] | 500 | 1.46 | 550
A11 | 4 | WT-4000 | 4,000 gal (6x4) | 0.5 |  |  | Y |  |  |  |  | 1057 | 0 | 0
A12 | 1 | EX-CRAWL-20T | 20-25 t (~48,500-62,800 lb) | 1 | Y | [6 empty] | 1040 | 2.78 | 550
A12 | 1 | WL-COMPACT-1Y | ~1-1.25 yd (~68-75 hp) | 1 | [7 empty] | 400 | 0.75 | 500
A12 | 1 | CP-TRENCH-ROLLER | ~32-33 in, ~3,200 lb | 1 |  |  | Y |  |  |  |  | 298 | 0 | 500
A12 | 1 | CP-PLATE-REV | ~800-1,100 lb reversible plate | 1 |  |  | Y |  |  |  |  | 240 | 0 | 200
A12 | 2 | EX-CRAWL-30T | 30-36 t (~68,000-81,000 lb) | 1 | Y | [6 empty] | 1424 | 4.5 | 1800
A12 | 2 | WL-COMPACT-1Y | ~1-1.25 yd (~68-75 hp) | 1 | [7 empty] | 400 | 0.75 | 500
A12 | 2 | CP-TRENCH-ROLLER | ~32-33 in, ~3,200 lb | 1 |  |  | Y |  |  |  |  | 298 | 0 | 500
A12 | 2 | CP-PLATE-REV | ~800-1,100 lb reversible plate | 1 |  |  | Y |  |  |  |  | 240 | 0 | 200
A12 | 3 | EX-CRAWL-30T | 30-36 t (~68,000-81,000 lb) | 1 | Y | [6 empty] | 1424 | 4.5 | 1800
A12 | 3 | EX-CRAWL-20T | 20-25 t (~48,500-62,800 lb) | 1 | [7 empty] | 1040 | 2.78 | 550
A12 | 3 | WL-COMPACT-1Y | ~1-1.25 yd (~68-75 hp) | 1 | [7 empty] | 400 | 0.75 | 500
A12 | 3 | DZ-CRAWL-D3 | D3 class (~100-104 hp, 20-24k lb) | 1 | [7 empty] | 875 | 1.93 | 550
A12 | 3 | CP-TRENCH-ROLLER | ~32-33 in, ~3,200 lb | 1 |  |  | Y |  |  |  |  | 298 | 0 | 500
A12 | 3 | CP-PLATE-REV | ~800-1,100 lb reversible plate | 1 |  |  | Y |  |  |  |  | 240 | 0 | 200
A12 | 4 | EX-CRAWL-30T | 30-36 t (~68,000-81,000 lb) | 2 | Y | [6 empty] | 1424 | 4.5 | 1800
A12 | 4 | WL-COMPACT-2Y | 2-2.5 yd (~110 hp) | 1 | [7 empty] | 675 | 1.16 | 500
A12 | 4 | DZ-CRAWL-D4 | D4 class (~130 hp, ~30k lb) | 1 | [7 empty] | 1142 | 2.85 | 550
A12 | 4 | CP-TRENCH-ROLLER | ~32-33 in, ~3,200 lb | 1 |  |  | Y |  |  |  |  | 298 | 0 | 500
A12 | 4 | CP-PLATE-REV | ~800-1,100 lb reversible plate | 1 |  |  | Y |  |  |  |  | 240 | 0 | 200
A13 | 1 | TB-STL-8x20 | Steel trench box 8x20 | 1 | Y | [6 empty] | 219 | 0 | 400
A13 | 2 | TB-STL-8x20 | Steel trench box 8x20 | 2 | Y | [6 empty] | 219 | 0 | 400

## Tier crew
Activity | Tier | Crew role | Count | Note
A1 | 1 | Foreman | 0.25
A1 | 1 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A1 | 2 | Foreman | 0.5
A1 | 2 | Operator (auto: follows machine count) | 3 | Listed for review; the app adds operators per machine
A1 | 3 | Foreman | 0.5
A1 | 3 | Operator (auto: follows machine count) | 3 | Listed for review; the app adds operators per machine
A1 | 4 | Foreman | 0.5
A1 | 4 | Operator (auto: follows machine count) | 3 | Listed for review; the app adds operators per machine
A1 | 4 | Laborer | 0.5
A1 | 5 | Foreman | 0.5
A1 | 5 | Operator (auto: follows machine count) | 4 | Listed for review; the app adds operators per machine
A1 | 5 | Laborer | 0.5
A1 | 6 | Foreman | 0.5
A1 | 6 | Operator (auto: follows machine count) | 4 | Listed for review; the app adds operators per machine
A1 | 6 | Laborer | 0.5
A1 | 6 | Grade checker | 0.5
A1 | 7 | Foreman | 0.5
A1 | 7 | Operator (auto: follows machine count) | 5 | Listed for review; the app adds operators per machine
A1 | 7 | Laborer | 0.5
A1 | 7 | Grade checker | 0.5
A1 | 8 | Foreman | 0.5
A1 | 8 | Operator (auto: follows machine count) | 8 | Listed for review; the app adds operators per machine
A1 | 8 | Laborer | 0.5
A1 | 8 | Grade checker | 0.5
A1 | 9 | Foreman | 1
A1 | 9 | Operator (auto: follows machine count) | 11 | Listed for review; the app adds operators per machine
A1 | 9 | Laborer | 1
A1 | 9 | Grade checker | 1
A2 | 1 | Foreman | 0.25
A2 | 1 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A2 | 1 | Laborer (spotter) | 0.5
A2 | 2 | Foreman | 0.25
A2 | 2 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A2 | 2 | Laborer (spotter) | 0.5
A2 | 3 | Foreman | 0.5
A2 | 3 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A2 | 3 | Laborer (spotter) | 1
A2 | 4 | Foreman | 0.5
A2 | 4 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A2 | 4 | Laborer (spotter) | 1
A3 | 1 | Foreman | 0.25
A3 | 1 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A3 | 2 | Foreman | 0.5
A3 | 2 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A3 | 3 | Foreman | 0.5
A3 | 3 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A3 | 3 | Laborer | 0.5
A3 | 4 | Foreman | 0.5
A3 | 4 | Operator (auto: follows machine count) | 3 | Listed for review; the app adds operators per machine
A3 | 4 | Laborer | 0.5
A3 | 5 | Foreman | 0.5
A3 | 5 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A3 | 5 | Laborer | 2
A3 | 6 | Foreman | 0.5
A3 | 6 | Operator (auto: follows machine count) | 4 | Listed for review; the app adds operators per machine
A3 | 6 | Grade checker | 0.5
A3 | 7 | Foreman | 0.5
A3 | 7 | Operator (auto: follows machine count) | 5 | Listed for review; the app adds operators per machine
A3 | 7 | Grade checker | 0.5
A3 | 8 | Foreman | 1
A3 | 8 | Operator (auto: follows machine count) | 5 | Listed for review; the app adds operators per machine
A3 | 8 | Grade checker | 1
A4 | 1 | Foreman | 0.25
A4 | 1 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A4 | 2 | Foreman | 0.25
A4 | 2 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A4 | 3 | Foreman | 0.25
A4 | 3 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A4 | 4 | Foreman | 0.5
A4 | 4 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A4 | 5 | Foreman | 0.5
A4 | 5 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A5 | 1 | Foreman | 0.25
A5 | 1 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A5 | 1 | Laborer | 1
A5 | 2 | Foreman | 0.25
A5 | 2 | Operator (auto: follows machine count) | 3 | Listed for review; the app adds operators per machine
A5 | 2 | Laborer | 0.5
A5 | 3 | Foreman | 0.5
A5 | 3 | Operator (auto: follows machine count) | 4 | Listed for review; the app adds operators per machine
A5 | 3 | Laborer | 0.5
A5 | 4 | Foreman | 0.5
A5 | 4 | Operator (auto: follows machine count) | 5 | Listed for review; the app adds operators per machine
A5 | 4 | Laborer | 0.5
A6 | 1 | Foreman | 0.25
A6 | 1 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A6 | 1 | Laborer (spotter) | 0.5
A6 | 2 | Foreman | 0.25
A6 | 2 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A6 | 2 | Laborer (spotter) | 0.5
A6 | 3 | Foreman | 0.25
A6 | 3 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A6 | 3 | Laborer (spotter) | 0.5
A6 | 4 | Foreman | 0.25
A6 | 4 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A6 | 4 | Laborer (spotter) | 0.5
A6 | 5 | Foreman | 0.25
A6 | 5 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A6 | 5 | Laborer (spotter) | 0.5
A6 | 6 | Foreman | 0.25
A6 | 6 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A6 | 6 | Laborer (spotter) | 0.5
A6 | 7 | Foreman | 0.5
A6 | 7 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A6 | 7 | Laborer (spotter) | 0.5
A6 | 8 | Foreman | 0.5
A6 | 8 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A6 | 8 | Laborer (spotter) | 0.5
A6 | 9 | Foreman | 0.5
A6 | 9 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A6 | 9 | Laborer (spotter) | 0.5
A6 | 10 | Foreman | 0.5
A6 | 10 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A6 | 10 | Laborer (spotter) | 0.5
A6 | 11 | Foreman | 0.5
A6 | 11 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A6 | 11 | Laborer (spotter) | 0.5
A7 | 1 | Laborer (spotter) | 0.5
A7 | 2 | Laborer (spotter) | 0.5
A7 | 3 | Laborer (spotter) | 0.5
A7 | 4 | Laborer (spotter) | 0.5
A7 | 5 | Laborer (spotter) | 0.5
A7 | 6 | Laborer (spotter) | 0.5
A7 | 7 | Laborer (spotter) | 0.5
A7 | 8 | Laborer (spotter) | 0.5
A7 | 9 | Laborer (spotter) | 0.5
A7 | 10 | Laborer (spotter) | 0.5
A7 | 11 | Laborer (spotter) | 0.5
A8 | 1 | Laborer (dump spotter) | 0.5
A8 | 2 | Laborer (dump spotter) | 0.5
A8 | 3 | Laborer (dump spotter) | 0.5
A8 | 4 | Laborer (dump spotter) | 0.5
A8 | 5 | Laborer (dump spotter) | 0.5
A8 | 6 | Laborer (dump spotter) | 0.5
A8 | 7 | Laborer (dump spotter) | 0.5
A8 | 8 | Laborer (dump spotter) | 0.5
A8 | 9 | Laborer (dump spotter) | 0.5
A8 | 10 | Laborer (dump spotter) | 0.5
A8 | 11 | Laborer (dump spotter) | 0.5
A9 | 1 | Foreman | 0.25
A9 | 1 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A9 | 1 | Laborer | 0.5
A9 | 2 | Foreman | 0.5
A9 | 2 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A9 | 2 | Laborer | 0.5
A9 | 3 | Foreman | 0.5
A9 | 3 | Operator (auto: follows machine count) | 3 | Listed for review; the app adds operators per machine
A9 | 3 | Laborer | 1
A9 | 4 | Foreman | 1
A9 | 4 | Operator (auto: follows machine count) | 4 | Listed for review; the app adds operators per machine
A9 | 4 | Laborer | 1
A10 | 1 | Operator (auto: follows machine count) | 1 | Listed for review; the app adds operators per machine
A10 | 1 | Foreman | 0.25
A10 | 2 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A10 | 2 | Foreman | 0.5
A11 | 1 | Foreman | 0.25
A11 | 1 | Operator (auto: follows machine count) | 1.5 | Listed for review; the app adds operators per machine
A11 | 1 | Laborer | 2
A11 | 2 | Foreman | 0.5
A11 | 2 | Operator (auto: follows machine count) | 1.5 | Listed for review; the app adds operators per machine
A11 | 2 | Laborer | 2
A11 | 2 | Grade checker | 0.5
A11 | 3 | Foreman | 1
A11 | 3 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A11 | 3 | Laborer | 2
A11 | 4 | Foreman | 1
A11 | 4 | Operator (auto: follows machine count) | 2.5 | Listed for review; the app adds operators per machine
A11 | 4 | Laborer | 2
A11 | 4 | Grade checker | 1
A12 | 1 | Foreman | 1
A12 | 1 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A12 | 1 | Pipelayer | 2
A12 | 1 | Laborer | 2
A12 | 2 | Foreman | 1
A12 | 2 | Operator (auto: follows machine count) | 2 | Listed for review; the app adds operators per machine
A12 | 2 | Laborer | 4
A12 | 3 | Foreman | 1
A12 | 3 | Operator (auto: follows machine count) | 4 | Listed for review; the app adds operators per machine
A12 | 3 | Laborer | 5
A12 | 4 | Foreman | 1
A12 | 4 | Operator (auto: follows machine count) | 4 | Listed for review; the app adds operators per machine
A12 | 4 | Laborer | 6

## Catalog gaps
Equip_ID | Machine | Missing in catalog | Effect if used | Enter once in Settings > Equipment library
WT-4000 | Water truck 4,000 gal | Fuel gal/hr; mob (self-propelled) | Line shows "No data" for fuel; mob needs a quote or "none" | Company fuel gal/hr; confirm mob none (drives itself)
WT-8000-ADT | Water truck 8,000 gal ADT | Fuel gal/hr | Fuel "No data" | Company fuel gal/hr
ADT-40T | ADT 40 t | Fuel gal/hr | Not used; 30 t trucks used instead | Enter fuel, then swap 3 x 30 t for 2 x 40 t where you prefer (old sheet used 40 t)
CP-SD-84-PAD | 84 in padfoot roller | Fuel gal/hr | Not used; 84 in smooth used | Enter fuel, then swap for cohesive (clay) fill
CP-TRENCH-ROLLER | Trench roller | Fuel gal/hr | Optional row in pipe crews | Company fuel gal/hr
CP-PLATE-REV | Reversible plate | Fuel gal/hr | Optional row in pipe crews | Company fuel gal/hr
CP-TAMP-815 / 825 | Tamping compactors | Production (D) | No capacity check on those Place and compact tiers | Nothing needed for pricing
DT-OP-3AXLE | Hired tri-axle | Minimum hours | Advisory only | Company minimum (often 4 hr)
TRK-PU-* | Pickups | All rates (D) | Left out of every spread | Add a company pickup with your rate if you price pickups in crews
PV-STABILIZER-WR2400 | Soil stabilizer / reclaimer | All rates | Stabilization left unmapped | Enter a rate to build a stabilization activity, or keep subcontracting

## Old sheet
From Crew_Assemley_DE_LLC V12 | Kept / dropped | How it is used here
Spreads for Cut to Fill, Strip, Respread, Import, Export, Hammer Hoe, Ripping, Finegrade, Storm/Sewer pipe | Kept | Anchors for the tiers marked "Old sheet", translated to catalog size classes and split into excavate / place
Quantity ranges (0-42k / 42-84k / 84-126k / >126k CY) and the production ladder | Kept | Default production by job quantity, extended down to 250/day for small jobs
Fractional machines and crew (1/2 water truck, 1/4 foreman) | Kept | Decimal counts in spreads
10-hour work day | Kept | Basis of every production per day
Typed-over equipment rates in crew tabs (e.g. CAT 330 $65/hr vs $142.80 list) | Dropped | National catalog rates; company rates go in as overrides
Fuel at $4 in the Equipment sheet vs $5 in crews | Dropped | Fuel price is an estimate setting
Labour rates x 0.93 | Dropped | Wage set rates
2021 burden worksheet | Dropped | Wage Calculator burden
"Labor Hours" output (crew $/CY / $166.11) | Dropped | Labour and equipment priced separately
Cut to Fill > 126k CY (highway trucks) tab | Dropped | Counts were mostly 0; top tiers are drafts
Pickups in every crew | Dropped | No catalog rate (see Catalog gaps)

## Catalog ref
Equip_ID | Type | Size class | Rent day | Rent week | Rent 4-week | Rent grade | Operated $/hr | Owned $/hr ex-fuel | Fuel type | Fuel gal/hr med | Transport class | Mob one way @50 mi
ADT-25T | Articulated dump truck (ADT) | 26.5 t payload | 1882 | 5223 | 14259 | A |  |  | diesel | 4.56 | lowboy-permitted | 1800
ADT-30T | Articulated dump truck (ADT) | 30 t payload | 2126 | 5764 | 15715 | A |  |  | diesel | 4.38 | lowboy-permitted | 1800
AT-BRK-20T | Attachment | Hydraulic breaker for 20-30 t excavator | 1050 | 2575 | 6400 | A |  |  | none (attachment) | 0 | flatbed | 400
AT-BRK-36T | Attachment | Hydraulic breaker for ~36 t excavator (HB-3100) | 1600 | 3975 | 9900 | B |  |  | none (attachment) | 0 | flatbed | 400
AT-GPS-DOZER | Attachment | GPS/machine-control kit for dozer | 560 | 1670 | 5000 | B |  |  | none (attachment) | 0 | flatbed | 400
BH-STD-14FT | Backhoe loader | Standard 14-15 ft dig (90-103 hp) | 500 | 1250 | 3735 | A |  | 104.69 | diesel | 1.46 | lowboy-legal | 550
CP-PLATE-REV | Plate compactor | ~800-1,100 lb reversible plate | 240 | 821 | 2418 | A |  |  | diesel |  | pickup-towed | 200
CP-SD-84-SM | Single-drum vibratory roller | 84 in smooth | 700 | 1988 | 5083 | A |  |  | diesel | 2.91 | lowboy-legal | 550
CP-TAMP-815 | Wheeled soil compactor (tamping) | Cat 815 (~249 hp) | 2629 | 7623 | 22107 | B |  |  | diesel | 6.84 | lowboy-permitted | 1800
CP-TAMP-825 | Wheeled soil compactor (tamping) | Cat 825 (~405 hp) | 4034 | 11697 | 33922 | B |  |  | diesel | 10.06 | lowboy-permitted | 1800
CP-TRENCH-ROLLER | Trench roller | ~32-33 in, ~3,200 lb | 298 | 1030 | 3090 | A |  |  | diesel |  | tilt-trailer | 500
CTL-LARGE | Skid steer / CTL | ROC >3,000 lb | 500 | 1700 | 4200 | A |  | 50.3 | diesel | 3.3 | tilt-trailer | 500
DT-OP-3AXLE | On-road dump truck | 3-axle (tri-axle), operated |  |  |  | A | 106.14 |  | diesel |  | self-propelled
DZ-CRAWL-D3 | Crawler dozer | D3 class (~100-104 hp, 20-24k lb) | 875 | 2629 | 6900 | A |  | 57.12 | diesel | 1.93 | lowboy-legal | 550
DZ-CRAWL-D4 | Crawler dozer | D4 class (~130 hp, ~30k lb) | 1142 | 3062 | 8302 | A |  | 76.27 | diesel | 2.85 | lowboy-legal | 550
DZ-CRAWL-D5 | Crawler dozer | D5 class (~170 hp, ~40k lb) | 1554 | 4210 | 11461 | A |  | 94.42 | diesel | 4.12 | lowboy-legal | 550
DZ-CRAWL-D6 | Crawler dozer | D6 class (~215-240 hp, ~50k lb) | 2111 | 5730 | 15656 | A |  | 117.51 | diesel | 4.82 | lowboy-legal | 550
DZ-CRAWL-D8 | Crawler dozer | D8 class (~363 hp) | 4170 | 12092 | 35066 | B |  | 182.04 | diesel | 8.59 | lowboy-permitted | 1800
EX-CRAWL-17T | Hydraulic excavator | 16-18 t (~38,000-40,000 lb) | 855 | 2463 | 6513 | A |  | 91.14 | diesel | 2.97 | lowboy-legal | 550
EX-CRAWL-20T | Hydraulic excavator | 20-25 t (~48,500-62,800 lb) | 1040 | 2927 | 7950 | A |  | 97.76 | diesel | 2.78 | lowboy-legal | 550
EX-CRAWL-30T | Hydraulic excavator | 30-36 t (~68,000-81,000 lb) | 1424 | 4019 | 10850 | A |  | 134.52 | diesel | 4.5 | lowboy-permitted | 1800
EX-CRAWL-50T | Hydraulic excavator | 45-55 t (~105,000-108,000 lb) | 2250 | 5600 | 14000 | A |  | 174.5 | diesel | 8.02 | multi-axle-heavy | 1913
EX-CRAWL-70T | Hydraulic excavator | 65-75 t (~145,000-163,000 lb) | 3950 | 10690 | 29160 | A |  | 212.07 | diesel | 9.95 | multi-axle-heavy | 1913
GR-12FT-140 | Motor grader | 12 ft (Cat 140) | 1949 | 5652 | 16389 | B |  | 146.12 | diesel | 3.53 | lowboy-legal | 550
GR-14FT-160 | Motor grader | 14 ft (Cat 160) | 2085 | 6046 | 17533 | B |  | 215.18 | diesel | 4.45 | lowboy-legal | 550
TB-STL-8x20 | Trench box / shield | Steel trench box 8x20 | 219 | 635 | 1842 | B |  |  | none | 0 | flatbed | 400
WL-COMPACT-1Y | Wheel loader | ~1-1.25 yd (~68-75 hp) | 400 | 1200 | 3240 | A |  | 55.34 | diesel | 0.75 | tilt-trailer | 500
WL-COMPACT-2Y | Wheel loader | 2-2.5 yd (~110 hp) | 675 | 1925 | 4900 | A |  | 79.15 | diesel | 1.16 | tilt-trailer | 500
WL-MED-45Y | Wheel loader | 4.5 yd (~225-250 hp) | 1473 | 4272 | 12387 | B |  | 128.75 | diesel | 3.02 | lowboy-legal | 550
WL-SMALL-3Y | Wheel loader | 3-3.2 yd (~170 hp) | 825 | 2050 | 5500 | A |  | 109.02 | diesel | 2.11 | lowboy-legal | 550
WT-4000 | Water truck / tank | 4,000 gal (6x4) | 1057 | 3067 | 8894 | B |  |  | diesel |  | self-propelled
WT-8000-ADT | Water truck / tank | 8,000 gal ADT-based | 2810 | 8149 | 23631 | B |  |  | diesel |  | lowboy-permitted | 1800
Source: IntelCost Equipment Catalog.xlsx, Equipment sheet, values copied as published. Blank = not in the catalog.

## Catalog production
Key | Equip_ID | Activity_ID | Production /hr (typical) | Unit | Grade | Conditions
CP-SD-84-SM¦EW-COMP-SOIL-8 | CP-SD-84-SM | EW-COMP-SOIL-8 | 265.1684 | CCY/hr | C | Lift 8 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical)
CTL-LARGE¦EW-LOAD-TRK | CTL-LARGE | EW-LOAD-TRK | 70.0188 | LCY/hr | C | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 80 in bucket 0.74 yd3 mapped to 3,500 lb+ ROC (notes mapping); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference
DZ-CRAWL-D3¦EW-PUSH-100 | DZ-CRAWL-D3 | EW-PUSH-100 | 145.3316 | LCY/hr | C | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20
DZ-CRAWL-D5¦EW-PUSH-100 | DZ-CRAWL-D5 | EW-PUSH-100 | 233.7502 | LCY/hr | C | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20
DZ-CRAWL-D6¦EW-PUSH-100 | DZ-CRAWL-D6 | EW-PUSH-100 | 381.1144 | LCY/hr | C | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20
DZ-CRAWL-D8¦EW-PUSH-100 | DZ-CRAWL-D8 | EW-PUSH-100 | 684.4815 | LCY/hr | C | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20
DZ-CRAWL-D8¦EW-RIP | DZ-CRAWL-D8 | EW-RIP | 300 | BCY/hr | C | Low 8,500 fps / typ 6,500 fps / high 5,000 fps seismic velocity; first gear ~1-1.5 mph
EX-CRAWL-17T¦EW-CUTLOAD | EX-CRAWL-17T | EW-CUTLOAD | 153.4978 | BCY/hr | C | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam)
EX-CRAWL-20T¦EW-CUTLOAD | EX-CRAWL-20T | EW-CUTLOAD | 163.344 | BCY/hr | C | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam)
EX-CRAWL-30T¦EW-CUTLOAD | EX-CRAWL-30T | EW-CUTLOAD | 310.752 | BCY/hr | C | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam)
EX-CRAWL-50T¦EW-CUTLOAD | EX-CRAWL-50T | EW-CUTLOAD | 510.9082 | BCY/hr | C | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam)
EX-CRAWL-70T¦EW-CUTLOAD | EX-CRAWL-70T | EW-CUTLOAD | 796.8 | BCY/hr | C | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam)
WL-MED-45Y¦EW-LOAD-TRK | WL-MED-45Y | EW-LOAD-TRK | 425.79 | LCY/hr | C | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 4.5 yd (Wheeler Cat 950 rental line; cat.com 950 rated 4.1)
WL-SMALL-3Y¦EW-LOAD-TRK | WL-SMALL-3Y | EW-LOAD-TRK | 293.322 | LCY/hr | C | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 3.0-3.2 yd rental class
Source: IntelCost Equipment Catalog.xlsx, Production sheet (typical, at the catalog efficiency 0.83). Dozer: 100 ft push. Roller: 8 in lifts. Ripping: indicative, seismic ~6,500 fps.