## README
IntelCost Equipment Catalog - review draft
Built 2026-10-21 from the research notes in 'Construction equipment catalog and rates' (no new research). For review by the Director of Estimating, then for building the Equipment List library and the equipment picker in the Equipment cost component.
How a row is used in the app
1. Pick | User picks Equipment type -> size class (one Equipment row, Equip_ID).
2. Activity | User picks an Activity the machine serves (Equipment.Activities lists the Activity_IDs; Production holds the Equip_ID x Activity_ID rates). Production auto-fills Prod_typical (low/high shown for judgement).
3. Hours | Hours = Quantity / Production (convert BCY/LCY/CCY with Factors section 1). For crew/DOT daily rates: days = Quantity / daily rate; equipment hours = days x shift hours. Duration-based equipment (lifts, cranes, telehandlers, compressors, generators, lights, pumps, shoring, site) has no production rate: duration = the served crew/activity duration (Duration_Norms).
4. Cost | Cost = equipment basis + fuel + operator + mob/demob: - Rental basis: Rent_day/week/4wk (bare, no operator, no fuel), chosen by duration (cheapest combination), x equipment location factor (Settings B8). - Owned basis: Owned_rate_hr_excl_fuel x hours x location factor. - Fuel: Fuel_gal_hr_med (low/high by duty) x hours x user fuel price (Settings B4). Do NOT add fuel to Owned_rate_hr_incl_fuel. - Operator: hours x the project's wage set for Typical_operator_craft (labor). NEVER from this workbook. - Operated rows (Rent_basis = operated: cranes, concrete pumps, dump trucks with driver) already include the operator; do not add labor. - Mob + demob: one-time per move, counted once per resource per project (Mob_Demob; Default_mob_one_way / Default_demob_one_way at Settings B6 miles).
Sheets
README | This page: workflow, column dictionary, confidence legend, rate dates, caveats.
Equipment | One row per equipment size class (628 rows). Rates, fuel, transport, default mob/demob, activities, notes and flags.
Activities | Activity master: unit, norm basis (per hour at 50-min hour vs per 8-hr / working day), method formula, inputs, sources, type (Production / Duration / Quantity).
Production | Equip_ID x Activity_ID (592 rows): Prod_low / typical / high with unit, basis, default conditions, calculation shown, sources, confidence. Calculated rows are live formulas driven by Input_capacity (yellow) and Settings (efficiency, speeds).
Duration_Norms | How duration is derived for duration-based equipment; minimum hours/rental periods; shift/overtime; standby; Caltrans delay/OT factors.
Factors | Soil conversions, fill factors, efficiency, operator, dozer corrections, rolling resistance, cycle components, compaction (16.3), water, grader, fuel factors.
Mob_Demob | Transport classes with $/loaded mile, minimums, permits, escorts; calculator; legal limits; rental delivery norms.
Rental_Terms | Hour limits (8/40/160 vs 176), overtime, multipliers observed, damage waiver, environmental fee, refuel, shift multipliers.
Location | Method (equipment factor / local fuel / wage-set operator) and evidence (RSMeans IL, Blue Book, EIA PADD diesel).
Sources | Source_ID register: title, publisher, edition/date, URL, what it supports.
Gaps | Every missing or weak item with impact and the recommended way to close it; live counts.
Settings | All assumptions referenced by formulas: fuel prices, FEMA back-out diesel price, default mob distance, job efficiency, location factor, fuel factors, multipliers, production speeds. Blue = editable.
Confidence legend (Rent_confidence, Owned_confidence, Production.Confidence)
A (green) | Sourced from 2+ sources that are not derived from each other; median used (per-source values in Notes). ScaffoldExchange (cites Sunbelt/URI/BigRentz) does not count as independent of COSTARS or BigRentz; broad DOZR bands (60-120, 120-180 ft) are not counted as class sources.
B (blue) | Single source, or several sources that are not independent (value as published; FEMA rows are B).
C (amber) | Derived by a stated method: interpolation between adjacent sourced classes (never extrapolated), week/4-week from day by the Settings multipliers, fuel back-out, HP x 0.0486 x load factor, or production calculated from documented formulas. Method is written in Notes / Calc_shown.
D (grey) | No basis. Rate cell left blank; Flags says 'Needs rate' (or 'Needs fuel gal/hr' / input needed). Production rows become D whenever their driving input is blank.
Column dictionary - Equipment
Equip_ID | Stable readable key (TYPE-SUBTYPE-SIZE). Never reuse a retired ID.
Category / Type / Sub_type / Size_class | Picker hierarchy.
Defining_spec / Spec_value / Spec_unit | The spec that defines the class (operating weight, net HP, bucket, ROC, drum width, platform height, capacity...).
Example_models | Representative models from the sources (not an endorsement).
Operating_weight_lb / Net_HP | Representative values from notes (blank = not in notes).
Capacity / Platform_or_lift_height_ft | Bucket/payload/lift capacity; platform height (lifts), lift height (telehandlers).
Fuel_type | diesel / gas / electric / dual / hybrid / propane / none.
Typical_operator_craft | Craft label only - wages come from the project wage set.
Default_billing_basis | day/wk/4wk (bare rental), hr (operated or owned), 4wk/month, LF etc.
Rent_day / Rent_week / Rent_4wk | Bare rental (no operator, no fuel), USD. 4-week = 28 days (Wheeler 176 hr, others 160 hr).
Rent_low_4wk / Rent_high_4wk | Lowest/highest 4-week value across the sources used. For a single source they are blank, EXCEPT where that one source publishes its own range (office trailers, containers, fence, tower crane, rentd compressors) - then they hold that range (see Notes).
Rent_basis | bare or operated.
Rent_hr_operated / Operated_min_hr | ADDED columns: operated hourly rate (includes operator/driver) and minimum billed hours, for cranes, pumps and dump trucks.
Rent_source_ids / Rent_date / Rent_confidence | Source IDs (Sources sheet), vintage, A-D.
FEMA_code / Owned_rate_hr_incl_fuel / Owned_rate_year | FEMA 2025 published hourly (ownership + operating + fuel; operator excluded).
Fuel_gal_hr_low/med/high / Fuel_source | Cat VisionLink Dec 2022 (50/30/10% idle) or derived HP x fuel factor x load factor (C).
Owned_rate_hr_excl_fuel | Formula = incl-fuel - Fuel_gal_hr_med x Settings B5 (EIA 2025 diesel $3.660). Example D6: 135.15 - 4.82 x 3.66 = 117.51.
Owned_confidence | Confidence of Owned_rate_hr_incl_fuel: B for FEMA as published; C for interpolated; D when blank.
Owned_excl_fuel_confidence | ADDED: confidence of Owned_rate_hr_excl_fuel (always C = derived fuel back-out when present; D when blank).
Standby_rule | Owned standby (USACE / Caltrans class delay factor), rental and FEMA rules.
Transport_class | self-propelled / pickup-towed / tilt-trailer / flatbed / lowboy-legal / lowboy-permitted / multi-axle-heavy / crane-assembled / delivered-by-supplier.
Transport_weight_lb / Transport_width_ft / Permit_likely | Operating weight used as transport weight; width only where sourced; Y/N/maybe from legal limits (80,000 lb, 8'6").
Default_mob_one_way / Default_demob_one_way | Formulas from Mob_Demob typical columns at Settings B6 miles; blank where the class is quote-only or self-propelled.
Activities | Comma list of Activity_IDs.
Notes / Flags | Every derivation is described in Notes; Flags list Needs rate / Needs fuel / FEMA ⚠ / label corrections.
Rate dates
Rental (earthwork, support) | Dealer sheets 2025 (Wheeler UT Mar 2025; Columbus OH Jun 2025; Burris IL Mar 2025; RTL MN Spring 2025; Nu-Way MO Jan 2025) and Ahearn MA (read Oct 2026); DOZR Mar 2026; rentd Jul 2026.
Rental (aerial) | Mixed: Sunbelt PA COSTARS contract caps 3/2023-3/2024; BigRentz Dec 2022 data; DOZR Mar 2026; ScaffoldExchange Sep 2026. Older figures likely understate 2026.
Operated | Cranes NTX 2025, Dependable Oct 2025, CFCS Jun 2026; pumps Ohio (read Oct 2026), CCE Mar 2026; dump trucks MN DLI May 1 2026, dumptruckrates Sep 2026.
Owned | FEMA 2025 schedule (declarations on/after Jul 1 2025). Fuel: Cat VisionLink Dec 2022. Back-out diesel: EIA 2025 average.
Fuel price default | EIA US on-highway diesel week of Oct 19 2026 = $6.276/gal (Settings B4).
Key caveats
Rental sample | Leans Midwest / Mountain West (UT, OH, IL, MN, MO, MA). No TX/CA/FL bare earthwork sheets. Wheeler (Cat dealer) is consistently the high end; medians used.
Aerial rates | Partly 2022-2024; COSTARS day rates are contract ceilings. Spider/track lifts use COSTARS 'atrium' classes.
FEMA ⚠ | Suspect FEMA values are kept as published and flagged (generators 17-45 kW, pickups, BW120, 13 CY mixer, small pumps, 125 ft boom, V120 trencher, 19 in chipper, 130 CFM compressor). Verify against the PDF. FEMA 8636 'Scraper, Wirtgen WR2400' corrected to stabilizer/recycler.
Fuel back-out | FEMA's embedded diesel price is not published; EIA 2025 average assumed. Gas/LPG FEMA rows have no ex-fuel value (no gasoline basis in notes).
Production | Cat dozer push curves were not obtained: dozer rows use the Peurifoy blade/cycle method with Cat SAE J1265 blade capacities (specs_fill) and Settings dozing speeds (D9-D11 use their published gear speeds). Excavator buckets: typical = midpoint of the GP range from Deere/Komatsu/Cat specs (C); minis 1-2 t and 5-6 t, 45-50 t long-reach etc. stay D (no bucket published). Haul and scraper rows stay D until Settings B22-B27 average speeds are entered (specs give only top speeds and one rimpull worked example, not average haul speeds). DOT daily rates are crew/spread outcomes (include delays), not single-machine output.
Location | Equipment location factor 0.85-1.15 is an inference from RSMeans IL and Blue Book. Never apply the labor factor to equipment.
Mob/demob | Haul $/mile from one trade publisher (2026, high-diesel period). Load/unload hours not sourced (excluded).
Interpolation | C-rated interpolations are linear between adjacent sourced classes and never extrapolated.
Non-monotonic steps | Where a smaller class costs more than the next larger one (or fuel/ex-fuel inverts), the source data is kept and the row is flagged 'Non-monotonic vs <ID> - source data'.
Rounding | All hard-coded medians use half-up rounding (Excel ROUND). A few values differ by 1 from the research-notes tables, which used banker's rounding; those rows say so in Notes.
Out of scope | Snow & ice equipment (FEMA 8450-8458, 8549-8565), aircraft/helicopters/drones (8900-8916), marine (barges, tow/push/tug boats, airboats), fire apparatus, ambulances, buses, police and garbage vehicles are intentionally excluded. Log skidders, blowers, grizzly feeders, leaf vac and vans also have no rows (FEMA rates not captured).
IDs | A few IDs contain lowercase 'x' (box sizes, e.g. TB-STL-8x12) or '_' (GEN-5_5). Kept unchanged because IDs are stable keys.
Colours
Blue font | Sourced hard-coded value / editable input
Black font | Formula or text
Yellow fill | Input cell (Settings, Production Input_capacity)
Grey/white bands | Alternate categories on Equipment columns A-E
Red bold flag | FEMA ⚠ value

## Equipment
Equip_ID | Category | Type | Sub_type | Size_class | Defining_spec | Spec_value | Spec_unit | Example_models | Operating_weight_lb | Net_HP | Capacity | Platform_or_lift_height_ft | Fuel_type | Typical_operator_craft | Default_billing_basis | Rent_day | Rent_week | Rent_4wk | Rent_low_4wk | Rent_high_4wk | Rent_basis | Rent_hr_operated | Operated_min_hr | Rent_source_ids | Rent_date | Rent_confidence | FEMA_code | Owned_rate_hr_incl_fuel | Owned_rate_year | Fuel_gal_hr_low | Fuel_gal_hr_med | Fuel_gal_hr_high | Fuel_source | Owned_rate_hr_excl_fuel | Owned_confidence | Owned_excl_fuel_confidence | Standby_rule | Transport_class | Transport_weight_lb | Transport_width_ft | Permit_likely | Default_mob_one_way | Default_demob_one_way | Activities | Notes | Flags
DZ-CRAWL-D1 | Earthwork | Crawler dozer | Small (Cat D1-D3) | D1 class (~80 hp) | Net HP | 80 | hp | Cat D1 (formerly D3K2) | 17855 | 80 | Blade Cat D1 std blade 1.99 yd3 (LGP 2.17) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8250 | 47.73 | FEMA 2025 | 1.36 | 1.79 | 2.33 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 41.18 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 17855 |  | N | 500 | 500 | EW-STRIP,EW-PUSH-100,EW-SPREAD,EW-RGRADE | Weight/HP Ziegler. Max speeds F 5.6 / R 6.2 mph (hydrostatic) [CAT-DOZ-PG]; production uses Settings dozing speeds because no working-speed reduction is sourced. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
DZ-CRAWL-D2 | Earthwork | Crawler dozer | Small (Cat D1-D3) | D2 class (85+ hp) | Net HP (min) | 85 | hp | Cat D2 (formerly D4K2; 92 hp, 18,382 lb) | 18382 | 92 | Blade Cat D2 std 2.59 yd3 (LGP 2.42) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  | 55.96 | FEMA 2025 (interpolated) | 1.56 | 2.06 | 2.68 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 48.42 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 18382 |  | N | 500 | 500 | EW-STRIP,EW-PUSH-100,EW-SPREAD,EW-RGRADE | Only the Cat minimum HP (85+) is sourced (Carter); no weight, HP, fuel or rates. Specs from Western States Cat D2 page [CAT-DOZ-PG]. Owned_rate_hr_incl_fuel interpolated (C) between DZ-CRAWL-D1 and DZ-CRAWL-D3 by Net HP (FEMA 2025 endpoints). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
DZ-CRAWL-D3 | Earthwork | Crawler dozer | Small (Cat D1-D3) | D3 class (~100-104 hp, 20-24k lb) | Net HP | 104 | hp | Cat D3; Komatsu D39EX/PX; Develon DD100/130 | 20640 | 104 | Blade Cat D3 std 2.86 yd3 (LGP 3.06) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 875 | 2629 | 6900 | 5413 | 7623 | bare |  |  | W25;C25;R25 | 2025-2026 | A | 8251 | 64.18 | FEMA 2025 | 1.51 | 1.93 | 2.36 | Cat VisionLink Dec 2022, model D3-12 [CATFUEL22] | 57.12 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 20640 |  | N | 550 | 550 | EW-STRIP,EW-PUSH-100,EW-PUSH-200,EW-SPREAD,EW-RGRADE | Operating weight given only as 20,000-24,000 lb class band (rental notes); transport class set manually. Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 3 sources (W 906/2629/7623; C 875/2175/5412; R 850/2850/6900). Class mapping D39->D3, DD100/130->D3 per notes. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
DZ-CRAWL-D4 | Earthwork | Crawler dozer | Medium (Cat D4-D7) | D4 class (~130 hp, ~30k lb) | Net HP | 130 | hp | Cat D4 (formerly D6K2); Komatsu D51EX/PX | 29259 | 130 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 1142 | 3062 | 8302 | 7075 | 9529 | bare |  |  | W25;C25 | 2025-2026 | A | 8252 | 86.7 | FEMA 2025 | 2.19 | 2.85 | 3.5 | Cat VisionLink Dec 2022, model D4-16 [CATFUEL22] | 76.27 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 29259 |  | N | 550 | 550 | EW-CLR-MED,EW-STRIP,EW-PUSH-100,EW-PUSH-200,EW-SPREAD,EW-RGRADE | Rent: Median (=mean) of 2 sources: W 1133/3286/9529; C 1150/2838/7075. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
DZ-CRAWL-D5 | Earthwork | Crawler dozer | Medium (Cat D4-D7) | D5 class (~170 hp, ~40k lb) | Net HP | 170 | hp | Cat D5 LGP VPAT; Komatsu D61EX/PX | 42263 | 170 | Blade Cat D5 VPAT 4.6 yd3 (LGP VPAT 5.5; push-arm SU 5.6) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 1554 | 4210 | 11461 | 9200 | 13721 | bare |  |  | W25;C25 | 2025-2026 | A |  | 109.5 | FEMA 2025 (interpolated) | 3.18 | 4.12 | 5.06 | Cat VisionLink Dec 2022, model D5-17 [CATFUEL22] | 94.42 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 42263 |  | N | 550 | 550 | EW-CLR-MED,EW-STRIP,EW-PUSH-100,EW-PUSH-200,EW-PUSH-300,EW-SPREAD,EW-RGRADE | Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median (=mean) of 2 sources: W 1632/4732/13721; C 1475/3688/9200. Owned_rate_hr_incl_fuel interpolated (C) between DZ-CRAWL-D4 and DZ-CRAWL-D6 by Net HP (FEMA 2025 endpoints). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
DZ-CRAWL-D6 | Earthwork | Crawler dozer | Medium (Cat D4-D7) | D6 class (~215-240 hp, ~50k lb) | Net HP | 215 | hp | Cat D6; Komatsu D71PX | 50733 | 215 | Blade Cat D6 SU 7.5 yd3 (VPAT 5.4; angle 5.5; LGP-36 S 5.0) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2111 | 5730 | 15656 | 12000 | 19312 | bare |  |  | W25;C25 | 2025-2026 | A | 8253 | 135.15 | FEMA 2025 | 3.74 | 4.82 | 5.9 | Cat VisionLink Dec 2022, model D6-20 [CATFUEL22] | 117.51 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 50733 |  | maybe | 550 | 550 | EW-CLR-MED,EW-STRIP,EW-PUSH-100,EW-PUSH-200,EW-PUSH-300,EW-SPREAD,EW-RGRADE | Rent: Median (=mean) of 2 sources: W D6/D6 LGP avg 2296/6659/19312; C D71PX 1925/4800/12000. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
DZ-CRAWL-D6-XE | Earthwork | Crawler dozer | Medium - electric drive (XE) | D6 XE (215 hp) | Net HP | 215 | hp | Cat D6 XE | 51333 | 215 |  |  | hybrid | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 3.59 | 4.6 | 5.61 | Cat VisionLink Dec 2022, model D6-20 XE [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 51333 |  | maybe | 550 | 550 | EW-STRIP,EW-PUSH-100,EW-PUSH-200,EW-PUSH-300,EW-SPREAD,EW-RGRADE | Diesel-electric drive. No rate source; D6 class row is the nearest priced class. | Needs rate; Needs rate (rental); Needs rate (owned)
DZ-CRAWL-D6-LGP | Earthwork | Crawler dozer | Medium - LGP (low ground pressure) | D6 LGP | Track variant | LGP |  | Cat D6 LGP |  |  | Blade Cat D6 LGP SU 7.6 yd3 (LGP VPAT 5.9-6.5) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2372 | 6878 | 19947 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | EW-STRIP,EW-PUSH-100,EW-SPREAD,EW-RGRADE | HP/weight for LGP not in notes. Rent: Wheeler only. | Needs fuel gal/hr; Needs rate (owned)
DZ-CRAWL-D7 | Earthwork | Crawler dozer | Medium (Cat D4-D7) | D7 class (~265 hp) | Net HP | 265 | hp | Cat D7 (formerly D7E) | 65644 | 265 | Blade Cat D7 (Tier 3, MX page) SU 9.7 yd3 (S 8.1) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2973 | 8623 | 25006 |  |  | bare |  |  | W25 | 2025 | B |  | 161.61 | FEMA 2025 (interpolated) | 4.4 | 5.71 | 7.02 | Cat VisionLink Dec 2022, model D7-17 [CATFUEL22] | 140.71 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted | 65644 |  | Y | 1800 | 1800 | EW-CLR-MED,EW-STRIP,EW-PUSH-100,EW-PUSH-200,EW-PUSH-300,EW-SPREAD,EW-RGRADE | Transport set to lowboy-permitted: ~65,600 lb machine + tractor/lowboy exceeds 80,000 lb gross (notes' 36 t excavator reasoning). Rent: Wheeler only. Owned_rate_hr_incl_fuel interpolated (C) between DZ-CRAWL-D6 and DZ-CRAWL-D8 by Net HP (FEMA 2025 endpoints). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
DZ-CRAWL-D8 | Earthwork | Crawler dozer | Large (Cat D8-D11) | D8 class (~363 hp) | Net HP | 363 | hp | Cat D8 (D8T) | 87083 | 363 | Blade Cat D8 SU 13.47 yd3 (LGP SU 12.9) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 4170 | 12092 | 35066 |  |  | bare |  |  | W25 | 2025 | B | 8254 | 213.48 | FEMA 2025 | 6.54 | 8.59 | 10.64 | Cat VisionLink Dec 2022, model D8-21 / D8T [CATFUEL22] | 182.04 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted | 87083 |  | Y | 1800 | 1800 | EW-CLR-HVY,EW-PUSH-100,EW-PUSH-200,EW-PUSH-300,EW-SPREAD,EW-RIP | Ziegler lists D8 as Medium, Carter as Large; Large used (Carter rename grouping). Rent: Wheeler only. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
DZ-CRAWL-D9 | Earthwork | Crawler dozer | Large (Cat D8-D11) | D9 class (~452 hp) | Net HP | 452 | hp | Cat D9 | 110205 | 452 | Blade Cat D9 SU 17.8 yd3 (U 21.7) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8255 | 360.3 | FEMA 2025 | 7.93 | 10.38 | 12.82 | Cat VisionLink Dec 2022, model D9-07 [CATFUEL22] | 322.31 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 110205 |  | Y | 1913 | 1913 | EW-CLR-HVY,EW-PUSH-100,EW-PUSH-200,EW-PUSH-300,EW-RIP | Weight not in notes; transport set per mob notes ('D9+' multi-axle). Weight from cat.com (D9 110,205-111,362 lb) [CAT-DOZ-PG]. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
DZ-CRAWL-D10 | Earthwork | Crawler dozer | Large (Cat D8-D11) | D10 class (~602 hp) | Net HP | 602 | hp | Cat D10 (D10T2) | 154888 | 602 | Blade Cat D10 10SU 24.2 yd3 (10U 28.7) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  | 431.85 | FEMA 2025 (interpolated) | 11.46 | 15.09 | 18.73 | Cat VisionLink Dec 2022, model D10T2 [CATFUEL22] | 376.62 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 154888 |  | Y | 1913 | 1913 | EW-PUSH-100,EW-PUSH-200,EW-PUSH-300,EW-RIP | Rental quoted on request only (Wheeler). Weight from cat.com (D9 110,205-111,362 lb) [CAT-DOZ-PG]. Owned_rate_hr_incl_fuel interpolated (C) between DZ-CRAWL-D9 and DZ-CRAWL-D11 by Net HP (FEMA 2025 endpoints). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
DZ-CRAWL-D11 | Earthwork | Crawler dozer | Large (Cat D8-D11) | D11 class (~850 hp) | Net HP | 850 | hp | Cat D11 | 235507 | 850 | Blade Cat D11 SU 35.6 yd3 (U 45; reclamation U 55; carrydozer 57) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8256 | 550.14 | FEMA 2025 | 15.45 | 20.52 | 25.59 | Cat VisionLink Dec 2022, model D11-07 [CATFUEL22] | 475.04 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 235507 |  | Y | 1913 | 1913 | EW-PUSH-100,EW-PUSH-200,EW-PUSH-300,EW-RIP | Rental quoted on request only (Wheeler). Weight from cat.com (D9 110,205-111,362 lb) [CAT-DOZ-PG]. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
DZ-WHEEL-814 | Earthwork | Wheel dozer | Rubber-tired dozer | Cat 814 class (~249 hp) | Net HP | 249 | hp | Cat 814 |  | 249 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8260 | 101.21 | FEMA 2025 | 4.24 | 5.57 | 7.26 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 80.82 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-PUSH-100,EW-PUSH-200,EW-SPREAD | Weight not in notes; transport class assumed permitted (verify). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
DZ-WHEEL-824 | Earthwork | Wheel dozer | Rubber-tired dozer | Cat 824 class (~405 hp) | Net HP | 405 | hp | Cat 824 | 74966 | 405 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8261 | 170.28 | FEMA 2025 | 6.89 | 9.05 | 11.81 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 137.16 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted | 74966 |  | Y | 1800 | 1800 | EW-PUSH-100,EW-PUSH-200,EW-SPREAD | Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
DZ-WHEEL-834 | Earthwork | Wheel dozer | Rubber-tired dozer | Cat 834 class (~496 hp) | Net HP | 496 | hp | Cat 834 | 105271 | 496 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8262 | 308.97 | FEMA 2025 | 8.44 | 11.09 | 14.46 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 268.38 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 105271 |  | Y | 1913 | 1913 | EW-PUSH-100,EW-PUSH-200,EW-SPREAD | Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
DZ-WHEEL-844 | Earthwork | Wheel dozer | Rubber-tired dozer | Cat 844 class (~732 hp) | Net HP | 732 | hp | Cat 844 |  | 732 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8263 | 402.76 | FEMA 2025 | 12.45 | 16.36 | 21.35 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 342.88 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy |  |  | Y | 1913 | 1913 | EW-PUSH-100,EW-PUSH-200,EW-SPREAD | Weight not in notes; transport class assumed permitted (verify). Transport set to multi-axle-heavy for consistency with the lighter 834 (105,271 lb); 844 weight not in notes. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
DZ-WHEEL-854 | Earthwork | Wheel dozer | Rubber-tired dozer | Cat 854 class (~814 hp) | Net HP | 814 | hp | Cat 854 | 224647 | 814 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 13.85 | 18.2 | 23.74 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 224647 |  | Y | 1913 | 1913 | EW-PUSH-100,EW-PUSH-200,EW-SPREAD | Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned)
EX-MINI-1T | Earthwork | Hydraulic excavator | Mini/compact 1-2 t | 1-2 t (<=5,000 lb) | Operating weight | 3913 | lb | Cat 300.9D (2,061 lb, 13 hp), 301.5 (3,913 lb, 21 hp), 301.7 CR, 301.8, 302 CR; Kubota K008; Bobcat E10/E20 | 3913 | 21 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 237 | 748 | 2200 | 1665 | 2913 | bare |  |  | W25;B25;R25;N25;A26;DOZR-EX | 2025-2026 | A |  |  |  | 0.36 | 0.47 | 0.61 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 3913 |  | N | 500 | 500 | EW-TRENCH-5,EW-STRUCT,EW-BACKFILL | Representative model 301.5 (3,913 lb, 21 hp) used for weight/HP. Tail swing (zero/reduced/conventional) does not change the rate class. No FEMA code below 45 hp; not extrapolated. Tail swing: zero / minimal (<10% overhang) / conventional variants exist [BOBCAT-EX]; not priced separately by the rental sources. Max dig depth: Deere 17 P 7'2" [DEERE-RENT; CAT-EXC-PG]. Rent: Median of 6 sources (W 346/1004/2913; B 248/745/2235; R 200/750/2200; N 190/665/1665; A 300/900/2200; D 225/675/1775). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate (owned)
EX-MINI-3T | Earthwork | Hydraulic excavator | Mini/compact 3-4 t | 3-4 t (5,000-10,000 lb) | Operating weight | 9867 | lb | Cat 302.7 CR, 303 CR, 303.5 CR, 304 (9,867 lb, 45 hp); Kubota KX033/KX040; Bobcat E26/E35/E42 | 9867 | 45 | GP bucket 0.15 yd3 (typ; Deere 35G spec-basis bucket 0.11 m3 (0.15 yd3); single value, not a range) |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 325 | 1013 | 2788 | 2250 | 4438 | bare |  |  | W25;C25;B25;R25;N25;A26;DOZR-EX | 2025-2026 | A |  |  |  | 0.77 | 1.01 | 1.31 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 9867 |  | N | 500 | 500 | EW-TRENCH-5,EW-STRUCT,EW-BACKFILL,UT-PIPE-WATER | Representative model Cat 304 (9,867 lb, 45 hp). FEMA 8280 (305 CR) caps at 45 hp but is mapped to the 5-6 t class; not reused here. Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Tail swing: zero / minimal (<10% overhang) / conventional variants exist [BOBCAT-EX]; not priced separately by the rental sources. Max dig depth: Cat 303.5 CR 110.6-122.4 in; Deere 35G 10'0"; Kubota KX040-4 11.23 ft [DEERE-RENT; CAT-EXC-PG]. Rent: Median of 7 sources (W 528/1530/4438; C 375/912/2250; B 310/930/2790; R 307/1215/3190; N 290/1012/2788; A 375/1075/2625; D 325/975/2550). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate (owned)
EX-MINI-5T | Earthwork | Hydraulic excavator | Mini/compact 5-6 t | 5-6 t (10,000-14,000 lb) | Operating weight | 12688 | lb | Cat 305 CR (12,688 lb, 45 hp, 12 ft dig), 306 CR; Kubota KX057; Case CX55; Bobcat E50/E60 | 12688 | 45 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 443 | 1319 | 3228 | 2950 | 6226 | bare |  |  | W25;C25;B25;R25;N25;A26 | 2025-2026 | A | 8280 | 57.14 | FEMA 2025 | 1.15 | 1.55 | 1.94 | Cat VisionLink Dec 2022, model 305-07 CR [CATFUEL22] | 51.47 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 12688 |  | N | 500 | 500 | EW-TRENCH-5,EW-TRENCH-10,EW-STRUCT,EW-BACKFILL,UT-PIPE-WATER | Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Tail swing: zero / minimal (<10% overhang) / conventional variants exist [BOBCAT-EX]; not priced separately by the rental sources. Max dig depth: Cat 305 CR 134.6-144.5 in; Deere 50 P 11'7"; Bobcat E50 11.4 ft [DEERE-RENT; CAT-EXC-PG]. Rent: Median of 6 sources (W 740/2147/6226; C 488/1212/3000; B 370/1110/3330; R 410/1672/3798; N 335/1175/2950; A 475/1425/3125). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
EX-MIDI-8T | Earthwork | Hydraulic excavator | Midi 7-8 t (nominal 8 t) | 7-8 t nominal (~15,400-19,800 lb) | Operating weight | 18493 | lb | Cat 307.5 (17,905 lb), 308 CR (18,493 lb, 69.5 hp); Komatsu PC88MR (19,225 lb); Kubota KX080; Bobcat E88 | 18493 | 69.5 | GP bucket 0.26 yd3 (typ; Komatsu PC88MR-11 single listed bucket 0.26 yd3 (aggregator)) |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 600 | 1798 | 4498 | 3780 | 6924 | bare |  |  | W25;C25;B25;R25 | 2025 | A |  | 77.76 | FEMA 2025 (interpolated) | 0.68 | 0.95 | 1.22 | Cat VisionLink Dec 2022, model 308-07 CR [CATFUEL22] | 74.28 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 18493 |  | N | 500 | 500 | EW-CUTLOAD,EW-MASS,EW-TRENCH-5,EW-TRENCH-10,EW-STRUCT,EW-BACKFILL,UT-PIPE-STORM,DM-PAVE-CONC | Cat 308-07 CR fuel (0.95 med) is below the 305 CR (1.55) in the source; reproduced as published. Split in revision from the notes' 8-10 t class (Bobcat 7-8 / 9-10 t classes). Tail swing: zero / minimal (<10% overhang) / conventional variants exist in compact classes [BOBCAT-EX]; rental sources do not price them separately. Max dig depth: Deere 85 P 14'10"; PC88MR 15 ft [DEERE-RENT; CAT-EXC-PG]. Rent: Median of 4 sources after split (W 308 823/2388/6924; C PC88MR 650/1600/4000; B KX080/ET90 420/1260/3780; R E88 550/1995/4995). 8.4-8.8 t models assigned to the 7-8 t (nominal 8 t) class. Owned_rate_hr_incl_fuel interpolated (C) between EX-MINI-5T and EX-CRAWL-13T by Net HP (FEMA 2025 endpoints). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Fuel value looks low vs smaller class
EX-MIDI-10T | Earthwork | Hydraulic excavator | Midi 9-10 t | 9-10 t (~19,800-23,000 lb) | Operating weight | 23002 | lb | Cat 309 CR (21,091 lb), 310 (23,002 lb, 69.5 hp, 205.2 in dig) | 23002 | 69.5 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 717 | 2182 | 5843 | 4250 | 7437 | bare |  |  | W25;A26 | 2025-2026 | A |  | 77.76 | FEMA 2025 (interpolated) | 1.18 | 1.55 | 2.03 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 72.09 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 23002 |  | N | 550 | 550 | EW-CUTLOAD,EW-MASS,EW-TRENCH-5,EW-TRENCH-10,EW-STRUCT,EW-BACKFILL,UT-PIPE-STORM | Split from the 8-10 t class in revision. Rent: Mean of 2 sources after split (W 309/310 avg 884.5/2564/7436.5; A 18-25K lb 550/1800/4250). Ahearn 18-25K lb class straddles both midi rows; assigned here. Half-up rounding. Owned_rate_hr_incl_fuel interpolated (C) between EX-MINI-5T and EX-CRAWL-13T by Net HP (FEMA 2025 endpoints). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
EX-CRAWL-13T | Earthwork | Hydraulic excavator | Small 13-15 t | 13-15 t (~30,000-34,000 lb) | Operating weight | 30400 | lb | Cat 313 GC (30,400 lb, 73 hp), 313 (108 hp), 315 GC (34,000 lb); Komatsu PC138USLC; Develon DX140 | 30400 | 90 | GP bucket 0.75 yd3 (typ; midpoint of typical GP 0.5-1.0 yd3 (Deere 135 P HD 0.47-0.99)) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 700 | 2100 | 5250 | 4635 | 8703 | bare |  |  | W25;C25;B25;R25;A26 | 2025-2026 | A | 8281 | 95.01 | FEMA 2025 | 1.49 | 1.9 | 2.31 | Cat VisionLink Dec 2022, model 313-07 GC [CATFUEL22] | 88.06 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 30400 |  | N | 550 | 550 | EW-CUTLOAD,EW-MASS,EW-TRENCH-5,EW-TRENCH-10,EW-STRUCT,EW-BACKFILL,UT-PIPE-STORM,DM-PAVE-CONC | Net_HP = FEMA HP cap (90); Ziegler lists 313 GC at 73 hp. Max dig depth: Deere 135 P 20'0" [DEERE-RENT; CAT-EXC-PG]. Rent: Median of 5 sources (W 1034/3001/8703; C 850/2100/5200; B 515/1545/4635; R 650/2200/5600; A 700/2000/5250). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
EX-CRAWL-17T | Earthwork | Hydraulic excavator | Small 16-18 t | 16-18 t (~38,000-40,000 lb) | Operating weight | 40200 | lb | Cat 317 GC (38,000 lb), 317 (40,200 lb, 133 hp); Komatsu PC170LC; Develon DX170/180 | 40200 | 133 | GP bucket 0.899 yd3 (typ; interpolated by operating weight between EX-CRAWL-13T (30,400 lb, 0.75) and EX-CRAWL-20T (48,500 lb, 1.025)) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 855 | 2463 | 6513 | 5750 | 8766 | bare |  |  | W25;C25;R25;A26 | 2025-2026 | A |  | 102.01 | FEMA 2025 (interpolated) | 2.26 | 2.97 | 3.88 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 91.14 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 40200 |  | N | 550 | 550 | EW-CUTLOAD,EW-MASS,EW-TRENCH-5,EW-TRENCH-10,EW-STRUCT,EW-BACKFILL,UT-PIPE-STORM,DM-PAVE-CONC | Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 4 sources (W 1042/3023/8766; C 950/2375/5900; R 760/2550/7125; A 750/2250/5750). Owned_rate_hr_incl_fuel interpolated (C) between EX-CRAWL-13T and EX-CRAWL-20T by operating weight (FEMA 2025 endpoints). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Non-monotonic vs EX-CRAWL-20T - source data
EX-CRAWL-20T | Earthwork | Hydraulic excavator | Medium 20-25 t | 20-25 t (~48,500-62,800 lb) | Operating weight | 48500 | lb | Cat 320 GC (48,500 lb, 146 hp), 320 (172 hp), 323, 325, 326; Komatsu PC210LC/PC238; Develon DX225/235/255 | 48500 | 150 | GP bucket 1.025 yd3 (typ; midpoint of typical GP 0.75-1.3 yd3 (Deere 210 P 0.56-1.29)) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 1040 | 2927 | 7950 | 6500 | 10259 | bare |  |  | W25;C25;R25;A26 | 2025-2026 | A | 8282 | 107.93 | FEMA 2025 | 2.18 | 2.78 | 3.37 | Cat VisionLink Dec 2022, model 320-07 GC [CATFUEL22] | 97.76 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 48500 |  | maybe | 550 | 550 | EW-CUTLOAD,EW-MASS,EW-TRENCH-5,EW-TRENCH-10,EW-STRUCT,EW-BACKFILL,UT-PIPE-STORM,DM-PAVE-CONC,UT-PIPE-SAN,EW-TRENCH-15 | Max dig depth: Deere 210 P 21'11"; Cat 320 22 ft [DEERE-RENT; CAT-EXC-PG]. Rent: Median of 4 sources (W 1220/3538/10259; C 1162/2888/7200; R 917/2967/8700; A 800/2500/6500). Machine-control 'i' models cost 25-75% more (Columbus PC210LCi 1400/4150/12400). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
EX-CRAWL-30T | Earthwork | Hydraulic excavator | Medium 30-36 t | 30-36 t (~68,000-81,000 lb) | Operating weight | 69200 | lb | Cat 330 (69,200 lb, 273 hp), 330 GC, 335, 336 (81,100 lb, 300 hp); Komatsu PC290/PC360; Develon DX300/350 | 69200 | 201 | GP bucket 1.95 yd3 (typ; midpoint of typical GP 1.4-2.5 yd3 (Deere 345/350 P, Komatsu PC360LC-11)) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 1424 | 4019 | 10850 | 9000 | 14177 | bare |  |  | W25;C25;R25;A26 | 2025-2026 | A | 8283 | 150.99 | FEMA 2025 | 3.51 | 4.5 | 5.49 | Cat VisionLink Dec 2022, model 330-07 GC [CATFUEL22] | 134.52 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted | 69200 | 11.1 | Y | 1800 | 1800 | EW-CUTLOAD,EW-MASS,EW-TRENCH-5,EW-TRENCH-10,EW-STRUCT,EW-BACKFILL,UT-PIPE-STORM,DM-PAVE-CONC,UT-PIPE-SAN,UT-PIPE-STORM-L,EW-TRENCH-15 | Transport width 11.1 ft = Cat 336D L (133.5 in) per RitchieSpecs; >8.5 ft so oversize. Net_HP = FEMA cap (201). Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Max dig depth: Deere 350 P 24'3"-26'10"; Cat 336 26.11 ft [DEERE-RENT; CAT-EXC-PG]. Rent: Median of 4 sources (W 1686/4888/14176; C 1650/4088/10200; R 1198/3950/11500; A 1075/3475/9000). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
EX-CRAWL-40T | Earthwork | Hydraulic excavator | Large 36-45 t | ~40 t (83,000 lb) | Operating weight | 83100 | lb | Cat 340 (83,100 lb, 346 hp) | 83100 | 350 | GP bucket 2.402 yd3 (typ; interpolated by operating weight between EX-CRAWL-30T (69,200 lb, 1.95) and EX-CRAWL-70T (162,900 lb, 5.0)) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 1903 | 5520 | 16008 |  |  | bare |  |  | W25 | 2025 | B | 8284 | 183.84 | FEMA 2025 | 5.32 | 6.96 | 8.61 | Cat VisionLink Dec 2022, model 340-08 [CATFUEL22] | 158.37 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted | 83100 |  | Y | 1800 | 1800 | EW-CUTLOAD,EW-MASS,EW-TRENCH-10,EW-STRUCT,UT-PIPE-STORM-L,EW-TRENCH-15 | Rent: Wheeler 340 only. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Non-monotonic vs EX-CRAWL-50T - source data
EX-CRAWL-50T | Earthwork | Hydraulic excavator | Large 45-55 t | 45-55 t (~105,000-108,000 lb) | Operating weight | 107800 | lb | Cat 349/350/352 (105,100-107,800 lb, 413-443 hp); Komatsu PC490LC | 107800 | 443 | GP bucket 3.206 yd3 (typ; interpolated by operating weight between EX-CRAWL-30T (69,200 lb, 1.95) and EX-CRAWL-70T (162,900 lb, 5.0)) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2250 | 5600 | 14000 | 13500 | 22488 | bare |  |  | W25;C25;A26 | 2025-2026 | A |  | 203.85 | FEMA 2025 (interpolated) | 6.19 | 8.02 | 9.85 | Cat VisionLink Dec 2022, model 352-07 [CATFUEL22] | 174.5 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 107800 |  | Y | 1913 | 1913 | EW-CUTLOAD,EW-MASS,EW-STRUCT | Max dig depth: Cat 352 26.11 ft [DEERE-RENT; CAT-EXC-PG]. Rent: Median of 3 sources (W 2674/7754/22488; C 2250/5600/14000; A 2000/4500/13500). PC490+ may bill set-up/dismantle separately (Columbus). Owned_rate_hr_incl_fuel interpolated (C) between EX-CRAWL-40T and EX-CRAWL-90T by operating weight (FEMA 2025 endpoints). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
EX-CRAWL-70T | Earthwork | Hydraulic excavator | Mass excavation 65-75 t | 65-75 t (~145,000-163,000 lb) | Operating weight | 162900 | lb | Cat 374 (162,900 lb, 484 hp); Komatsu PC650LC (145,000 lb) | 162900 | 484 | GP bucket 5 yd3 (typ; midpoint of typical production bucket 4-6 yd3 (Cat 374 SD 4.32; Deere 870 P 4.56 spec bucket)) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 3950 | 10690 | 29160 | 23000 | 35320 | bare |  |  | W25;C25 | 2025-2026 | A |  | 248.49 | FEMA 2025 (interpolated) | 7.74 | 9.95 | 12.17 | Cat VisionLink Dec 2022, model 374-07 [CATFUEL22] | 212.07 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 162900 |  | Y | 1913 | 1913 | EW-CUTLOAD,EW-MASS | Max dig depth: Cat 374 28.1 ft [DEERE-RENT; CAT-EXC-PG]. Rent: Median (=mean) of 2 sources: W 374 4200/12179/35320; C PC650 3700/9200/23000. (Notes' 65-95 t class split into 65-75 and 90-95 t.) Owned_rate_hr_incl_fuel interpolated (C) between EX-CRAWL-40T and EX-CRAWL-90T by operating weight (FEMA 2025 endpoints). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
EX-CRAWL-90T | Earthwork | Hydraulic excavator | Mass excavation 90-95 t | 90-95 t (~205,000-207,000 lb) | Operating weight | 207400 | lb | Cat 395 (207,400 lb, 542 hp); Komatsu PC900LC (205,000 lb) | 207400 | 550 | GP bucket 6 yd3 (typ; midpoint of typical 5-7 yd3 (Cat 395 SD 6.8)) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 4999 | 13555 | 36988 | 29000 | 44976 | bare |  |  | W25;C25 | 2025-2026 | A | 8285 | 284.54 | FEMA 2025 | 9.6 | 12.45 | 15.3 | Cat VisionLink Dec 2022, model 395-07 [CATFUEL22] | 238.97 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 207400 |  | Y | 1913 | 1913 | EW-CUTLOAD,EW-MASS | Max dig depth: Cat 395 31.9 ft [DEERE-RENT; CAT-EXC-PG]. Rent: Median (=mean) of 2 sources: W 395 5348/15509/44976; C PC900 4650/11600/29000. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
EX-WHEEL-11T | Earthwork | Hydraulic excavator | Wheeled excavator | Wheeled ~25,000 lb | Operating weight | 25000 | lb | Wheeled excavator 25K lb class (Ahearn) | 25000 |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 850 | 2500 | 5500 |  |  | bare |  |  | A26 | read Oct 2026 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 25000 |  | N | 550 | 550 | EW-TRENCH-5,EW-STRUCT,EW-BACKFILL | Rent: Ahearn only. | Needs fuel gal/hr; Needs rate (owned)
EX-WHEEL-20T | Earthwork | Hydraulic excavator | Wheeled excavator | Wheeled 40,000-55,000 lb | Operating weight | 43980 | lb | Cat M314-M322 (36,990-54,770 lb, 134-174 hp; 18.6-23 mph travel); Ahearn 40-45K lb | 43980 | 174 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 1050 | 3500 | 7500 |  |  | bare |  |  | A26 | read Oct 2026 | B |  |  |  | 2.96 | 3.89 | 5.07 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 43980 |  | N | 550 | 550 | EW-TRENCH-5,EW-TRENCH-10,EW-STRUCT,EW-BACKFILL,EW-TRENCH-15 | Representative Cat M318 (174 hp, 43,980 lb). Can road short distances at 18.6-23 mph. Rent: Ahearn 40-45K lb only. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate (owned)
EX-LR-40T | Earthwork | Hydraulic excavator | Long-reach (LRE) | Long-reach ~43 t (42.8 ft dig) | Max dig depth | 42.8 | ft | Cat 340 LRE | 96500 |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted | 96500 |  | Y | 1800 | 1800 | EW-MASS | Specs Ziegler. | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
EX-LR-55T | Earthwork | Hydraulic excavator | Long-reach (LRE) | Long-reach ~58 t (42.8 ft dig) | Max dig depth | 42.8 | ft | Cat 352 LRE | 128100 |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 128100 |  | Y | 1913 | 1913 | EW-MASS | Specs Ziegler. | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
EX-SHOVEL-95T | Earthwork | Hydraulic excavator | Front shovel | Front shovel ~96 t | Operating weight | 212300 | lb | Cat 395 Front Shovel | 212300 |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 (book) / 0.16 (Sep 2026 interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 212300 |  | Y | 1913 | 1913 | EW-CUTLOAD |  | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
EX-GRADALL-XL3100 | Earthwork | Hydraulic excavator | Truck-mounted (Gradall) | Gradall XL3100 III (0.57 CY) | Bucket | 0.57 | CY | Gradall XL3100 III |  | 184 | 0.57 CY bucket |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8287 | 215.34 | FEMA 2025 | 3.13 | 4.11 | 5.37 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 200.3 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD factor 0.12. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-CUTLOAD,EW-TRENCH-5,EW-STRUCT | HP from taxonomy extract (owned_rates lists n/c). Travels on its own truck carrier. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
EX-GRADALL-XL4100 | Earthwork | Hydraulic excavator | Truck-mounted (Gradall) | Gradall XL4100 III (0.62 CY) | Bucket | 0.62 | CY | Gradall XL4100 III |  | 238 | 0.62 CY bucket |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8288 | 315.08 | FEMA 2025 | 4.05 | 5.32 | 6.94 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 295.61 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD factor 0.12. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-CUTLOAD,EW-TRENCH-5,EW-STRUCT | HP from taxonomy extract (owned_rates lists n/c). Travels on its own truck carrier. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
EX-GRADALL-XL5100 | Earthwork | Hydraulic excavator | Truck-mounted (Gradall) | Gradall XL5100 (1.25 CY) | Bucket | 1.25 | CY | Gradall XL5100 |  | 230 | 1.25 CY bucket |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8289 | 351.11 | FEMA 2025 | 3.91 | 5.14 | 6.71 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 332.3 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD factor 0.12. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-CUTLOAD,EW-TRENCH-5,EW-STRUCT | HP from taxonomy extract (owned_rates lists n/c). Travels on its own truck carrier. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
EX-CLAM-10CY | Earthwork | Clamshell bucket (crane/cable) | Cable clamshell | Clamshell 1.0 CY | Bucket | 1.0 | CY |  |  |  | 1.0 CY |  | none (attachment) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8270 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8270: Code listed in taxonomy; rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
EX-CLAM-3-4CY | Earthwork | Clamshell bucket (crane/cable) | Cable clamshell | Clamshell 3-4 CY | Bucket | 3-4 | CY |  |  |  | 3-4 CY |  | none (attachment) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8271 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8271: Code listed in taxonomy; rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
EX-CLAM-5CY | Earthwork | Clamshell bucket (crane/cable) | Cable clamshell | Clamshell 5 CY | Bucket | 5 | CY |  |  |  | 5 CY |  | none (attachment) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8272 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8272: Code listed in taxonomy; rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
EX-CLAM-75CY | Earthwork | Clamshell bucket (crane/cable) | Cable clamshell | Clamshell 7.5 CY | Bucket | 7.5 | CY |  |  |  | 7.5 CY |  | none (attachment) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8273 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8273: Code listed in taxonomy; rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
EX-DRAG-2CY | Earthwork | Dragline bucket (crane/cable) | Cable dragline | Dragline 2 CY | Bucket | 2 | CY |  |  |  | 2 CY |  | none (attachment) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8275 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8275: Code listed in taxonomy; rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
EX-DRAG-5CY | Earthwork | Dragline bucket (crane/cable) | Cable dragline | Dragline 5 CY | Bucket | 5 | CY |  |  |  | 5 CY |  | none (attachment) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8276 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8276: Code listed in taxonomy; rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
EX-DRAG-10CY | Earthwork | Dragline bucket (crane/cable) | Cable dragline | Dragline 10 CY | Bucket | 10 | CY |  |  |  | 10 CY |  | none (attachment) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8277 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8277: Code listed in taxonomy; rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
EX-DRAG-14CY | Earthwork | Dragline bucket (crane/cable) | Cable dragline | Dragline 14 CY | Bucket | 14 | CY |  |  |  | 14 CY |  | none (attachment) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8278 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8278: Code listed in taxonomy; rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
BH-415 | Earthwork | Backhoe loader | Center-pivot, compact | Cat 415 class (69 hp) | Net HP | 69 | hp | Cat 415 IL (69 hp, 17,637 lb) | 17637 | 69 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 491 | 1424 | 4129 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 1.17 | 1.54 | 2.01 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 17637 |  | N | 500 | 500 | EW-TRENCH-5,EW-BACKFILL,EW-LOAD-TRK | Rent: Wheeler only. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Non-monotonic vs BH-STD-14FT - source data; Needs rate (owned)
BH-STD-14FT | Earthwork | Backhoe loader | Center-pivot, standard | Standard 14-15 ft dig (90-103 hp) | Max dig depth | 14 | ft | Cat 416/420/420 XE (24,251 lb, 92-103 hp); Case 580SN; 90-99 hp class | 24251 | 103 | 0.87 CY loader bucket (Case 580 per FEMA 8401); Bucket 1.25 yd3 typ (Cat 420 loader MP bucket 1.25 yd3) |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 500 | 1250 | 3735 | 2750 | 5209 | bare |  |  | W25;B25;A26 | 2025-2026 | A | 8572 | 110.03 | FEMA 2025 | 1.16 | 1.46 | 1.77 | Cat VisionLink Dec 2022, model 420-07 [CATFUEL22] | 104.69 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 24251 |  | N | 550 | 550 | EW-TRENCH-5,EW-STRUCT,EW-BACKFILL,EW-LOAD-TRK,UT-PIPE-WATER | Weight is max operating weight (Ziegler). Cat 420: 91 hp net, loader MP bucket 1.25 yd3, 14 ft std dig; travel F 3.7/5.8/12/25 mph [CAT-420]. Hoe bucket capacity not published (trench/structural rows stay D). Rent: Median of 3 sources (W 420 619/1796/5209; B Case 580SN 415/1245/3735; A 90-99 hp 500/1250/2750). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
BH-CASE580-80HP | Earthwork | Backhoe loader | Center-pivot, standard (FEMA 8401) | Case 580 Super L (80 hp, 0.87 CY) | Net HP | 80 | hp | Case 580 Super L |  | 80 | 0.87 CY; Bucket 0.87 yd3 typ (Case 580 Super L 0.87 CY (FEMA 8401)) |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8401 | 92.56 | FEMA 2025 | 1.36 | 1.79 | 2.33 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 86.01 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | EW-TRENCH-5,EW-BACKFILL | Owned-rate row only; for rental use BH-STD-14FT. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Non-monotonic vs BH-430 - source data; Needs rate (rental)
BH-430 | Earthwork | Backhoe loader | Center-pivot, extended | Cat 430 class (107 hp, 15.1 ft dig) | Max dig depth | 15.1 | ft | Cat 430 | 24251 | 107 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 684 | 1982 | 5749 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 1.18 | 1.5 | 1.81 | Cat VisionLink Dec 2022, model 430-07 [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 24251 |  | N | 550 | 550 | EW-TRENCH-5,EW-BACKFILL,EW-LOAD-TRK | Rent: Wheeler only. | Needs rate (owned)
BH-440 | Earthwork | Backhoe loader | Center-pivot, large | Cat 440 class (104 hp, 29,321 lb) | Net HP | 104 | hp | Cat 440 | 29321 | 104 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 927 | 2688 | 7796 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 1.44 | 1.79 | 2.15 | Cat VisionLink Dec 2022, model 440-07 [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 29321 |  | N | 550 | 550 | EW-TRENCH-5,EW-TRENCH-10,EW-BACKFILL,EW-LOAD-TRK | Rent: Wheeler only. | Needs rate (owned)
BH-450 | Earthwork | Backhoe loader | Center-pivot, large | Cat 450 class (131 hp, 17 ft dig) | Max dig depth | 17 | ft | Cat 450 | 29321 | 131 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8573 |  |  | 1.47 | 1.83 | 2.2 | Cat VisionLink Dec 2022, model 450-07 [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 29321 |  | N | 550 | 550 | EW-TRENCH-5,EW-TRENCH-10,EW-BACKFILL,EW-LOAD-TRK | FEMA 8573: FEMA rate not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
BH-SIDESHIFT | Earthwork | Backhoe loader | Side-shift | Side-shift 70-92 hp | Net HP | 92 | hp | Cat 428 (70 hp), 432 (92 hp), 434 (92 hp; 25,353 lb) | 25353 | 92 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 1.56 | 2.06 | 2.68 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 25353 |  | N | 550 | 550 | EW-TRENCH-5,EW-BACKFILL | Representative 434. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned)
WL-MINI-07Y | Earthwork | Wheel loader | Compact (mini) | 0.5-0.7 CY (~38 hp) | Bucket | 0.7 | CY | Gehl 280 |  | 38 | 0.5-0.7 CY; Bucket 0.6 yd3 typ (midpoint of 0.5-0.7 CY (Gehl 280, taxonomy)) |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8390 | 42.33 | FEMA 2025 | 0.65 | 0.85 | 1.11 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 39.22 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | EW-LOAD-TRK,EW-STOCKPILE,EW-BACKFILL | Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
WL-COMPACT-1Y | Earthwork | Wheel loader | Compact | ~1-1.25 yd (~68-75 hp) | Bucket | 1 | CY | Cat 903/906/907/908 (74.7 hp, 12,628-14,617 lb, 1.0-2.0 yd); Bobcat L85; Kubota R630 | 12628 | 74.7 | 1.0-1.25 CY; Bucket 1.125 yd3 typ (midpoint of 1.0-1.25 yd rental class (Cat 906 GP 1.0-1.7; Deere 244 P 1.0-1.4)) |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 400 | 1200 | 3240 | 3000 | 5209 | bare |  |  | W25;B25;A26 | 2025-2026 | A | 8391 | 58.08 | FEMA 2025 | 0.57 | 0.75 | 0.92 | Cat VisionLink Dec 2022, model 906M [CATFUEL22] | 55.34 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 12628 |  | N | 500 | 500 | EW-LOAD-TRK,EW-STOCKPILE,EW-BACKFILL | Rent: Median of 3 sources (W 906 619/1796/5209; B 360/1080/3240; A 400/1200/3000). FEMA: FEMA 8391 Bobcat L85 (68 hp) mapped to this class by HP. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
WL-COMPACT-2Y | Earthwork | Wheel loader | Compact | 2-2.5 yd (~110 hp) | Bucket | 2.25 | CY | Cat 910/914 (110 hp, 18,102-19,103 lb, 1.7-4.6 yd); Komatsu WA200 (2.5 yd); Develon DL200 | 18102 | 110 | 2.0-2.5 CY; Bucket 2.25 yd3 typ (midpoint of 2.0-2.5 yd rental class (Deere 344 P 2.0-2.6)) |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 675 | 1925 | 4900 | 4230 | 6956 | bare |  |  | W25;B25;C25;R25 | 2025-2026 | A | 8392 | 83.4 | FEMA 2025 | 0.96 | 1.16 | 1.36 | Cat VisionLink Dec 2022, model 910-14 [CATFUEL22] | 79.15 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 18102 |  | N | 500 | 500 | EW-LOAD-TRK,EW-STOCKPILE,EW-BACKFILL | Rent: Median of 4 sources (W 914 827/2399/6956; B 470/1410/4230; C 750/1850/4600; R 600/2000/5200). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
WL-SMALL-3Y | Earthwork | Wheel loader | Small | 3-3.2 yd (~170 hp) | Bucket | 3 | CY | Cat 926 (170 hp, 27,972 lb, 3.0 yd), 930 (31,124 lb, 3.2 yd); Komatsu WA270 | 27972 | 170 | 3.0-3.2 CY; Bucket 3.1 yd3 typ (midpoint of 3.0-3.2 yd rental class) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 825 | 2050 | 5500 | 5100 | 8211 | bare |  |  | W25;C25;A26 | 2025-2026 | A | 8393 | 116.74 | FEMA 2025 | 1.72 | 2.11 | 2.51 | Cat VisionLink Dec 2022, model 926M [CATFUEL22] | 109.02 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 27972 |  | N | 550 | 550 | EW-LOAD-TRK,EW-STOCKPILE,EW-BACKFILL | Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 3 sources (W 926/930 avg 976/2831/8210; C 825/2050/5100; A 550/2000/5500). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
WL-SMALL-4Y | Earthwork | Wheel loader | Small | 3.5-4.25 yd (~190-232 hp) | Bucket | 3.8 | CY | Cat 938 (191 hp, 35,528 lb, 3.8 yd); Komatsu WA320 (3.5)/WA380 (4.25); Deere 644K (4.2 CY) | 35528 | 191 | 3.5-4.25 CY; Bucket 3.875 yd3 typ (midpoint of 3.5-4.25 yd rental class) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 1088 | 2700 | 7000 | 5700 | 9884 | bare |  |  | W25;C25;A26 | 2025-2026 | A | 8394 | 116.87 | FEMA 2025 | 1.9 | 2.36 | 2.82 | Cat VisionLink Dec 2022, model 938M [CATFUEL22] | 108.23 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 35528 |  | N | 550 | 550 | EW-LOAD-TRK,EW-STOCKPILE,EW-BACKFILL | Rent: Median of 3 sources (W 938 1175/3408/9884; C WA320/380 avg 1088/2700/6700; A 850/2500/7000). FEMA: FEMA 8394 Deere 644K (4.2 CY, 232 hp) mapped to this class by bucket. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
WL-MED-45Y | Earthwork | Wheel loader | Medium | 4.5 yd (~225-250 hp) | Bucket | 4.5 | CY | Cat 950 GC (225 hp, 3.75-5.75 yd), 950 (249 hp, 42,461 lb) | 42461 | 249 | 4.5 CY; Bucket 4.5 yd3 typ (4.5 yd (Wheeler Cat 950 rental line; cat.com 950 rated 4.1)) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 1473 | 4272 | 12387 |  |  | bare |  |  | W25 | 2025 | B | 8396 | 139.8 | FEMA 2025 | 2.38 | 3.02 | 3.66 | Cat VisionLink Dec 2022, model 950M [CATFUEL22] | 128.75 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 42461 |  | N | 550 | 550 | EW-LOAD-TRK,EW-STOCKPILE,EW-BACKFILL | Rent: Wheeler 950 (4.5 yd) only. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
WL-MED-5Y | Earthwork | Wheel loader | Medium | 5-5.25 yd (~255-321 hp) | Bucket | 5.25 | CY | Cat 962/966 (321 hp, 51,124 lb, 5.25 yd); Case 921C (5 CY, 255 hp) | 51124 | 321 | 5.0-5.25 CY; Bucket 5.25 yd3 typ (5.25 yd (Cat 966 rental line)) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2085 | 6046 | 17533 |  |  | bare |  |  | W25 | 2025 | B | 8395 | 163.2 | FEMA 2025 | 3.08 | 3.88 | 4.69 | Cat VisionLink Dec 2022, model 966M [CATFUEL22] | 149 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 51124 |  | maybe | 550 | 550 | EW-LOAD-TRK,EW-STOCKPILE,EW-BACKFILL | Rent: Wheeler 966 (5.25 yd) only. FEMA: FEMA 8395 is a Case 921C (5 CY); fuel row is Cat 966M - different makes in one class. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
WL-MED-972 | Earthwork | Wheel loader | Medium | Cat 972 class (~339 hp) | Net HP | 339 | hp | Cat 972 (339 hp, 54,858 lb) | 54858 | 339 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2236 | 6484 | 18803 |  |  | bare |  |  | W25 | 2025 | B | 8397 | 188.93 | FEMA 2025 | 3.3 | 4.18 | 5.06 | Cat VisionLink Dec 2022, model 972M [CATFUEL22] | 173.63 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 54858 |  | maybe | 550 | 550 | EW-LOAD-TRK,EW-STOCKPILE,EW-BACKFILL | Rent: Wheeler only. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
WL-MED-980 | Earthwork | Wheel loader | Medium | Cat 980 class (~420 hp, 5.75-7.5 yd) | Net HP | 420 | hp | Cat 980 / 980 GC | 65610 | 393 | 5.75-7.5 CY (980 GC); Bucket 6.625 yd3 typ (midpoint of Cat 980 GC 5.75-7.5 yd3) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2719 | 7886 | 22869 |  |  | bare |  |  | W25 | 2025 | B |  | 223.06 | FEMA 2025 (interpolated) | 4.07 | 5.19 | 6.32 | Cat VisionLink Dec 2022, model 980M [CATFUEL22] | 204.06 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 65610 |  | maybe | 550 | 550 | EW-LOAD-TRK,EW-STOCKPILE,EW-BACKFILL | 980 GC: 393 hp, 65,610 lb; F 4.1/7.9/14/24.7 mph [CAT-WL-PG]. Rent: Wheeler only. Owned_rate_hr_incl_fuel interpolated (C) between WL-MED-972 and WL-LARGE-988 by Net HP (FEMA 2025 endpoints). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
WL-MED-982 | Earthwork | Wheel loader | Medium | Cat 982 class (~432 hp) | Net HP | 432 | hp | Cat 982 | 78264 | 432 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  | 247.71 | FEMA 2025 (interpolated) | 4.49 | 5.77 | 7.04 | Cat VisionLink Dec 2022, model 982M [CATFUEL22] | 226.59 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted | 78264 |  | Y | 1800 | 1800 | EW-LOAD-TRK,EW-STOCKPILE | Owned_rate_hr_incl_fuel interpolated (C) between WL-MED-972 and WL-LARGE-988 by Net HP (FEMA 2025 endpoints). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
WL-LARGE-986 | Earthwork | Wheel loader | Large | Cat 986 class (~449 hp, 6.5-13.5 yd) | Net HP | 449 | hp | Cat 986 | 97785 | 449 | 6.5-13.5 CY |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  | 258.45 | FEMA 2025 (interpolated) | 7.64 | 10.04 | 13.09 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 221.7 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted | 97785 |  | Y | 1800 | 1800 | EW-LOAD-TRK,EW-STOCKPILE | Owned_rate_hr_incl_fuel interpolated (C) between WL-MED-972 and WL-LARGE-988 by Net HP (FEMA 2025 endpoints). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Non-monotonic vs WL-LARGE-988 - source data; Needs rate (rental)
WL-LARGE-988 | Earthwork | Wheel loader | Large | Cat 988 class (~580 hp, 6.2-17 yd) | Net HP | 580 | hp | Cat 988 | 112574 | 580 | 6.2-17 CY |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8398 | 341.25 | FEMA 2025 | 6.76 | 8.62 | 10.48 | Cat VisionLink Dec 2022, model 988K [CATFUEL22] | 309.7 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 112574 |  | Y | 1913 | 1913 | EW-LOAD-TRK,EW-STOCKPILE | Cat 988: 6.2-17 yd3 (17 = light material); rated payload 12.5 t face / 16 t loose; production left D (bucket range too wide for a typical) [CAT-WL-PG]. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
WL-LARGE-990 | Earthwork | Wheel loader | Large (quarry/mining) | Cat 990 class (~786 hp) | Net HP | 786 | hp | Cat 990 | 178517 | 786 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 13.37 | 17.57 | 22.92 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 178517 |  | Y | 1913 | 1913 | EW-LOAD-TRK | No FEMA row above 580 hp; not extrapolated. Cat 993/995 (mining) omitted. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned)
WL-LARGE-992 | Earthwork | Wheel loader | Large (quarry/mining) | Cat 992 class (~814 hp) | Net HP | 814 | hp | Cat 992 | 233430 | 814 | 15-32 CY |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 13.85 | 18.2 | 23.74 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRRT factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 233430 |  | Y | 1913 | 1913 | EW-LOAD-TRK | No FEMA row above 580 hp; not extrapolated. Cat 993/995 (mining) omitted. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned)
TL-CRAWL-963 | Earthwork | Track loader | Crawler loader | 3-3.2 CY (~178 hp) | Bucket | 3 | CY | Cat 963C |  | 178 | 3-3.2 CY; Bucket 3.1 yd3 typ (midpoint of Cat 963 3-3.2 CY) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8383 | 197.79 | FEMA 2025 | 3.03 | 3.98 | 5.19 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 183.22 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRCL factor 0.11. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | EW-LOAD-TRK,EW-BACKFILL | HP from taxonomy (FEMA cap 178). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
TL-CRAWL-973 | Earthwork | Track loader | Crawler loader | 4-4.19 CY (~238 hp) | Bucket | 4 | CY | Cat 973C |  | 238 | 4-4.19 CY; Bucket 4.095 yd3 typ (midpoint of Cat 973 4-4.19 CY) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8384 | 254.71 | FEMA 2025 | 4.05 | 5.32 | 6.94 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 235.24 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LDRCL factor 0.11. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-LOAD-TRK,EW-BACKFILL | Weight not in notes; transport assumed permitted (verify). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
SS-WHEEL-MICRO | Earthwork | Skid steer / CTL | Wheeled skid steer, micro | ROC 700-1,099 lb (~24 hp) | Rated operating capacity | 900 | lb | Bobcat S70 |  | 24 | ROC 700-1,099 lb |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 230 | 690 | 2070 |  |  | bare |  |  | B25 | Mar 2025 | B | 8540 | 31.67 | FEMA 2025 | 0.41 | 0.54 | 0.7 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 29.69 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | EW-LOAD-TRK,EW-BACKFILL,EW-SPREAD-SSL | Rent: Burris only. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
SS-WHEEL-SMALL | Earthwork | Skid steer / CTL | Wheeled skid steer, small frame | ROC <1,750 lb | Rated operating capacity | 1500 | lb | Cat 226D; Bobcat S450 (1,370 lb), S530 (1,750 lb); ~5,000-6,000 lb, ~50 hp | 5500 | 50 | ROC 1,370-1,749 lb |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 230 | 743 | 2038 | 1875 | 3462 | bare |  |  | W25;B25;R25;N25 | 2025-2026 | A |  |  |  |  | 2.46 |  | Cat Dec 2022 single value, 226D3-249D3 group [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 5500 |  | N | 500 | 500 | EW-LOAD-TRK,EW-BACKFILL,EW-SPREAD-SSL | Spec value 1,500 lb = mid of class; weight/HP are SkidSteers.com frame-class figures (5,000-6,000 lb, ~50 hp). Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 4 sources (W 412/1194/3462; B 240/720/2160; R 185/675/1875; N 219/765/1915). | Needs rate (owned)
SS-WHEEL-MED | Earthwork | Skid steer / CTL | Wheeled skid steer, medium frame | ROC 1,750-2,500 lb | Rated operating capacity | 2100 | lb | Bobcat S590/S64 (2,300), S595/S66 (2,400); Gehl SSV65; 6,000-7,000 lb, 50-70 hp | 6500 | 70 | ROC 1,750-2,500 lb; Bucket 0.6 yd3 typ (62-68 in bucket 0.57-0.63 yd3 mapped to 1,750-2,200 lb ROC (notes mapping; midpoint)) |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 257 | 838 | 2310 | 2250 | 2500 | bare |  |  | B25;R25;A26 | 2025-2026 | A |  |  |  |  | 2.62 |  | Cat Dec 2022 single value, 236D3-262D3 group [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 6500 |  | N | 500 | 500 | EW-LOAD-TRK,EW-BACKFILL,EW-SPREAD-SSL | Rent: Median of 3 sources (B 257/770/2310; R 225/838/2250; A 375/1200/2500). | Needs rate (owned)
SS-WHEEL-LARGE | Earthwork | Skid steer / CTL | Wheeled skid steer, large frame | ROC 2,500-3,500 lb | Rated operating capacity | 3000 | lb | Cat 270 XE; Bobcat S650/S76 (2,900), S770 (3,350), S86 (3,400); Gehl SSV75; 7,000-10,000 lb, 70+ hp | 8500 | 74 | ROC 2,500-3,500 lb; Bucket 0.69 yd3 typ (74 in bucket 0.69 yd3 mapped to 2,500-3,200 lb ROC (notes mapping)) |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 373 | 1175 | 2958 | 2750 | 6003 | bare |  |  | W25;B25;R25;A26 | 2025-2026 | A | 8541 | 45.23 | FEMA 2025 |  | 3.3 |  | Cat Dec 2022 single value, 272D3/299D3 group [CATFUEL22] | 33.15 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 8500 |  | N | 500 | 500 | EW-LOAD-TRK,EW-BACKFILL,EW-SPREAD-SSL | Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 4 sources (W 714/2070/6003; B 350/1050/3150; R 273/1025/2767; A 395/1300/2750). FEMA: FEMA 8541 Bobcat S76 (~2,900 lb ROC, to 74 hp). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
SS-WHEEL-XL | Earthwork | Skid steer / CTL | Wheeled skid steer, large frame (high ROC) | ROC 3,000-4,500 lb | Rated operating capacity | 3400 | lb | Bobcat S86 (3,400 lb ROC, to 105 hp) |  | 105 | ROC 3,000-4,499 lb |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 330 | 1090 | 3170 | 3100 | 3240 | bare |  |  | B25;R25 | 2025-2026 | A | 8542 | 60.67 | FEMA 2025 |  | 3.3 |  | Cat Dec 2022 single value, 272D3/299D3 group [CATFUEL22] | 48.59 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | EW-LOAD-TRK,EW-BACKFILL,EW-SPREAD-SSL | Rent: Median (=mean) of 2 sources: B 3,000-4,499 lb 360/1080/3240; R S86 300/1100/3100. Overlaps SS-WHEEL-LARGE. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
SS-MTL | Earthwork | Skid steer / CTL | Mini track loader (stand-on) | Mini track loader (~25 hp) | Net HP | 25 | hp | Bobcat MT100/MT120 |  | 25 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 250 | 975 | 2695 |  |  | bare |  |  | R25 | Spring 2025 | B | 8380 | 36.92 | FEMA 2025 | 0.43 | 0.56 | 0.73 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 34.87 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | EW-BACKFILL,EW-SPREAD-SSL | Rent: RTL MT100 only. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
CTL-SMALL | Earthwork | Skid steer / CTL | Compact track loader, small | ROC <2,000 lb | Rated operating capacity | 1700 | lb | Cat 239; Bobcat T450 (1,500), T590 (1,900) |  | 55 | ROC <2,000 lb |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 372 | 1288 | 3198 | 2795 | 4542 | bare |  |  | W25;R25;N25;A26 | 2025-2026 | A | 8381 | 41.49 | FEMA 2025 |  | 2.46 |  | Cat Dec 2022 single value, 226D3-249D3 group (incl. 239D3) [CATFUEL22] | 32.49 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | EW-LOAD-TRK,EW-BACKFILL,EW-SPREAD-SSL | Rent: Median of 4 sources (W 540/1566/4542; R 300/1325/3395; N 319/1115/2795; A 425/1250/3000). FEMA: FEMA 8381 Bobcat T450 (to 55 hp). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
CTL-MED | Earthwork | Skid steer / CTL | Compact track loader, medium | ROC 2,000-3,000 lb | Rated operating capacity | 2500 | lb | Bobcat T550/T595/T650/T76; Takeuchi TL10; Kubota SVL65/75 |  |  | ROC 2,000-3,000 lb; Bucket 0.69 yd3 typ (74 in bucket 0.69 yd3 mapped to 2,500-3,200 lb ROC (notes mapping)) |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 383 | 1383 | 3450 | 3133 | 4106 | bare |  |  | B25;R25;N25;A26;C25 | 2025-2026 | A |  |  |  |  | 2.62 |  | Cat Dec 2022 single value, 259D3-289D3 group [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | EW-LOAD-TRK,EW-BACKFILL,EW-SPREAD-SSL | Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 5 sources (B 382/1148/3442; R 369/1450/4106; N 365/1250/3450; A 450/1383/3133; C 575/1400/3500). | Needs rate (owned)
CTL-LARGE | Earthwork | Skid steer / CTL | Compact track loader, large | ROC >3,000 lb | Rated operating capacity | 3500 | lb | Cat 285 XE; Bobcat T770/T86 (3,800); Takeuchi TL12; Kubota SVL97 |  | 105 | ROC >3,000 lb; Bucket 0.74 yd3 typ (80 in bucket 0.74 yd3 mapped to 3,500 lb+ ROC (notes mapping)) |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 500 | 1700 | 4200 | 3950 | 10185 | bare |  |  | W25;B25;R25;A26;C25 | 2025-2026 | A | 8382 | 62.38 | FEMA 2025 |  | 3.3 |  | Cat Dec 2022 single value, 299D3 group [CATFUEL22] | 50.3 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | EW-LOAD-TRK,EW-BACKFILL,EW-SPREAD-SSL | Rent: Median of 5 sources (W 1211/3511/10185; B 448/1342/4028; R 475/1850/4748; A 500/1700/3950; C 700/1700/4200). FEMA: FEMA 8382 Bobcat T86 (to 105 hp). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
SC-621-24 | Earthwork | Wheel tractor scraper | Open bowl, single engine | 24 yd3 bowl | Bowl capacity (heaped) | 24 | yd3 | Cat 621 |  |  | 24 yd3 heaped; rated load 57,610 lb |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8524 | 189.79 | FEMA 2025 | 5.14 | 6.56 | 7.97 | Cat VisionLink Dec 2022, model 621K [CATFUEL22] | 165.78 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-SCR-1000,EW-SCR-2000,EW-SCR-3000 | No published scraper rental rates found. Weight not in notes; transport assumed permitted. Loaded top speed 33.5 mph; 407 hp [CAT-SCR-PG]. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
SC-623-23 | Earthwork | Wheel tractor scraper | Elevating | 23 yd3 bowl | Bowl capacity (heaped) | 23 | yd3 | Cat 623 |  |  | 23 yd3 heaped; rated load 55,200 lb |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 5.93 | 7.59 | 9.25 | Cat VisionLink Dec 2022, model 623K [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-SCR-1000,EW-SCR-2000,EW-SCR-3000 | No published scraper rental rates found. Weight not in notes; transport assumed permitted. | Needs rate; Needs rate (rental); Needs rate (owned)
SC-627-24 | Earthwork | Wheel tractor scraper | Open bowl, tandem-powered (push-pull) | 24 yd3 bowl | Bowl capacity (heaped) | 24 | yd3 | Cat 627 |  |  | 24 yd3 heaped; rated load not in specs |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 10.52 | 9.77 | 9.03 | Cat VisionLink Dec 2022, model 627K [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-SCR-1000,EW-SCR-2000,EW-SCR-3000 | No published scraper rental rates found. Cat VisionLink values run high->low (low 10.52 > high 9.03) as published. Weight not in notes; transport assumed permitted. | Needs rate; Fuel low/high inverted in source; Needs rate (rental); Needs rate (owned)
SC-631-34 | Earthwork | Wheel tractor scraper | Open bowl, single engine | 34 yd3 bowl | Bowl capacity (heaped) | 34 | yd3 | Cat 631 |  |  | 34 yd3 heaped; rated load 82,200 lb |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8521 | 344.22 | FEMA 2025 | 6.99 | 9.06 | 11.13 | Cat VisionLink Dec 2022, model 631K [CATFUEL22] | 311.06 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-SCR-1000,EW-SCR-2000,EW-SCR-3000 | No published scraper rental rates found. Weight not in notes; transport assumed permitted. Loaded top speed 34.7 mph; 570 hp [CAT-SCR-PG]. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
SC-637-34 | Earthwork | Wheel tractor scraper | Open bowl, tandem-powered | 34 yd3 bowl | Bowl capacity (heaped) | 34 | yd3 | Cat 637 (coal bowl 50 yd) |  |  | 34 yd3 heaped; rated load 82,200 lb |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 12.6 | 12.2 | 11.79 | Cat VisionLink Dec 2022, model 637K [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-SCR-1000,EW-SCR-2000,EW-SCR-3000 | No published scraper rental rates found. Fuel values inverted as published. Weight not in notes; transport assumed permitted. 637 Coal Bowl 50 yd3 variant not catalogued separately. | Needs rate; Fuel low/high inverted in source; Needs rate (rental); Needs rate (owned)
SC-651-44 | Earthwork | Wheel tractor scraper | Open bowl, single engine | 44 yd3 bowl | Bowl capacity (heaped) | 44 | yd3 | Cat 651 |  |  | 44 yd3 heaped; rated load not in specs |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8522 | 545.78 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-SCR-1000,EW-SCR-2000,EW-SCR-3000 | No published scraper rental rates found. No Cat fuel row for 651 and no HP captured. Weight not in notes; transport assumed permitted. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
SC-657-44 | Earthwork | Wheel tractor scraper | Open bowl, tandem-powered | 44 yd3 bowl | Bowl capacity (heaped) | 44 | yd3 | Cat 657 |  |  | 44 yd3 heaped; rated load 104,000 lb |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 15.65 | 13.87 | 12.08 | Cat VisionLink Dec 2022, model 657-07 [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-SCR-1000,EW-SCR-2000,EW-SCR-3000 | No published scraper rental rates found. Fuel values inverted as published. Weight not in notes; transport assumed permitted. Loaded top speed 33 mph; 637 + 479 hp [CAT-SCR-PG]. | Needs rate; Fuel low/high inverted in source; Needs rate (rental); Needs rate (owned)
SC-PULL-4CY | Earthwork | Pull scraper (towed) | Box / pull pan | 4.1 CY, 84 in | Bowl capacity | 4.1 | CY | Rome 5C |  |  | 4.1 CY |  | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8269 | 18.41 | FEMA 2025 | 0 | 0 | 0 | No engine (towed / attachment / non-powered) | 18.41 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Towed by a tractor/dozer priced separately. Ex-fuel = incl-fuel rate (no liquid fuel to back out). | Needs rate (rental)
GR-COMPACT | Earthwork | Motor grader | Compact | Compact grader | Model | CG65E |  | Cat CG65E |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 1073 | 3111 | 9021 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: GRADR factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | EW-FGRADE | Specs not in notes. Rent: Wheeler only. | Needs fuel gal/hr; Needs rate (owned)
GR-12FT-120 | Earthwork | Motor grader | 12 ft moldboard | 12 ft (Cat 120) | Moldboard length | 12 | ft | Cat 120 (130 hp, 35,067 lb) | 35067 | 130 | 12 ft moldboard |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8331 | 131.96 | FEMA 2025 | 2.35 | 2.9 | 3.45 | Cat VisionLink Dec 2022, model 120-14 [CATFUEL22] | 121.35 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: GRADR factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 35067 |  | N | 550 | 550 | EW-FGRADE,EW-RGRADE-GR,EW-SPREAD-BASE | Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
GR-12FT-140 | Earthwork | Motor grader | 12 ft moldboard | 12 ft (Cat 140) | Moldboard length | 12 | ft | Cat 140/140 AWD (179 hp, 42,647 lb); 140 GC | 42647 | 179 | 12 ft moldboard |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 1949 | 5652 | 16389 |  |  | bare |  |  | W25 | 2025 | B | 8332 | 159.04 | FEMA 2025 | 2.83 | 3.53 | 4.24 | Cat VisionLink Dec 2022, model 140-15 [CATFUEL22] | 146.12 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: GRADR factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 42647 |  | N | 550 | 550 | EW-FGRADE,EW-RGRADE-GR,EW-SPREAD-BASE | Wheeler single-source dealer pricing; independents likely 20-35% lower (notes inference). Rent: Wheeler 140/150 line. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
GR-12FT-120GC | Earthwork | Motor grader | 12 ft moldboard | 12 ft (Cat 120 GC) | Moldboard length | 12 | ft | Cat 120 GC (171 hp) |  | 171 | 12 ft moldboard |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 2.91 | 3.82 | 4.99 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: GRADR factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | EW-FGRADE,EW-RGRADE-GR,EW-SPREAD-BASE | FEMA 8331 'Cat 120' carries a 171 hp cap, which equals the 120 GC rating; FEMA rate kept on GR-12FT-120 (no basis to move it). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned)
GR-12FT-140GC | Earthwork | Motor grader | 12 ft moldboard | 12 ft (Cat 140 GC) | Moldboard length | 12 | ft | Cat 140 GC (196 hp) |  | 196 | 12 ft moldboard |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 2.67 | 3.37 | 4.06 | Cat VisionLink Dec 2022, model 140-01 GC [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: GRADR factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | EW-FGRADE,EW-RGRADE-GR,EW-SPREAD-BASE | FEMA 8332 'Cat 140' carries a 196 hp cap, which equals the 140 GC rating; FEMA rate kept on GR-12FT-140. | Needs rate; Needs rate (rental); Needs rate (owned)
GR-12FT-150 | Earthwork | Motor grader | 12 ft moldboard | 12 ft (Cat 150) | Moldboard length | 12 | ft | Cat 150 (200 hp) |  | 200 | 12 ft moldboard |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 1949 | 5652 | 16389 |  |  | bare |  |  | W25 | 2025 | B |  | 192.84 | FEMA 2025 (interpolated) | 2.87 | 3.58 | 4.29 | Cat VisionLink Dec 2022, model 150-15 [CATFUEL22] | 179.74 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: GRADR factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | EW-FGRADE,EW-RGRADE-GR,EW-SPREAD-BASE | Wheeler single-source dealer pricing; independents likely 20-35% lower (notes inference). Weight not in notes. Rent: Wheeler 140/150 line (same as 140). Owned_rate_hr_incl_fuel interpolated (C) between GR-12FT-140 and GR-14FT-160 by Net HP (FEMA 2025 endpoints). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
GR-14FT-160 | Earthwork | Motor grader | 14 ft moldboard | 14 ft (Cat 160) | Moldboard length | 14 | ft | Cat 160 (224 hp) |  | 224 | 14 ft moldboard |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2085 | 6046 | 17533 |  |  | bare |  |  | W25 | 2025 | B | 8333 | 231.47 | FEMA 2025 | 3.51 | 4.45 | 5.39 | Cat VisionLink Dec 2022, model 160-15 [CATFUEL22] | 215.18 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: GRADR factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | EW-FGRADE,EW-RGRADE-GR,EW-SPREAD-BASE | Wheeler single-source dealer pricing; independents likely 20-35% lower (notes inference). Weight not in notes. Rent: Wheeler only. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
GR-14FT-14 | Earthwork | Motor grader | 14 ft moldboard | 14 ft (Cat 14) | Moldboard length | 14 | ft | Cat 14 (238 hp, 57,250 lb) | 57250 | 238 | 14 ft moldboard |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2598 | 7535 | 21853 |  |  | bare |  |  | W25 | 2025 | B |  | 240.2 | FEMA 2025 (interpolated) | 3.7 | 4.66 | 5.62 | Cat VisionLink Dec 2022, model 14-15 [CATFUEL22] | 223.14 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: GRADR factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 57250 |  | maybe | 550 | 550 | EW-FGRADE,EW-RGRADE-GR,EW-SPREAD-BASE | Wheeler single-source dealer pricing; independents likely 20-35% lower (notes inference). Rent: Wheeler only. Owned_rate_hr_incl_fuel interpolated (C) between GR-14FT-160 and GR-18FT-18 by Net HP (FEMA 2025 endpoints). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
GR-16FT-16 | Earthwork | Motor grader | 16 ft moldboard | 16 ft (Cat 16) | Moldboard length | 16 | ft | Cat 16 (290 hp, 71,454 lb) | 71454 | 290 | 16 ft moldboard |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 5061 | 14676 | 42562 |  |  | bare |  |  | W25 | 2025 | B |  | 272.6 | FEMA 2025 (interpolated) | 4.35 | 5.53 | 6.72 | Cat VisionLink Dec 2022, model 16-15 [CATFUEL22] | 252.36 | C | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: GRADR factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted | 71454 |  | Y | 1800 | 1800 | EW-FGRADE,EW-RGRADE-GR,EW-SPREAD-BASE | Wheeler single-source dealer pricing; independents likely 20-35% lower (notes inference). Rent: Wheeler only. Owned_rate_hr_incl_fuel interpolated (C) between GR-14FT-160 and GR-18FT-18 by Net HP (FEMA 2025 endpoints). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
GR-18FT-18 | Earthwork | Motor grader | 18 ft moldboard | 18 ft (Cat 18) | Moldboard length | 18 | ft | Cat 18 (304 hp, 74,324 lb) | 74324 | 304 | 18 ft moldboard |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 5574 | 16166 | 46881 |  |  | bare |  |  | W25 | 2025 | B | 8334 | 281.33 | FEMA 2025 | 5.19 | 6.59 | 7.99 | Cat VisionLink Dec 2022, model 18-15 [CATFUEL22] | 257.21 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: GRADR factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted | 74324 |  | Y | 1800 | 1800 | EW-FGRADE,EW-RGRADE-GR,EW-SPREAD-BASE | Wheeler single-source dealer pricing; independents likely 20-35% lower (notes inference). Rent: Wheeler only. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
GR-24FT-24 | Earthwork | Motor grader | 24 ft moldboard | 24 ft (Cat 24) | Moldboard length | 24 | ft | Cat 24 (535 hp, 165,314 lb) | 165314 | 535 | 24 ft moldboard |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 9.1 | 11.96 | 15.6 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: GRADR factor 0.11 (book) / 0.10 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 165314 |  | Y | 1913 | 1913 | EW-FGRADE,EW-RGRADE-GR,EW-SPREAD-BASE | Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned)
ADT-25T | Hauling | Articulated dump truck (ADT) | Standard | 26.5 t payload | Rated payload | 26.5 | ton | Cat 725 (26.5 t); Doosan DA30 |  |  | 26.5 ton payload; heaped 19.6 yd3 (Cat 725 26.5 t / 19.6 yd3 heaped) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 1882 | 5223 | 14259 | 12000 | 16517 | bare |  |  | W25;R25 | 2025-2026 | A |  |  |  | 3.56 | 4.56 | 5.56 | Cat VisionLink Dec 2022, model 725 [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-HAUL-ADT-05,EW-HAUL-ADT-10,EW-HAUL-ADT-20 | Not in FEMA schedule. Weight/width not in notes; transport assumed permitted. Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median (=mean) of 2 sources: W 725 1964/5695/16517; R DA30 1800/4750/12000. | Needs rate (owned)
ADT-30T | Hauling | Articulated dump truck (ADT) | Standard | 30 t payload | Rated payload | 30 | ton | Cat 730 (38.9 t as listed); Komatsu HM300 (31 t) |  |  | 30 ton payload; heaped 23.3 yd3 (Volvo A30 32 st / 23.3 yd3 (class proxy; Cat 730 heaped not in specs)) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2126 | 5764 | 15715 | 12500 | 18930 | bare |  |  | W25;C25 | 2025-2026 | A |  |  |  | 3.38 | 4.38 | 5.39 | Cat VisionLink Dec 2022, model 730 [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-HAUL-ADT-05,EW-HAUL-ADT-10,EW-HAUL-ADT-20 | Not in FEMA schedule. Weight/width not in notes; transport assumed permitted. Rent: Median (=mean) of 2 sources: W 730 2251/6528/18930; C HM300 2000/5000/12500. | Needs rate (owned)
ADT-35T | Hauling | Articulated dump truck (ADT) | Standard | 35.3 t payload | Rated payload | 35.3 | ton | Cat 735 (35.3 t) |  |  | 35.3 ton payload; heaped 28.4 yd3 (Volvo A35 38 st / 28.4 yd3 (class proxy)) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-HAUL-ADT-05,EW-HAUL-ADT-10,EW-HAUL-ADT-20 | Not in FEMA schedule. Weight/width not in notes; transport assumed permitted. | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
ADT-40T | Hauling | Articulated dump truck (ADT) | Standard | 40 t payload | Rated payload | 40 | ton | Cat 740 / 740 GC (40 t); Komatsu HM400 (44 t); Doosan DA45 |  |  | 40 ton payload; heaped 31.4 yd3 (Volvo A40G 43 st / 31.4 yd3 (class proxy)) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2750 | 7500 | 17000 | 15000 | 24648 | bare |  |  | W25;C25;R25 | 2025-2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-HAUL-ADT-05,EW-HAUL-ADT-10,EW-HAUL-ADT-20 | Not in FEMA schedule. Weight/width not in notes; transport assumed permitted. Rent: Median of 3 sources (W 740 GC 2931/8499/24648; C HM400 2400/6000/15000; R DA45 2750/7500/17000). Columbus tailgate +$1,000/mo. | Needs fuel gal/hr; Needs rate (owned)
ADT-45T | Hauling | Articulated dump truck (ADT) | Standard | 45.2 t payload | Rated payload | 45.2 | ton | Cat 745 (45.2 t) |  |  | 45.2 ton payload; heaped 33.4 yd3 (Cat 745 45.2 t / 33.4 yd3) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 3263 | 9463 | 27443 |  |  | bare |  |  | W25 | 2025 | B |  |  |  |  | 7.03 |  | Cat Dec 2022 single value, 745 (single value) [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-HAUL-ADT-05,EW-HAUL-ADT-10,EW-HAUL-ADT-20 | Not in FEMA schedule. Weight/width not in notes; transport assumed permitted. Rent: Wheeler only. | Needs rate (owned)
ADT-EJ-30T | Hauling | Articulated dump truck (ADT) | Ejector body | 30 t payload (ejector) | Rated payload | 30 | ton | Cat 730 EJ |  |  | 30 ton |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-HAUL-ADT-05,EW-HAUL-ADT-10 |  | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
ADT-EJ-42T | Hauling | Articulated dump truck (ADT) | Ejector body | 42 t payload (ejector) | Rated payload | 42 | ton | Cat 740 EJ |  |  | 42 ton |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-HAUL-ADT-05,EW-HAUL-ADT-10 |  | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
RDT-770 | Hauling | Rigid off-highway truck | Quarry/construction | 42.1 t payload | Rated payload | 42.1 | ton | Cat 770 |  |  | 42.1 ton |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 5.22 | 6.7 | 8.18 | Cat VisionLink Dec 2022, model 770G [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy |  |  | Y | 1913 | 1913 | EW-HAUL-RDT-10 | No rental or FEMA rate. Transport assumed multi-axle/partial disassembly (verify). | Needs rate; Needs rate (rental); Needs rate (owned)
RDT-772 | Hauling | Rigid off-highway truck | Quarry/construction | 51.6 t payload | Rated payload | 51.6 | ton | Cat 772 |  |  | 51.6 ton; heaped 40.8 yd3 (Cat 772 51.6 t / 40.8 yd3) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 5.88 | 7.6 | 9.33 | Cat VisionLink Dec 2022, model 772G [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy |  |  | Y | 1913 | 1913 | EW-HAUL-RDT-10 | No rental or FEMA rate. Transport assumed multi-axle/partial disassembly (verify). | Needs rate; Needs rate (rental); Needs rate (owned)
RDT-773 | Hauling | Rigid off-highway truck | Quarry/construction | 61.7 t payload | Rated payload | 61.7 | ton | Cat 773 |  |  | 61.7 ton; heaped 46.75 yd3 (Cat 773 61.7 t / 46.75 yd3) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 7.66 | 9.92 | 12.17 | Cat VisionLink Dec 2022, model 773G [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy |  |  | Y | 1913 | 1913 | EW-HAUL-RDT-10 | No rental or FEMA rate. Transport assumed multi-axle/partial disassembly (verify). | Needs rate; Needs rate (rental); Needs rate (owned)
RDT-775 | Hauling | Rigid off-highway truck | Quarry/construction | 70.5 t payload | Rated payload | 70.5 | ton | Cat 775 |  |  | 70.5 ton |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 8.26 | 10.73 | 13.21 | Cat VisionLink Dec 2022, model 775G [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy |  |  | Y | 1913 | 1913 | EW-HAUL-RDT-10 | No rental or FEMA rate. Transport assumed multi-axle/partial disassembly (verify). | Needs rate; Needs rate (rental); Needs rate (owned)
RDT-777 | Hauling | Rigid off-highway truck | Quarry/construction | 101.1 t payload | Rated payload | 101.1 | ton | Cat 777 |  |  | 101.1 ton; heaped 83.1 yd3 (Cat 777 101.1 t / 83.1 yd3) |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 12 | 15.63 | 19.27 | Cat VisionLink Dec 2022, model 777G [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy |  |  | Y | 1913 | 1913 | EW-HAUL-RDT-10 | No rental or FEMA rate. Transport assumed multi-axle/partial disassembly (verify). | Needs rate; Needs rate (rental); Needs rate (owned)
DUMPER-3T | Hauling | Site dumper | Tracked/wheeled site dumper | ~6,600 lb payload | Payload | 6613 | lb | Takeuchi/Yanmar TA3SH-type |  |  | 6,613 lb |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 575 | 1400 | 3500 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 |  | Rent: Columbus only. | Needs fuel gal/hr; Needs rate (owned)
DUMPER-6T | Hauling | Site dumper | Tracked/wheeled site dumper | ~13,200 lb payload | Payload | 13200 | lb | 6MDXS (13,230 lb); 13,200 lb dumper |  |  | 13,200 lb |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 775 | 2050 | 5250 | 4000 | 6500 | bare |  |  | C25;A26 | 2025-2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 |  | Rent: Median (=mean) of 2 sources: C 6MDXS 1050/2600/6500; A 500/1500/4000. | Needs fuel gal/hr; Needs rate (owned)
CRAWLER-CARRIER | Hauling | Crawler carrier | Rotating crawler carrier | RT7R class | Model | RT7R |  | Columbus RT7R |  |  |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 1600 | 3975 | 9900 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 |  | Rent: Columbus only. | Needs fuel gal/hr; Needs rate (owned)
DT-ROAD-7CY | Hauling | On-road dump truck | Straight truck | 7 CY struck | Struck capacity | 7 | CY | Freightliner M2 106 / 108SD / 114SD (FEMA basis) |  | 330 | 7 CY |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8720 | 95.38 | FEMA 2025 | 5.61 | 7.38 | 9.62 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 68.37 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-HAUL-TRK-05,EW-HAUL-TRK-10,EW-HAUL-TRK-20 | Bare (no driver) dump truck rental not found; see operated DT-OP rows. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
DT-ROAD-9CY | Hauling | On-road dump truck | Straight truck | 9 CY struck | Struck capacity | 9 | CY | Freightliner M2 106 / 108SD / 114SD (FEMA basis) |  | 350 | 9 CY |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8721 | 100.63 | FEMA 2025 | 5.95 | 7.82 | 10.21 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 72.01 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-HAUL-TRK-05,EW-HAUL-TRK-10,EW-HAUL-TRK-20 | Bare (no driver) dump truck rental not found; see operated DT-OP rows. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
DT-ROAD-12CY | Hauling | On-road dump truck | Straight truck | 12 CY struck | Struck capacity | 12 | CY | Freightliner M2 106 / 108SD / 114SD (FEMA basis) |  | 350 | 12 CY |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8722 | 120.74 | FEMA 2025 | 5.95 | 7.82 | 10.21 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 92.12 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-HAUL-TRK-05,EW-HAUL-TRK-10,EW-HAUL-TRK-20 | Bare (no driver) dump truck rental not found; see operated DT-OP rows. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
DT-ROAD-14CY | Hauling | On-road dump truck | Straight truck | 14 CY struck | Struck capacity | 14 | CY | Freightliner M2 106 / 108SD / 114SD (FEMA basis) |  | 470 | 14 CY |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8723 | 122.94 | FEMA 2025 | 7.99 | 10.51 | 13.71 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 84.47 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-HAUL-TRK-05,EW-HAUL-TRK-10,EW-HAUL-TRK-20 | Bare (no driver) dump truck rental not found; see operated DT-OP rows. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Non-monotonic vs DT-ROAD-12CY - source data; Needs rate (rental)
DT-ROAD-18CY | Hauling | On-road dump truck | Straight truck | 18 CY struck | Struck capacity | 18 | CY | Freightliner M2 106 / 108SD / 114SD (FEMA basis) |  | 525 | 18 CY |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8724 | 147.99 | FEMA 2025 | 8.93 | 11.74 | 15.31 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 105.02 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-HAUL-TRK-05,EW-HAUL-TRK-10,EW-HAUL-TRK-20 | Bare (no driver) dump truck rental not found; see operated DT-OP rows. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
DT-OP-3AXLE | Hauling | On-road dump truck | Operated (with driver) | 3-axle (tri-axle), operated | Axles | 3 | axles | [5 empty] | diesel | Truck Driver (per WD class/axles) - included in operated rate | hr (operated) | [5 empty] | operated | 106.14 |  | MNDLI;DTR | Dec 2025-Sep 2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-HAUL-TRK-05,EW-HAUL-TRK-10,EW-HAUL-TRK-20 | Operated rate INCLUDES driver: do not add labor. MN figure is a prevailing-wage minimum for Region 1. Rent (operated, incl. operator): Median (=mean) of MN DLI Region 1 3-axle $104.77/hr (May 1 2026) and dumptruckrates.com range midpoint $107.50 ($85-130/hr). Low/high = 85/130. | Needs rate (owned); Needs fuel gal/hr
DT-OP-4AXLE | Hauling | On-road dump truck | Operated (with driver) | 4+ axle, operated | Axles | 4 | axles | [5 empty] | diesel | Truck Driver (per WD class/axles) - included in operated rate | hr (operated) | [5 empty] | operated | 140.96 |  | MNDLI | May 1 2026 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-HAUL-TRK-05,EW-HAUL-TRK-10,EW-HAUL-TRK-20 | Operated rate INCLUDES driver. Rent (operated, incl. operator): MN DLI Region 1 4+ axle minimum. | Needs rate (owned); Needs fuel gal/hr
DT-OP-SEMI | Hauling | On-road dump truck | Operated (with driver) | Tractor-trailer (semi end dump), operated | Configuration | tractor-trailer | [6 empty] | diesel | Truck Driver (per WD class/axles) - included in operated rate | hr (operated) | [5 empty] | operated | 134.62 |  | MNDLI | May 1 2026 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-HAUL-TRK-10,EW-HAUL-TRK-20 | Operated rate INCLUDES driver. Rent (operated, incl. operator): MN DLI Region 1 tractor-trailer minimum. | Needs rate (owned); Needs fuel gal/hr
DTRL-8590 | Hauling | Dump trailer | Rear dump trailer | Rear dump trailer 20 ft (13 ton, 23.7 CY) | Capacity | 23.7 | CY |  |  |  | 23.7 CY |  | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8590 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Towed by a truck tractor (TRK-TRAC rows). FEMA 8590: Rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
DTRL-8591 | Hauling | Dump trailer | End dump trailer 30 CY | End dump trailer 30 CY | Capacity | 30 | CY |  |  |  | 30 CY |  | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8591 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Towed by a truck tractor (TRK-TRAC rows). FEMA 8591: Rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
DTRL-8637 | Hauling | Dump trailer | Bottom-dump trailer, off-highway | Bottom-dump trailer, off-highway (Load King 2842) 28 CY | Capacity | 28 | CY |  |  |  | 28 CY |  | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8637 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Towed by a truck tractor (TRK-TRAC rows). FEMA 8637: Rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
WT-2000 | Hauling | Water truck / tank | On-highway | 2,000 gal on-highway | Tank capacity | 2000 | gal |  |  |  | 2,000 gal |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | 604 | 1752 | 5082 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-WATER,EW-DUST | Rent: Wheeler only. | Needs fuel gal/hr; Needs rate (owned)
WT-2500 | Hauling | Water truck / tank | On-highway | 2,500 gal (4x2) | Tank capacity | 2500 | gal |  |  |  | 2,500 gal |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8780 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-WATER,EW-DUST | FEMA 8780: FEMA rate not reliably extracted. | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned; FEMA code exists)
WT-4000 | Hauling | Water truck / tank | On-highway | 4,000 gal (6x4) | Tank capacity | 4000 | gal |  |  |  | 4,000 gal |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | 1057 | 3067 | 8894 |  |  | bare |  |  | W25 | 2025 | B | 8781 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-WATER,EW-DUST | Rent: Wheeler only. FEMA 8781: FEMA rate not reliably extracted. | Needs fuel gal/hr; Needs rate (owned; FEMA code exists)
WT-6000-ADT | Hauling | Water truck / tank | Off-road (ADT chassis) | 6,000 gal ADT-based | Tank capacity | 6000 | gal |  |  |  | 6,000 gal |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2337.5 | 7013 | 20338 |  |  | bare |  |  | W25 | 2025 | C | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-WATER,EW-DUST | Rent: Day = midpoint of Wheeler's $2,197-2,478/day (two units); week/4-week derived with catalog multipliers. Rent_week = day x Settings week/day multiplier (3.0); Rent_4wk = week x 4wk/week multiplier (2.9) - method C. | Needs fuel gal/hr; Needs rate (owned)
WT-8000-ADT | Hauling | Water truck / tank | Off-road (ADT chassis) | 8,000 gal ADT-based | Tank capacity | 8000 | gal |  |  |  | 8,000 gal |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2810 | 8149 | 23631 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-WATER,EW-DUST | Rent: Wheeler only. | Needs fuel gal/hr; Needs rate (owned)
WT-9000-ADT | Hauling | Water truck / tank | Off-road (ADT chassis) | 9,000 gal ADT-based | Tank capacity | 9000 | gal |  |  |  | 9,000 gal |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 3550 | 10295 | 29857 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-WATER,EW-DUST | Rent: Wheeler only. | Needs fuel gal/hr; Needs rate (owned)
WT-TANKER-4000 | Hauling | Water truck / tank | Water tanker | 4,000 gal tanker | Tank capacity | 4000 | gal |  |  |  | 4,000 gal |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8614 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-WATER,EW-DUST | FEMA 8614: FEMA rate not reliably extracted. | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned; FEMA code exists)
WTRL-4000 | Hauling | Water truck / tank | Water trailer (towed) | 4,000 gal water trailer | Tank capacity | 4000 | gal |  |  |  | 4,000 gal |  | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8610 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-WATER | FEMA 8610: Rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
WTRL-6000 | Hauling | Water truck / tank | Water trailer (towed) | 6,000 gal water trailer | Tank capacity | 6000 | gal |  |  |  | 6,000 gal |  | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8611 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-WATER | FEMA 8611: Rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
WTRL-10000 | Hauling | Water truck / tank | Water trailer (towed) | 10,000 gal water trailer | Tank capacity | 10000 | gal |  |  |  | 10,000 gal |  | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8612 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-WATER | FEMA 8612: Rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
WTRL-14000 | Hauling | Water truck / tank | Water trailer (towed) | 14,000 gal water trailer | Tank capacity | 14000 | gal |  |  |  | 14,000 gal |  | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8613 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-WATER | FEMA 8613: Rate not captured in owned-rate notes. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
WTRL-500 | Hauling | Water truck / tank | Water trailer (towed) | 500 gal water trailer | Tank capacity | 500 | gal |  |  |  | 500 gal |  | none (towed) | None (non-operated item) | day/wk/4wk | 155 | 455 | 1337 | 990 | 1683 | bare |  |  | W25;B25 | 2025-2026 | A |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | EW-DUST | Rent: Median (=mean) of 2 sources: W 200/580/1683; B 110/330/990. | Needs rate (owned)
WTANK-12000 | Hauling | Water truck / tank | Stand tank | 12,000 gal stand tank | Tank capacity | 12000 | gal |  |  |  | 12,000 gal |  | none | None (non-operated item) | day/wk/4wk | 461 | 1336 | 3875 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 |  | Rent: Wheeler only. | Needs rate (owned)
CP-PLATE-FWD | Compaction | Plate compactor | Forward, small | ~150-200 lb forward plate | Machine weight | 175 | lb | Wacker Neuson WP1550AW (19.5 in, 194 lb, 100 ft/min, 9,750 ft2/hr); VP1135; Multiquip MVC82 | 175 |  |  |  | gas | Laborer (per WD group) | day/wk/4wk | 78 | 268 | 858 | 485 | 1080 | bare |  |  | W25;B25;R25;N25 | 2025-2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed | 175 |  | N | 200 | 200 | EW-COMP-PLATE | No FEMA plate/rammer rows. Hauled in pickup/trailer. Rent: Median of 4 sources (W 128/372/1080; B 80/240/720; R 75/295/995; N 55/195/485). | Needs fuel gal/hr; Needs rate (owned)
CP-PLATE-REV | Compaction | Plate compactor | Reversible | ~800-1,100 lb reversible plate | Machine weight | 950 | lb | Wacker DPU5545/6555; Mikasa MVH408 (836 lb) | 950 |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | 240 | 821 | 2418 | 1850 | 2595 | bare |  |  | W25;B25;R25;N25 | 2025-2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed | 950 |  | N | 200 | 200 | EW-COMP-PLATE,EW-COMP-TRENCH | Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 4 sources (W 302/876/2541; B 255/765/2295; R 225/895/2595; N 200/740/1850). | Needs fuel gal/hr; Needs rate (owned)
CP-RAMMER | Compaction | Rammer (jumping jack) | Gas rammer | Rammer 100-140 lb | Machine weight | 130 | lb | Wacker Neuson BS60-4As (11 x 13.4 in shoe, 159 lb, 28.9 ft/min, ~1,590 ft2/hr); BS50; MTX60 | 130 |  |  |  | gas | Laborer (per WD group) | day/wk/4wk | 85 | 255 | 765 | 485 | 1137 | bare |  |  | W25;B25;N25 | 2025-2026 | A |  |  |  |  | 0.26 |  | Wacker Neuson BS60-4As 1.0 L/hr = 0.26 gal/hr [WN-BS60] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed | 130 |  | N | 200 | 200 | EW-COMP-RAMMER | Rent: Median of 3 sources (W 135/392/1137; B 85/255/765; N 55/195/485). | Needs rate (owned)
CP-HANDVIB | Compaction | Hand-held vibratory compactor | FEMA hand-held | Hand-held vibratory (28 hp as listed) | HP (as listed) | 28 | hp | FEMA 8220 |  | 28 |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8220 | 5.54 | FEMA 2025 | 0.48 | 0.63 | 0.82 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 3.23 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA: 28 HP looks inconsistent with a hand-held unit (as extracted). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged: HP as listed looks wrong for hand-held; verify; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
CP-TRENCH-ROLLER | Compaction | Trench roller | Remote multi-purpose | ~32-33 in, ~3,200 lb | Drum width | 33 | in | Wacker RTKX; Bomag; Multiquip RX1575 | 3200 |  | 33 in drum |  | diesel | Laborer (per WD group) | day/wk/4wk | 298 | 1030 | 3090 | 2100 | 3875 | bare |  |  | W25;B25;R25;N25 | 2025-2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 3200 |  | N | 500 | 500 | EW-COMP-TRENCH | Rent: Median of 4 sources (W 461/1336/3875; B 320/960/2880; R 275/1100/3300; N 225/780/2100). | Needs fuel gal/hr; Needs rate (owned)
CP-SSL-VIBROLL | Compaction | Vibratory roller attachment | Skid-steer attachment | 72-84 in SSL vibratory roller | Drum width | 84 | in | FEMA 8221 towed SSL roller 84 in; RTL 72 in attachment |  |  |  |  | none (attachment) | None (non-operated item) | day/wk/4wk | 250 | 875 | 2595 |  |  | bare |  |  | R25 | Spring 2025 | B | 8221 | 27.01 | FEMA 2025 | 0 | 0 | 0 | No engine (towed / attachment / non-powered) | 27.01 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | EW-COMP-SOIL-SM | Carrier (skid steer) priced separately. Rent: RTL 72 in attachment only. Ex-fuel = incl-fuel rate (no liquid fuel to back out).
CP-SD-48-SM | Compaction | Single-drum vibratory roller | Smooth drum, 50 in | 48-54 in smooth (~10,000 lb) | Drum width | 50 | in | Cat CS34 (50 in, 9,800 lb); Cat CS5 (50 in, ~9,800-10,307 lb, 74.6 hp) | 9800 | 74.6 | 50 in drum |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 1.27 | 1.67 | 2.18 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 9800 |  | N | 500 | 500 | EW-COMP-SOIL-6,EW-COMP-SOIL-8 | Wheeler drum widths inferred from Cat specs (notes). Owned rate removed in revision: earlier interpolation used a blank HP endpoint (CP-SD-48PAD). Cat CS34 50 in, 9,800 lb, max 5.5 mph [CAT-CMP-PG]. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned)
CP-SD-66-SM | Compaction | Single-drum vibratory roller | Smooth drum, 66 in | 66-67 in smooth | Drum width | 66 | in | Cat CS44B (66 in, 15,895 lb, max 7 mph) / CS7; Volvo SD45; Wacker SV414T 67 in | 15895 |  | 66 in drum |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 725 | 1775 | 4400 | 3750 | 6988 | bare |  |  | W25;C25;A26 | 2025-2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 15895 |  | N | 500 | 500 | EW-COMP-SOIL-6,EW-COMP-SOIL-8 | Wheeler drum widths inferred from Cat specs (notes). Fuel removed in revision (CS54B drum width not in notes). Weight = Cat CS44B [CAT-CMP-PG]. Rent: Median of 3 sources (W CS44 831/2410/6988; C SV414T 725/1775/4400; A 500/1500/3750). | Needs rate (owned); Needs fuel gal/hr
CP-SD-66-PAD | Compaction | Single-drum vibratory roller | Padfoot drum, 66 in | 66 in padfoot | Drum width | 66 | in | Cat CP44/CP7; Wacker RC70P | 16990 |  | 66 in drum |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 729 | 2135 | 6259 | 4005 | 8512 | bare |  |  | W25;B25 | 2025-2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 16990 |  | N | 500 | 500 | EW-COMP-SOIL-6,EW-COMP-SOIL-8 | Wheeler drum widths inferred from Cat specs (notes). Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median (=mean) of 2 sources: W CP44 1012/2935/8512; B RC70P 445/1335/4005. Wide spread; treat as range. | Needs fuel gal/hr; Needs rate (owned)
CP-SD-84-SM | Compaction | Single-drum vibratory roller | Smooth drum, 84 in | 84 in smooth | Drum width | 84 | in | Cat CS56/CS74 (84 in); Volvo SV544T; Wacker RC110; Cat CS56B (84 in, 25,346 lb, 1,400-1,830 vpm), CS10 GC (84 in, 23,136 lb) | 23136 |  | 84 in drum |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 700 | 1988 | 5083 | 4500 | 9910 | bare |  |  | W25;C25;B25;A26 | 2025-2026 | A |  |  |  |  | 2.91 |  | Cat Dec 2022 single value, CS56B (single) [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 23136 |  | N | 550 | 550 | EW-COMP-SOIL-6,EW-COMP-SOIL-8,EW-COMP-SOIL-12 | Wheeler drum widths inferred from Cat specs (notes). Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 4 sources (W CS56/74 avg 1178/3418/9910; C 800/1975/4900; B 585/1755/5265; A 600/2000/4500). | Needs rate (owned)
CP-SD-84-PAD | Compaction | Single-drum vibratory roller | Padfoot drum, 84 in | 84 in padfoot | Drum width | 84 | in | Cat CP56/CP74; Wacker RC110P; Cat CP56B (84 in, 25,707 lb) | 25707 |  | 84 in drum |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 967 | 2835 | 8309 | 5310 | 11308 | bare |  |  | W25;B25 | 2025-2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 25707 |  | N | 550 | 550 | EW-COMP-SOIL-6,EW-COMP-SOIL-8,EW-COMP-SOIL-12 | Wheeler drum widths inferred from Cat specs (notes). Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median (=mean) of 2 sources: W CP56/74 avg 1344/3899/11308; B RC110P 590/1770/5310. Wide spread. | Needs fuel gal/hr; Needs rate (owned)
CP-SD-84-HVY | Compaction | Single-drum vibratory roller | Smooth drum, 84 in | 84 in heavy (CS74/CS19 class, to ~41,600 lb) | Drum width | 84 | in | Cat CS74 (84 in), CS19 (41,641 lb); 120-176 hp gross | 41641 | 176 | 84 in drum |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 1284 | 3724 | 10799 |  |  | bare |  |  | W25 | 2025 | B |  |  |  |  | 3.09 |  | Cat Dec 2022 single value, CS74B (single) [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 41641 |  | N | 550 | 550 | EW-COMP-SOIL-6,EW-COMP-SOIL-8,EW-COMP-SOIL-12 | Wheeler drum widths inferred from Cat specs (notes). Rent: Wheeler CS74 only. | Needs rate (owned)
CP-SD-48PAD | Compaction | Single-drum vibratory roller | Padfoot, small | ~48 in padfoot (FEMA 2-ton class) | Drum width | 48 | in | Single-drum vibratory (FEMA 8219) |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8219 | 94.55 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | EW-COMP-SOIL-6 | Width not sourced (48-54 in soil rollers: no rental lines found). FEMA: Taxonomy lists 8219 as 2-ton pavement roller; owned notes list it as single-drum vibratory. Owned-notes label used. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; label conflict 8219; Needs rate (rental)
CP-SD-51PAD-CP563 | Compaction | Single-drum vibratory roller | Padfoot | Cat CP-563D 51 in (to 145 hp) | Drum width | 51 | in | Cat CP-563D |  | 145 | 51 in drum |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8224 | 124.72 | FEMA 2025 | 2.47 | 3.24 | 4.23 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 112.86 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | EW-COMP-SOIL-6,EW-COMP-SOIL-8 | Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
CP-TAMP-815 | Compaction | Wheeled soil compactor (tamping) | Tamping-foot | Cat 815 (~249 hp) | Net HP | 249 | hp | Cat 815 |  | 249 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 2629 | 7623 | 22107 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 5.17 | 6.84 | 8.51 | Cat VisionLink Dec 2022, model 815K [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-COMP-SOIL-8,EW-COMP-SOIL-12 | Weight not in notes. Rent: Wheeler only. | Needs rate (owned)
CP-TAMP-825 | Compaction | Wheeled soil compactor (tamping) | Tamping-foot | Cat 825 (~405 hp) | Net HP | 405 | hp | Cat 825 |  | 405 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | 4034 | 11697 | 33922 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 7.76 | 10.06 | 12.37 | Cat VisionLink Dec 2022, model 825K [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | EW-COMP-SOIL-8,EW-COMP-SOIL-12 | Weight not in notes. Rent: Wheeler only. | Needs rate (owned)
CP-LANDFILL-816 | Compaction | Landfill compactor | Landfill/sanitation | Cat 816 (~249 hp) | Net HP | 249 | hp | Cat 816 |  | 249 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8225 | 197.35 | FEMA 2025 | 4.24 | 5.57 | 7.26 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 176.96 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 |  | Specialty; weight not in notes. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
CP-LANDFILL-826 | Compaction | Landfill compactor | Landfill/sanitation | Cat 826 (~405 hp) | Net HP | 405 | hp | Cat 826 |  | 405 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8226 | 243.88 | FEMA 2025 | 6.89 | 9.05 | 11.81 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 210.76 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 |  | Specialty; weight not in notes. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
CP-LANDFILL-836 | Compaction | Landfill compactor | Landfill/sanitation | Cat 836 (~496 hp) | Net HP | 496 | hp | Cat 836 |  | 496 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8227 | 400.69 | FEMA 2025 | 8.44 | 11.09 | 14.46 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 360.1 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 |  | Specialty; weight not in notes. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
CP-TANDEM-SMALL | Paving | Tandem vibratory roller (asphalt) | Utility ride-on 1.5-3 t | 36-54 in double drum | Drum width | 47 | in | Cat CB1.7 (35 in, 3,538 lb)-CB4.4 (55 in, 8,362 lb); Wacker RD12/RD28; Bomag SW354; Cat CB2.7 (47.2 in, 5,936 lb) | 3538 |  | 36-54 in drums |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 299 | 796 | 2176 | 1875 | 2795 | bare |  |  | C25;B25;N25;W25 | 2025-2026 | A | 8218 | 92.08 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 3538 |  | N | 500 | 500 | PV-ROLL-HMA,EW-COMP-SOIL-SM | Rent: Median of 4 sources (C 325/775/1900; B 273/818/2453; N 215/650/1875; W 332/964/2795). FEMA: FEMA 8218 Bomag BW100AD-3 (to 33 hp). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr
CP-TANDEM-47 | Paving | Tandem vibratory roller (asphalt) | Utility ride-on | 47 in double drum (to 75 hp) | Drum width | 47.2 | in | Bomag BW120AD-4 |  | 75 | 47 in drums |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8222 | 61.71 | FEMA 2025 | 1.28 | 1.68 | 2.19 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 55.56 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | PV-ROLL-HMA | FEMA: Lower than the smaller BW100 (8218 $92.08). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged: 8222 lower than smaller 8218; verify; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
CP-TANDEM-54 | Paving | Tandem vibratory roller (asphalt) | Mid tandem | 54 in double drum | Drum width | 54 | in | Bomag SW504 |  |  | 54 in drums |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 425 | 1050 | 2600 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | PV-ROLL-HMA | Rent: Columbus only. | Needs fuel gal/hr; Needs rate (owned)
CP-TANDEM-67 | Paving | Tandem vibratory roller (asphalt) | Large tandem | 66-67 in double drum | Drum width | 67 | in | Bomag SW774; Cat CB8/CB10 (67 in; CB10 21,642-22,255 lb, 36.5 gal tank) | 21642 |  | 67 in drums |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 750 | 1850 | 4590 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 21642 |  | N | 550 | 550 | PV-ROLL-HMA | Rent: Columbus only. Oscillation versions ~$50-75/day more. | Needs fuel gal/hr; Needs rate (owned)
CP-TANDEM-79 | Paving | Tandem vibratory roller (asphalt) | Large tandem | 79 in double drum | Drum width | 79 | in | Bomag SW884; Cat CB13 |  |  | 79 in drums |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 975 | 2400 | 5950 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | PV-ROLL-HMA | Rent: Columbus only. | Needs fuel gal/hr; Needs rate (owned)
CP-TANDEM-84 | Paving | Tandem vibratory roller (asphalt) | Highway tandem | 84 in double drum (~29,000-32,000 lb) | Drum width | 84 | in | Cat CB15/CB16 | 32000 |  | 84 in drums |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 1496 | 4337 | 12578 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 32000 |  | N | 550 | 550 | PV-ROLL-HMA | Rent: Wheeler CB16 only. | Needs fuel gal/hr; Needs rate (owned)
CP-COMBO | Paving | Combination roller | Steel drum + rubber tire | Combination 2.7-4.0 t | Model | CC2.7/CC4.0 |  | Cat CC2.7, CC4.0 |  |  |  |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | PV-ROLL-HMA |  | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
CP-PNEU-SMALL | Paving | Pneumatic roller | Small 9-wheel | 9-wheel ~5,000 lb | Machine weight | 5000 | lb | Cat CT3 | 5000 |  |  |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 559 | 1621 | 4701 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 5000 |  | N | 500 | 500 | PV-ROLL-HMA | Rent: Wheeler only. | Needs fuel gal/hr; Needs rate (owned)
CP-PNEU-68 | Paving | Pneumatic roller | 9-wheel 68 in / 11-wheel 84 in | ~33,000 lb ballasted (CW16 class) | Rolling width | 68 | in | Cat CW16; Bomag BW11RH (68 in, to 100 hp) | 33000 | 100 |  |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 831 | 2410 | 6988 |  |  | bare |  |  | W25 | 2025 | B | 8223 | 114.91 | FEMA 2025 |  | 1.8 |  | Cat Dec 2022 single value, CW16 (single) [CATFUEL22] | 108.32 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 33000 |  | N | 550 | 550 | PV-ROLL-HMA,EW-COMP-SOIL-8 | Rent: Wheeler CW16 only. FEMA: FEMA 8223 Bomag BW11RH. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
CP-PNEU-82 | Paving | Pneumatic roller | Heavy | 82 in, to ~59,500 lb ballasted (CW34 class) | Rolling width | 82 | in | Cat CW34 (82 in, 8 tires, 22,050-59,525 lb, max 12 mph) | 59525 |  |  |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 1416 | 4107 | 11911 |  |  | bare |  |  | W25 | 2025 | B |  |  |  |  | 1.45 |  | Cat Dec 2022 single value, CW34 (single) [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 59525 |  | maybe | 550 | 550 | PV-ROLL-HMA,EW-PROOFROLL | Cat CW34 fuel (1.45) below CW16 (1.80) as published. Rent: Wheeler only. | Needs rate (owned)
CP-PNEU-TOWED | Compaction | Pneumatic roller | Towed 11-wheel | Towed pneumatic 11-wheel | Wheels | 11 | wheels | FEMA 8228 |  |  |  |  | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8228 | 14.94 | FEMA 2025 | 0 | 0 | 0 | No engine (towed / attachment / non-powered) | 14.94 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Tow tractor priced separately. Ex-fuel = incl-fuel rate (no liquid fuel to back out). | Needs rate (rental)
CP-STEEL-TOWED | Compaction | Static steel drum roller | Towed | Towed static steel drum | Type | towed |  | FEMA 8229 |  |  |  |  | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8229 | 2.69 | FEMA 2025 | 0 | 0 | 0 | No engine (towed / attachment / non-powered) | 2.69 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Tow tractor priced separately. Ex-fuel = incl-fuel rate (no liquid fuel to back out). | Needs rate (rental)
CP-PAVEROLLER-2T | Paving | Static tandem roller | Pavement roller | 2-ton pavement roller | Weight class | 2 | ton | FEMA 8129 |  |  |  |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8129 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | PV-ROLL-HMA | FEMA 8129: Code listed; rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-PAVER-TOWED | Paving | Asphalt paver | Towed | Towed paver 8 ft | Paving width | 8 | ft | FEMA 8430 |  |  |  |  | none (towed) | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8430 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | PV-HMA-LOT | FEMA 8430: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
PV-PAVER-P195 | Paving | Asphalt paver | Compact/commercial (Weiler) | 3'10"-7' (P195 class) | Paving range (max) | 7 | ft | Weiler P195 (13,000 lb) | 13000 |  | 3'10"-7' range |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 1356 | 3932 | 11403 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 13000 |  | N | 500 | 500 | PV-HMA-LOT | Rent: Wheeler only. | Needs fuel gal/hr; Needs rate (owned)
PV-PAVER-COMM | Paving | Asphalt paver | Commercial (Weiler) | 8-15'8" (P265-P395B class) | Paving range (max) | 15.7 | ft | Weiler P265, P385B, P395B (24,000 lb) | 24000 |  | 8'-15'8" range |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 1662 | 4819 | 13976 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 24000 |  | N | 550 | 550 | PV-HMA-LOT,PV-HMA-ROAD | Rent: Wheeler P385 only. | Needs fuel gal/hr; Needs rate (owned)
PV-PAVER-AP355 | Paving | Asphalt paver | Compact track | Cat AP355 | Model | AP355 |  | Cat AP355 |  |  |  |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  |  | 1.19 |  | Cat Dec 2022 single value, AP355 (single) [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | PV-HMA-LOT |  | Needs rate; Needs rate (rental); Needs rate (owned)
PV-PAVER-AP400 | Paving | Asphalt paver | Highway, wheel | Cat AP400 (8'-19'6") | Paving range (max) | 19.5 | ft | Cat AP400 | 30000 |  | 8'-19'6" range |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  |  | 1.95 |  | Cat Dec 2022 single value, AP400 [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 30000 |  | N | 550 | 550 | PV-HMA-ROAD,PV-HMA-LOT | Paver output is governed by plant/truck supply, not the paver (notes). Cat single fuel value used as medium. Paver ex-fuel is low-confidence on fuel side (3-4% share). | Needs rate; Needs rate (rental); Needs rate (owned)
PV-PAVER-AP455 | Paving | Asphalt paver | Highway, track | Cat AP455 (8'-19'6") | Paving range (max) | 19.5 | ft | Cat AP455 (120 hp) | 31533 | 120 | 8'-19'6" range |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8431 | 262.71 | FEMA 2025 |  | 2.03 |  | Cat Dec 2022 single value, AP455 [CATFUEL22] | 255.28 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 31533 |  | N | 550 | 550 | PV-HMA-ROAD,PV-HMA-LOT | Paver output is governed by plant/truck supply, not the paver (notes). Cat single fuel value used as medium. Paver ex-fuel is low-confidence on fuel side (3-4% share). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
PV-PAVER-AP500 | Paving | Asphalt paver | Highway, wheel | Cat AP500 (8'-19'6") | Paving range (max) | 19.5 | ft | Cat AP500 |  |  | 8'-19'6" range |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8434 | 274.31 | FEMA 2025 |  | 2.51 |  | Cat Dec 2022 single value, AP500 [CATFUEL22] | 265.12 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | PV-HMA-ROAD,PV-HMA-LOT | Paver output is governed by plant/truck supply, not the paver (notes). Cat single fuel value used as medium. Paver ex-fuel is low-confidence on fuel side (3-4% share). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
PV-PAVER-AP555 | Paving | Asphalt paver | Highway, track | Cat AP555 (8'-20') | Paving range (max) | 20 | ft | Cat AP555 (148 hp) | 33689 | 148 | 8'-20' range |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 3339 | 9682 | 28078 |  |  | bare |  |  | W25 | 2025 | B | 8432 | 271.01 | FEMA 2025 |  | 2.62 |  | Cat Dec 2022 single value, AP555 [CATFUEL22] | 261.42 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 33689 |  | N | 550 | 550 | PV-HMA-ROAD,PV-HMA-LOT | Paver output is governed by plant/truck supply, not the paver (notes). Cat single fuel value used as medium. Paver ex-fuel is low-confidence on fuel side (3-4% share). Rent: Wheeler only; $600 cleaning fee if not cleaned. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
PV-PAVER-AP600 | Paving | Asphalt paver | Highway, wheel | Cat AP600 (8'-20'6") | Paving range (max) | 20.5 | ft | Cat AP600 |  |  | 8'-20'6" range |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  |  | 2.91 |  | Cat Dec 2022 single value, AP600 [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | PV-HMA-ROAD,PV-HMA-LOT | Paver output is governed by plant/truck supply, not the paver (notes). Cat single fuel value used as medium. Paver ex-fuel is low-confidence on fuel side (3-4% share). | Needs rate; Needs rate (rental); Needs rate (owned)
PV-PAVER-AP655 | Paving | Asphalt paver | Highway, track | Cat AP655 (8'-20'6") | Paving range (max) | 20.5 | ft | Cat AP655 (173 hp) | 40560 | 173 | 8'-20'6" range |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 3731 | 10821 | 31381 |  |  | bare |  |  | W25 | 2025 | B | 8433 | 308.47 | FEMA 2025 |  | 3.04 |  | Cat Dec 2022 single value, AP655 [CATFUEL22] | 297.34 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 40560 |  | N | 550 | 550 | PV-HMA-ROAD,PV-HMA-LOT | Paver output is governed by plant/truck supply, not the paver (notes). Cat single fuel value used as medium. Paver ex-fuel is low-confidence on fuel side (3-4% share). Rent: Wheeler only; $600 cleaning fee if not cleaned. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
PV-PAVER-AP1000 | Paving | Asphalt paver | Highway, wheel | Cat AP1000 (10'-25'6") | Paving range (max) | 25.5 | ft | Cat AP1000 | 42620 |  | 10'-25'6" range |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8435 | 295.49 | FEMA 2025 |  | 3.43 |  | Cat Dec 2022 single value, AP1000 [CATFUEL22] | 282.94 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 42620 |  | N | 550 | 550 | PV-HMA-ROAD,PV-HMA-LOT | Paver output is governed by plant/truck supply, not the paver (notes). Cat single fuel value used as medium. Paver ex-fuel is low-confidence on fuel side (3-4% share). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
PV-PAVER-AP1055 | Paving | Asphalt paver | Highway, track | Cat AP1055 (9'10"-25') | Paving range (max) | 25 | ft | Cat AP1055 | 45087 |  | 9'10"-25' range |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 4230 | 12267 | 35574 |  |  | bare |  |  | W25 | 2025 | B |  |  |  |  | 3.65 |  | Cat Dec 2022 single value, AP1055 [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 45087 |  | maybe | 550 | 550 | PV-HMA-ROAD,PV-HMA-LOT | Paver output is governed by plant/truck supply, not the paver (notes). Cat single fuel value used as medium. Paver ex-fuel is low-confidence on fuel side (3-4% share). Rent: Wheeler only; $600 cleaning fee if not cleaned. | Needs rate (owned)
PV-MTV-8436 | Paving | Material transfer vehicle / pickup machine | MTV | Pickup machine / MTV (FEMA 8436) | FEMA code | 8436 |  | Pickup machine / MTV |  |  |  |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8436 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | PV-HMA-ROAD | Weight not in notes. FEMA 8436: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-MTV-8437 | Paving | Material transfer vehicle / pickup machine | MTV | Pickup machine / MTV (FEMA 8437) | FEMA code | 8437 |  | Pickup machine / MTV |  |  |  |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8437 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | PV-HMA-ROAD | Weight not in notes. FEMA 8437: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-MTV-8438 | Paving | Material transfer vehicle / pickup machine | MTV | Pickup machine / MTV (FEMA 8438) | FEMA code | 8438 |  | Pickup machine / MTV |  |  |  |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8438 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | PV-HMA-ROAD | Weight not in notes. FEMA 8438: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-MTV-8439 | Paving | Material transfer vehicle / pickup machine | MTV | Roadtec MTV-1000C (FEMA 8439) | FEMA code | 8439 |  | Roadtec MTV-1000C |  |  |  |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8439 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | PV-HMA-ROAD | Weight not in notes. FEMA 8439: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-PAVER-BELTEXT | Paving | Asphalt paver | Attachment | Paver belt extension | Type | belt ext. |  | FEMA 8447 |  |  |  |  | none (attachment) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8447 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8447: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
PV-WIDENER-10 | Paving | Shoulder widener (grader attachment) | Widener | Widener 10 ft spread | Spread width | 10 | ft | FEMA 8335 |  |  |  |  | none (attachment) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8335 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8335: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
PV-MILL-SSL | Paving | Cold planer | Skid-steer attachment | SSL planer attachment | Drum width |  | in | SSL planer |  |  |  |  | none (attachment) | None (non-operated item) | day/wk/4wk | 295 | 854 | 2477 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | PV-MILL-SMALL | Rent: Wheeler only; bits $8.50 each. | Needs rate (owned)
PV-MILL-SMALL | Paving | Cold planer | Small rear-loader (1-3 ft drum) | 1-3 ft drum (60-250 hp) | Drum width | 24 | in | Wirtgen W35Ri/W50Ri; Roadtec RX-100 | 20000 | 155 | 1-3 ft drum |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 2.64 | 3.47 | 4.52 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer | 20000 |  | N | 500 | 500 | PV-MILL-SMALL | Class from OneCrew (10,000-30,000 lb, 60-250 hp); weight/HP = mid of band. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned)
PV-MILL-PM310 | Paving | Cold planer | Compact (3-5 ft drum) | 39.4 in drum (Cat PM310) | Drum width | 39.4 | in | Cat PM310 (13 in max depth; 108 fpm max) |  |  | 39.4 in drum |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | PV-MILL-MID |  | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
PV-MILL-PM312 | Paving | Cold planer | Compact (3-5 ft drum) | 4 ft 1 in drum (Cat PM312) | Drum width | 49 | in | Cat PM312; Wirtgen W100Fi/W120Fi; Roadtec RX-300 (300-500 hp, 30,000-55,000 lb) | 42500 | 400 | 4'1" drum |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 3263 | 9463 | 27443 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 6.8 | 8.94 | 11.66 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal | 42500 |  | N | 550 | 550 | PV-MILL-MID | Weight/HP = mid of OneCrew compact band. Rent: Wheeler only. Haul $664-965 (<25 mi). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate (owned)
PV-MILL-PM622 | Paving | Cold planer | Large half-lane (6-12 ft drum) | ~6.6 ft drum (Cat PM622) | Drum width | 79.1 | in | Cat PM620 (79.1 in, 630 hp gross, to 328 ft/min) / PM622; Wirtgen W200Fi; Roadtec RX-505 | 77500 | 750 |  |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 5272 | 15290 | 44340 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 12.76 | 16.77 | 21.87 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted | 77500 |  | Y | 1800 | 1800 | PV-MILL-LARGE | Drum width not in notes for PM622 (79 in = Cat 2.0 m option is NOT sourced: treat spec value as placeholder). Weight/HP = mid of OneCrew large band. Width 79.1 in = Cat PM620 [CAT-PM620] (PM622 assumed same drum class). Rent: Wheeler only. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate (owned)
PV-MILL-PM822 | Paving | Cold planer | Large full-lane (6-12+ ft drum) | Full-lane (Cat PM822) | Drum width | 87 | in | Cat PM822; Wirtgen W210XF; Roadtec RX-700 | 77500 | 750 |  |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | 6179 | 17918 | 51963 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 12.76 | 16.77 | 21.87 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted | 77500 |  | Y | 1800 | 1800 | PV-MILL-LARGE | Drum width not in notes (placeholder). Weight/HP = mid of OneCrew large band. Rent: Wheeler only. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Spec width unverified; Needs rate (owned)
PV-DIST-550 | Paving | Asphalt distributor | Truck/trailer distributor | 550 gal | Tank | 550 | gal |  |  |  | 550 gal |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8580 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | PV-TACK,PV-PRIME | FEMA 8580: FEMA rate not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-DIST-1000 | Paving | Asphalt distributor | Truck/trailer distributor | 1,000 gal | Tank | 1000 | gal |  |  |  | 1,000 gal |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8581 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | PV-TACK,PV-PRIME | FEMA 8581: FEMA rate not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-DIST-2000 | Paving | Asphalt distributor | Truck/trailer distributor | 2,000 gal | Tank | 2000 | gal |  |  |  | 2,000 gal |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8582 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | PV-TACK,PV-PRIME | FEMA 8582: FEMA rate not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-DIST-4000 | Paving | Asphalt distributor | Truck/trailer distributor | 4,000 gal | Tank | 4000 | gal |  |  |  | 4,000 gal |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8583 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | PV-TACK,PV-PRIME | FEMA 8583: FEMA rate not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-CHIP-8423 | Paving | Chip spreader | Chip spreader | 2.8 CY | Size | 2.8 CY |  |  |  |  | 2.8 CY |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8423 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | PV-CHIPSEAL | FEMA 8423: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-CHIP-8424 | Paving | Chip spreader | Chip spreader | 3.5-3.8 CY | Size | 3.5-3.8 CY |  |  |  |  | 3.5-3.8 CY |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8424 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | PV-CHIPSEAL | FEMA 8424: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-CHIP-8425 | Paving | Chip spreader | Chip spreader | Mounted 8 ft | Size | Mounted 8 ft |  |  |  |  | Mounted 8 ft |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8425 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | PV-CHIPSEAL | FEMA 8425: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-CHIP-8584 | Paving | Chip spreader | Chip spreader | 13 ft | Size | 13 ft |  |  |  |  | 13 ft |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8584 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | PV-CHIPSEAL | FEMA 8584: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-BROOM-SP-8 | Paving | Broom / sweeper | Self-propelled broom | 8 ft 3-wheel open | Broom width | 8 | ft | Lay-Mor 6/8 ft (FEMA 8150) |  |  |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 412 | 1195 | 3465 |  |  | bare |  |  | W25 | 2025 | B | 8150 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | PV-SWEEP | Rent: Wheeler only. FEMA 8150: FEMA sweeper rates not reliably extracted. | Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-BROOM-SP-8CAB | Paving | Broom / sweeper | Self-propelled broom | 8 ft 4-wheel cab | Broom width | 8 | ft | [5 empty] | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 618 | 1792 | 5198 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | PV-SWEEP | Rent: Wheeler only. | Needs rate (owned); Needs fuel gal/hr
PV-BROOM-SSL | Paving | Broom / sweeper | Skid-steer pickup sweeper | SSL pickup sweeper | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 223 | 648 | 1673 | 1050 | 2295 | bare |  |  | R25;A26 | 2025-2026 | A |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | PV-SWEEP | Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median (=mean) of 2 sources: R 195/795/2295; A 250/500/1050. | Needs rate (owned)
PV-BROOM-TRACT-72 | Paving | Broom / sweeper | Tractor-mounted broom | 72 in | Broom width | 72 | in | FEMA 8151 |  |  |  |  | none (attachment) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8151 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8151: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
PV-SWEEPER-TRUCK | Paving | Broom / sweeper | Street sweeper truck | 120 in, 4.5 CY hopper | Sweep width | 120 | in | Elgin Pelican (FEMA 8157) |  |  | 4.5 CY hopper |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8157 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | PV-SWEEP | FEMA 8157: FEMA sweeper rates not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-BROOM-SP-8153 | Paving | Broom / sweeper | Self-propelled broom | Self-propelled broom 96 in | Broom width | 96 | in | FEMA 8153 |  |  |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8153 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | PV-SWEEP | FEMA 8153: FEMA broom/sweeper rates not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-BROOM-SP-8155 | Paving | Broom / sweeper | Self-propelled broom | Self-propelled broom 84 in | Broom width | 84 | in | FEMA 8155 |  |  |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8155 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | PV-SWEEP | FEMA 8155: FEMA broom/sweeper rates not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-BROOM-PULL | Paving | Broom / sweeper | Pull broom | Pull broom (towed) | Type | pull |  | FEMA 8154 |  |  |  |  | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8154 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | PV-SWEEP | FEMA 8154: FEMA rate not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
PV-SWEEPER-8158 | Paving | Broom / sweeper | Street sweeper truck | Street sweeper (FEMA 8158) | FEMA code | 8158 |  | FEMA 8158 |  |  |  |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8158 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | PV-SWEEP | FEMA 8158: FEMA sweeper rates not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-BROOM-RUNWAY | Paving | Broom / sweeper | Runway broom (high-speed) | Oshkosh H-Series (420 hp) | Net HP | 420 | hp | Oshkosh H-Series |  | 420 |  |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8565 | 119.23 | FEMA 2025 | 7.14 | 9.39 | 12.25 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 84.86 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Airfield specialty. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
PV-STRIPE-8440 | Paving | Line striper | Walk/ride striper | Walk-behind striper, single gun | Type | Walk-behind striper |  | Graco LineLazer |  |  |  |  | gas | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8440 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | PV-STRIPE-SMALL | FEMA 8440: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-STRIPE-8441 | Paving | Line striper | Walk/ride striper | Ride-on striper | Type | Ride-on striper |  | Graco LineLazer |  |  |  |  | gas | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8441 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | PV-STRIPE-SMALL | FEMA 8441: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-STRIPE-8442 | Paving | Line striper | Walk/ride striper | Ride-on striper, 2x25 gal | Type | Ride-on striper |  | Graco LineLazer |  |  |  |  | gas | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8442 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | PV-STRIPE-SMALL | FEMA 8442: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-STRIPE-TRUCK | Paving | Line striper | Truck-mounted | Truck-mounted RoadLazer | Type | truck |  | Graco RoadLazer (FEMA 8445) |  |  |  |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8445 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | PV-STRIPE-TRUCK | FEMA 8445: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
PV-STABILIZER-WR2400 | Paving | Soil stabilizer / reclaimer | Stabilizer/recycler | Wirtgen WR 2400 class | Model | WR 2400 |  | Wirtgen WR 2400 |  |  |  |  | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8636 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | PV-STABILIZE | FEMA 8636 mislabel fixed: the WR 2400 is a Wirtgen recycler/stabilizer, not a scraper. FEMA 8636: FEMA lists 8636 as 'Scraper, Wirtgen WR2400' - MISLABEL corrected to stabilizer/recycler; rate not captured. | Needs rate; FEMA label corrected (8636); Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
CN-MIXER-5CF | Concrete | Concrete/mortar mixer | Wheelbarrow | 5 cu ft | Drum | 5 | cu ft |  |  |  | 5 cu ft |  | gas | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8410 | 1.95 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | CN-MIX-SMALL | Gasoline unit: ex-fuel left blank because the notes give no 2025 gasoline basis and no gal/hr. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | Needs fuel gal/hr; Needs rate (rental)
CN-MIXER-12CF | Concrete | Concrete/mortar mixer | Trailer mortar mixer | 12 cu ft | Drum | 12 | cu ft |  |  |  | 12 cu ft |  | gas | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8411 | 8 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | CN-MIX-SMALL | Gasoline unit: ex-fuel left blank because the notes give no 2025 gasoline basis and no gal/hr. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | Needs fuel gal/hr; Needs rate (rental)
CN-MIXER-16CF | Concrete | Concrete/mortar mixer | Trailer mortar mixer | 16 cu ft | Drum | 16 | cu ft |  |  |  | 16 cu ft |  | gas | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8412 | 12.4 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | CN-MIX-SMALL | Gasoline unit: ex-fuel left blank because the notes give no 2025 gasoline basis and no gal/hr. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | Needs fuel gal/hr; Needs rate (rental)
CN-TRUCKMIX-11 | Concrete | Concrete mixer truck | Transit mixer | 11 CY | Drum | 11 | CY | Freightliner 114SD |  |  | 11 CY |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8414 | 82.26 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
CN-TRUCKMIX-13 | Concrete | Concrete mixer truck | Transit mixer | 13 CY | Drum | 13 | CY |  |  |  | 13 CY |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8673 | 255.58 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA: About 3x the 11 CY rate. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged: ~3x 11 CY rate; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
CN-PUMP-BOOM-38M | Concrete | Concrete pump | Truck-mounted boom | Boom pump 38 m | Vertical reach | 3 | m | Putzmeister M38-5 class |  |  |  |  | diesel | Pump operator - included in operated rate | hr (operated) | [5 empty] | operated | 185 | 3 | CPO | read Oct 2026 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | CN-PUMP-BOOM | Operated: includes operator; also $/yd3, travel hours, 8-12% fuel surcharge, washout $250-450 (CCE). Minimum 3-4 hr block ($600-1,600 min charge). Rent (operated, incl. operator): Ohio $185/hr job time + $4.00/yd3 + travel $125/hr. | Needs rate (owned); Needs fuel gal/hr
CN-PUMP-BOOM-46M | Concrete | Concrete pump | Truck-mounted boom | Boom pump 46 m | Vertical reach | 4 | m | 46 m class (M42-5 nearest named) |  |  |  |  | diesel | Pump operator - included in operated rate | hr (operated) | [5 empty] | operated | 225 | 3 | CPO | read Oct 2026 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | CN-PUMP-BOOM | Operated: includes operator; also $/yd3, travel hours, 8-12% fuel surcharge, washout $250-450 (CCE). Minimum 3-4 hr block ($600-1,600 min charge). Rent (operated, incl. operator): Ohio $225/hr + $4.00/yd3 + travel $130/hr + permit $210. | Needs rate (owned); Needs fuel gal/hr
CN-PUMP-LINE | Concrete | Concrete pump | Line/trailer | Line pump (trailer) | Type | line |  | Trailer/line pump |  |  |  |  | diesel | Pump operator - included in operated rate | hr (operated) | [5 empty] | operated | 140 | 3 | CPO | read Oct 2026 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | CN-PUMP-LINE | Operated: includes operator; also $/yd3, travel hours, 8-12% fuel surcharge, washout $250-450 (CCE). Minimum 3-4 hr block ($600-1,600 min charge). Rent (operated, incl. operator): Ohio $140/hr port-to-port. National planning range $125-225/hr (CCE). | Needs rate (owned); Needs fuel gal/hr
CN-PUMP-BOOM-63M | Concrete | Concrete pump | Truck-mounted boom | Boom pump 47-63 m+ | Vertical reach | 63 | m | Putzmeister 63 m class |  |  |  |  | diesel | Pump operator - included in operated rate | hr (operated) | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | CN-PUMP-BOOM | No public 2025-2026 rate for 47/52/58/63 m. National boom range $200-350+/hr (CCE) is too wide to assign a class value. | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
CN-TELEBELT | Concrete | Concrete conveyor | Truck-mounted telescopic belt | 110 ft Telebelt | Reach | 110 | ft | Putzmeister Telebelt |  |  |  |  | diesel | Operator - included in operated rate | hr (operated) | [5 empty] | operated | 185 |  | CPO | read Oct 2026 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | CN-PLACE-BELT | Rent (operated, incl. operator): Ohio $185/hr + $3.50/yd3 or $2.00/ton + travel $110/hr. | Needs rate (owned); Needs fuel gal/hr
CN-VIB-FLEX | Concrete | Concrete vibrator | Flex-shaft | 2.5 in head, 16 ft shaft | Head | 2.5 | in | FEMA 8421 |  |  |  |  | gas | Cement Mason / Laborer (per WD) | day/wk/4wk | 60 | 180 | 522 |  |  | bare |  |  | W25 | 2025 | C | 8421 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | CN-PLACE-SLAB | Rent: Wheeler ~$60/day; week/4-week derived. Rent_week = day x Settings week/day multiplier (3.0); Rent_4wk = week x 4wk/week multiplier (2.9) - method C. FEMA 8421: Rate not captured. | Needs rate (owned; FEMA code exists); Needs fuel gal/hr
CN-VIB-MIH | Concrete | Concrete vibrator | Motor-in-head | Motor-in-head vibrator | Type | motor-in-head |  | FEMA 8761 |  |  |  |  | electric | Cement Mason / Laborer (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8761 |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | CN-PLACE-SLAB | FEMA 8761: Code listed in taxonomy; rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
CN-TROWEL-WB | Concrete | Power trowel | Walk-behind | 36-46 in walk-behind | Ring diameter | 46 | in | FEMA 8290 (48 in walk-behind) |  |  |  |  | gas | Cement Mason / Laborer (per WD) | day/wk/4wk | 101 | 312 | 861 | 525 | 1197 | bare |  |  | W25;N25 | 2025-2026 | A | 8290 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | CN-FINISH-WB | Rent: Median (=mean) of 2 sources: W 46 in 142/413/1197; N 36/46 avg 60/210/525. Wide spread. FEMA 8290: Rate not captured. | Needs rate (owned; FEMA code exists); Needs fuel gal/hr
CN-TROWEL-RIDE-72 | Concrete | Power trowel | Ride-on | Ride-on 72 in | Overall diameter | 72 | in | [5 empty] | gas | Cement Mason / Laborer (per WD) | day/wk/4wk | 225 | 785 | 1965 |  |  | bare |  |  | N25 | Jan 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | CN-FINISH-RIDE | Rent: Nu-Way only. | Needs rate (owned); Needs fuel gal/hr
CN-TROWEL-RIDE-91 | Concrete | Power trowel | Ride-on | Ride-on 91 in | Overall diameter | 91 | in | [5 empty] | gas | Cement Mason / Laborer (per WD) | day/wk/4wk | 245 | 855 | 2135 |  |  | bare |  |  | N25 | Jan 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | CN-FINISH-RIDE | Rent: Nu-Way only. | Needs rate (owned); Needs fuel gal/hr
CN-TROWEL-RIDE-98 | Concrete | Power trowel | Ride-on | Ride-on 97.5 in | Overall diameter | 97.5 | in | [5 empty] | gas | Cement Mason / Laborer (per WD) | day/wk/4wk | 425 | 1495 | 3750 |  |  | bare |  |  | N25 | Jan 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | CN-FINISH-RIDE | Rent: Nu-Way only. | Needs rate (owned); Needs fuel gal/hr
CN-SCREED-ROLLER | Concrete | Screed | Roller screed | Roller screed | Type | roller | [6 empty] | gas | Cement Mason / Laborer (per WD) | day/wk/4wk | 100 | 350 | 875 |  |  | bare |  |  | N25 | Jan 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | CN-PLACE-SLAB | Rent: Nu-Way only. | Needs rate (owned); Needs fuel gal/hr
CN-SCREED-HAND | Concrete | Screed | Hand-held power screed | Hand-held power screed | Type | hand-held | [6 empty] | gas | Cement Mason / Laborer (per WD) | day/wk/4wk | 75 | 250 | 600 |  |  | bare |  |  | N25 | Jan 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | CN-PLACE-SLAB | Rent: Nu-Way only. | Needs rate (owned); Needs fuel gal/hr
CN-SCREED-VIB-10 | Concrete | Screed | Vibratory | 10 ft vibratory screed | Length | 10 | ft | [5 empty] | gas | Cement Mason / Laborer (per WD) | day/wk/4wk | 128 | 371 | 1076 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | CN-PLACE-SLAB | Rent: Wheeler only. | Needs rate (owned); Needs fuel gal/hr
CN-SCREED-TRUSS-20 | Concrete | Screed | Gas truss screed w/ winches | 20 ft base truss screed | Length | 20 | ft | [5 empty] | gas | Cement Mason / Laborer (per WD) | wk/4wk |  | 520 | 1260 |  |  | bare |  |  | N25 | Jan 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | CN-PLACE-SLAB | Rent: Nu-Way only: $520/wk, $1,260/mo, 1-week minimum; +$5.75/day per extra foot. No day rate. | Needs rate (owned); Needs fuel gal/hr
CN-LASER-SCREED | Concrete | Laser screed | Ride-on/boom | Laser screed | Type | boom |  | Somero |  |  |  |  | diesel | Cement Mason / Laborer (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | CN-PLACE-LASER | No rate or SF/day source (marketing only). | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
CN-SAW-WB-14 | Concrete | Concrete saw | Walk-behind (gas) | 14-20 in blade | Blade | 14 | in | 13-20 hp walk-behind; FEMA 8510 (14 in) |  |  |  |  | gas | Laborer (per WD group) | day/wk/4wk | 109 | 343 | 945 | 660 | 1229 | bare |  |  | W25;N25 | 2025-2026 | A | 8510 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | CN-SAWCUT | Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median (=mean) of 2 sources: W 14 in 146/424/1229; N 13/20 hp avg 72/262/660. FEMA 8510: Rate not captured. | Needs rate (owned; FEMA code exists); Needs fuel gal/hr
CN-SAW-26 | Concrete | Concrete saw | Walk-behind diesel | 26 in blade (35/48 hp) | Blade | 26 | in | FEMA 8511 (14-42 in diesel) |  | 48 |  |  | diesel | Laborer (per WD group) | day/wk/4wk | 125 | 440 | 1100 |  |  | bare |  |  | N25 | Jan 2025 | B | 8511 |  |  | 0.82 | 1.07 | 1.4 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | CN-SAWCUT | Rent: Nu-Way only. FEMA 8511: Rate not captured. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate (owned; FEMA code exists)
CN-SAW-36 | Concrete | Concrete saw | Walk-behind diesel | 36 in blade (66/70 hp) | Blade | 36 | in |  |  | 70 |  |  | diesel | Laborer (per WD group) | day/wk/4wk | 165 | 580 | 1450 |  |  | bare |  |  | N25 | Jan 2025 | B |  |  |  | 1.19 | 1.56 | 2.04 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | CN-SAWCUT | Rent: Nu-Way only. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate (owned)
CN-SAW-DEEP-60 | Concrete | Concrete saw | Deep-cut | 60 in blade | Blade | 60 | in | FEMA 8512 |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8512 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | CN-SAWCUT | FEMA 8512: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
CN-SAW-EARLY | Concrete | Concrete saw | Early-entry | Early-entry 13.5 in | Blade | 13.5 | in | [5 empty] | gas | Laborer (per WD group) | day/wk/4wk | 167 | 557 | 1452 | 908 | 1995 | bare |  |  | N25;W25 | 2025-2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | CN-SAWCUT | Rent: Mean of 2 sources: N early-entry 225/800/1995; W green-concrete saw 108/313/908 (half-up; day corrected from 165 to 167). | Needs rate (owned); Needs fuel gal/hr
CN-BUGGY | Concrete | Power buggy | Walk/ride buggy | Power buggy | Type | buggy | [6 empty] | gas | Laborer (per WD group) | day/wk/4wk | 149 | 447 | 1296 |  |  | bare |  |  | W25 | 2025 | C | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | CN-PLACE-BUGGY | Rent: Day = midpoint of Wheeler $114-184/day; week/4-week derived. Rent_week = day x Settings week/day multiplier (3.0); Rent_4wk = week x 4wk/week multiplier (2.9) - method C. | Needs rate (owned); Needs fuel gal/hr
CN-BUGGY-TRACK-16 | Concrete | Power buggy | Tracked | Tracked mud buggy 16 cf | Capacity | 16 | cu ft | [5 empty] | gas | Laborer (per WD group) | day/wk/4wk | 200 | 800 | 2400 |  |  | bare |  |  | R25 | Spring 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | CN-PLACE-BUGGY | Rent: RTL only. | Needs rate (owned); Needs fuel gal/hr
CN-SLIPFORM-PAVER | Concrete | Slipform paver | Concrete pavement | Slipform paver (by width) | Paving width |  | ft | [5 empty] | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy |  |  | Y | 1913 | 1913 | CN-SLIPFORM-PAVE | Caltrans CONSF width bands garbled in extraction. | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
CN-CURB-MACHINE | Concrete | Curb machine | Curb/gutter slipform | Curb & gutter slipform | Max width |  | ft | [5 empty] | diesel | Operating Engineer - paving group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | CN-CURB | Caltrans CRBEX (width bands not extracted). | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
CN-LASER-LEVEL | Concrete | Laser level | Rotary laser | Rotary laser level | Type | laser | [6 empty] | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 79 | 237 | 687 |  |  | bare |  |  | W25 | 2025 | C |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | Rent: Wheeler $79/day; week/4-week derived. Rent_week = day x Settings week/day multiplier (3.0); Rent_4wk = week x 4wk/week multiplier (2.9) - method C. | Needs rate (owned)
AW-SC-EL-10 | Aerial work platforms | Scissor lift, electric slab | Electric slab (Group A, Type 3) | 10 ft platform | Platform height | 10 | ft | Lightweight 10 ft (COSTARS class) |  |  |  | 10 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 200 | 442 | 514 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. FEMA has no scissor codes; no owned proxy applied. Rent: Single source (COSTARS 200/442/514). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Non-monotonic vs AW-SC-EL-13 - source data; Needs rate (owned)
AW-LLA-5 | Aerial work platforms | Low-level access lift | Low-level access (Group A) | Low-level access 1-5 ft | Platform height (max of bin) | 5 | ft | Sunbelt LLA bins |  |  |  | 5 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | Class from Sunbelt electric scissor size bins [SUNBELT-LLA]; no rates in notes. | Needs rate; Needs rate (rental); Needs rate (owned)
AW-LLA-10 | Aerial work platforms | Low-level access lift | Low-level access (Group A) | Low-level access 6-10 ft | Platform height (max of bin) | 10 | ft | Sunbelt LLA bins |  |  |  | 10 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | Class from Sunbelt electric scissor size bins [SUNBELT-LLA]; no rates in notes. | Needs rate; Needs rate (rental); Needs rate (owned)
AW-LLA-15 | Aerial work platforms | Low-level access lift | Low-level access (Group A) | Low-level access 11-15 ft | Platform height (max of bin) | 15 | ft | Sunbelt LLA bins |  |  |  | 15 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | Class from Sunbelt electric scissor size bins [SUNBELT-LLA]; no rates in notes. | Needs rate; Needs rate (rental); Needs rate (owned)
AW-SC-EL-13 | Aerial work platforms | Scissor lift, electric slab | Electric slab (Group A, Type 3) | 13 ft platform (30.5 in wide) | Platform height | 13 | ft | Genie GS-1330m (18'10" working); COSTARS 14-15' lightweight |  |  | 500 lb platform | 13 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 201 | 342 | 494 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 2.54 | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. FEMA has no scissor codes; no owned proxy applied. Mapped to COSTARS 14-15 ft lightweight class. Rent: Single source (COSTARS 201/342/494). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-SC-EL-15 | Aerial work platforms | Scissor lift, electric slab | Electric slab (Group A, Type 3) | 15 ft platform (30 in wide) | Platform height | 15 | ft | Genie GS-1530 (21 ft working) |  |  | 600 lb platform | 15 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 201 | 342 | 494 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 2.5 | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. FEMA has no scissor codes; no owned proxy applied. Same COSTARS 14-15 ft class as AW-SC-EL-13. Rent: Single source (COSTARS 201/342/494). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Non-monotonic vs AW-SC-EL-19 - source data; Needs rate (owned)
AW-SC-EL-19 | Aerial work platforms | Scissor lift, electric slab | Electric slab (Group A, Type 3) | 19 ft platform (30 in wide) | Platform height | 19 | ft | Genie GS-1930 / GS-1932 (25 ft working) |  |  | 500 lb platform | 19 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 134 | 324 | 584 | 500 | 850 | bare |  |  | COSTARS;BIGR-SC;DOZR-SC;SCAFEX | mixed: 3/2023-3/2024, Dec 2022, Mar 2026, Sep 2026 | A |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 2.5 | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. FEMA has no scissor codes; no owned proxy applied. Notes cross-check suggested ~$600-650/4wk (mean $629). Rent: Median of 4 source points (COSTARS 174/341/500; BIGR 142/306/592; DOZRS 125/287.5/575; SCAF 125/375/850). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). BigRentz = 23-city mean, Dec 2022 data, 'monthly' column. | Needs rate (owned)
AW-SC-EL-20 | Aerial work platforms | Scissor lift, electric slab | Electric slab (Group A, Type 3) | 20 ft platform (32 in wide) | Platform height | 20 | ft | Genie GS-2032 (800 lb) / GS-2046 (46 in, 1,200 lb) |  |  | 800 lb platform | 20 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 194 | 381 | 630 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 2.67 | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. FEMA has no scissor codes; no owned proxy applied. Rent: Single source (COSTARS 194/381/630). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-SC-EL-26N | Aerial work platforms | Scissor lift, electric slab | Electric slab (Group A, Type 3) | 26 ft platform (32 in wide) | Platform height | 26 | ft | Genie GS-2632 (32 ft working) |  |  | 500 lb platform | 26 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 190 | 467 | 878 | 795 | 1100 | bare |  |  | COSTARS;BIGR-SC;DOZR-SC;SCAFEX | mixed: 3/2023-3/2024, Dec 2022, Mar 2026, Sep 2026 | A |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 2.67 | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. FEMA has no scissor codes; no owned proxy applied. Narrow (fits standard doors). Rent: Median of 4 source points (COSTARS 238/459/795; BIGR 179/390/806; DOZRS 200/475/950; SCAF 175/475/1100). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). BigRentz = 23-city mean, Dec 2022 data, 'monthly' column. | Needs rate (owned)
AW-SC-EL-26W | Aerial work platforms | Scissor lift, electric slab | Electric slab (Group A, Type 3) | 26 ft platform (46 in wide) | Platform height | 26 | ft | Genie GS-2646 |  |  | 1000 lb platform | 26 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 252 | 463 | 836 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 3.83 | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. FEMA has no scissor codes; no owned proxy applied. Wide 46 in deck. Rent: Single source (COSTARS 252/463/836). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-SC-EL-32N | Aerial work platforms | Scissor lift, electric slab | Electric slab (Group A, Type 3) | 32 ft platform (32 in wide) | Platform height | 32 | ft | Genie GS-3232 (37'8" working) |  |  | 500 lb platform | 32 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 250 | 621 | 1215 | 1175 | 1500 | bare |  |  | COSTARS;DOZR-SC;SCAFEX | mixed: 3/2023-3/2024, Mar 2026, Sep 2026 | A |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 2.67 | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. FEMA has no scissor codes; no owned proxy applied. BigRentz 32 ft given only as city ranges (not used). Rent: Median of 3 source points (COSTARS 315/621/1215; DOZRS 250/587.5/1175; SCAF 250/675/1500). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-SC-EL-32W | Aerial work platforms | Scissor lift, electric slab | Electric slab (Group A, Type 3) | 32 ft platform (46 in wide) | Platform height | 32 | ft | Genie GS-3246 |  |  | 700 lb platform | 32 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 294 | 566 | 1175 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 3.83 | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. FEMA has no scissor codes; no owned proxy applied. COSTARS 30-33 ft (non-narrow) class. Rent: Single source (COSTARS 294/566/1175). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-SC-EL-40 | Aerial work platforms | Scissor lift, electric slab | Electric slab (Group A, Type 3) | 40 ft platform (46 in wide) | Platform height | 40 | ft | Genie GS-4046 (45'2" working) |  |  | 770 lb platform | 40 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 330 | 764 | 1596 | 1450 | 1850 | bare |  |  | COSTARS;BIGR-SC;DOZR-SC;SCAFEX | mixed: 3/2023-3/2024, Dec 2022, Mar 2026, Sep 2026 | A |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 3.83 | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. FEMA has no scissor codes; no owned proxy applied. COSTARS calls this class 40-44 ft narrow; BigRentz MSP/SLC outliers $2,733/mo excluded by using the mean as published. Rent: Median of 4 source points (COSTARS 334/753/1477; BIGR 347/774/1715; DOZRS 325/737.5/1450; SCAF 300/850/1850). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). BigRentz = 23-city mean, Dec 2022 data, 'monthly' column. | Needs rate (owned)
AW-SC-EL-46 | Aerial work platforms | Scissor lift, electric slab | Electric slab (Group A, Type 3) | 46 ft platform (55 in wide) | Platform height | 46 | ft | Genie GS-4655 (52 ft working) |  |  | 770 lb platform | 46 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 371 | 857 | 1942 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 4.58 | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. FEMA has no scissor codes; no owned proxy applied. COSTARS 45-49 ft class. Rent: Single source (COSTARS 371/857/1942). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-SC-RT-26 | Aerial work platforms | Scissor lift, rough terrain | Rough terrain (Group A, Type 3) | 26 ft platform (69 in wide) | Platform height | 26 | ft | Genie GS-2669 DC/RT |  |  | 1500 lb platform | 26 | dual | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 310 | 808 | 1839 | 1177 | 2500 | bare |  |  | COSTARS;SCAFEX | mixed: 3/2023-3/2024, Sep 2026 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 5.75 | N | 200 | 200 | LF-AWP-DUR | DC = electric drive RT, RT = engine. FEMA has no scissor codes. ScaffoldExchange 26-33 ft RT range applied to 26 and 33 ft rows. Large spread between sources. Rent: Median of 2 source points (COSTARS 295/615/1177; SCAF 325/1000/2500). Graded B: ScaffoldExchange cites Sunbelt/URI/BigRentz, so it is not independent of COSTARS/BigRentz. DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-SC-RT-33 | Aerial work platforms | Scissor lift, rough terrain | Rough terrain (Group A, Type 3) | 33 ft platform (69 in wide) | Platform height | 33 | ft | Genie GS-3369 DC/RT |  |  | 1000 lb platform | 33 | dual | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 325 | 851 | 1931 | 1362 | 2500 | bare |  |  | COSTARS;SCAFEX | mixed: 3/2023-3/2024, Sep 2026 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 5.75 | N | 200 | 200 | LF-AWP-DUR | DC = electric drive RT, RT = engine. FEMA has no scissor codes. COSTARS 30-35 ft RT. Rent: Median of 2 source points (COSTARS 324/702/1362; SCAF 325/1000/2500). Graded B: ScaffoldExchange cites Sunbelt/URI/BigRentz, so it is not independent of COSTARS/BigRentz. DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-SC-RT-33BD | Aerial work platforms | Scissor lift, rough terrain | Rough terrain (Group A, Type 3) | 33 ft platform (92 in wide) | Platform height | 33 | ft | Genie GS-3384 / GS-3390 big deck (2,500 lb) |  |  | 2500 lb platform | 33 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 7.67 | N | 200 | 200 | LF-AWP-DUR | DC = electric drive RT, RT = engine. FEMA has no scissor codes. No separate rate for big-deck 2,500 lb units. | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
AW-SC-RT-40 | Aerial work platforms | Scissor lift, rough terrain | Rough terrain (Group A, Type 3) | 40 ft platform (69 in wide) | Platform height | 40 | ft | Genie GS-4069 DC/RT |  |  | 800 lb platform | 40 | dual | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 462 | 1061 | 2175 | 1850 | 2500 | bare |  |  | COSTARS;DOZR-SC | mixed: 3/2023-3/2024, Mar 2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 5.75 | N | 200 | 200 | LF-AWP-DUR | DC = electric drive RT, RT = engine. FEMA has no scissor codes. DOZR 40-60 ft RT range midpoint. Rent: Median of 2 source points (COSTARS 373/872/1850; DOZRS 550/1250/2500). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Non-monotonic vs AW-SC-RT-40OR - source data; Needs rate (owned)
AW-SC-RT-40OR | Aerial work platforms | Scissor lift, rough terrain | Rough terrain (Group A, Type 3) | 40 ft platform (92 in wide) | Platform height | 40 | ft | 40 ft RT with outriggers |  |  |  | 40 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 416 | 886 | 1950 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 7.67 | N | 200 | 200 | LF-AWP-DUR | DC = electric drive RT, RT = engine. FEMA has no scissor codes. Rent: Single source (COSTARS 416/886/1950). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-SC-RT-43 | Aerial work platforms | Scissor lift, rough terrain | Rough terrain (Group A, Type 3) | 43 ft platform (92 in wide) | Platform height | 43 | ft | Genie GS-4390 |  |  | 1500 lb platform | 43 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 525 | 1375 | 3125 | 2500 | 3750 | bare |  |  | SCAFEX;DOZR-SC | mixed: Mar 2026, Sep 2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 7.67 | N | 200 | 200 | LF-AWP-DUR | DC = electric drive RT, RT = engine. FEMA has no scissor codes. Rent: Median of 2 source points (SCAF 500/1500/3750; DOZRS 550/1250/2500). DOZR/ScaffoldExchange values are range midpoints. | Needs fuel gal/hr; Non-monotonic vs AW-SC-RT-50 - source data; Needs rate (owned)
AW-SC-RT-50 | Aerial work platforms | Scissor lift, rough terrain | Rough terrain (Group A, Type 3) | 50 ft platform (92 in wide) | Platform height | 50 | ft | Genie GS-5390 (53 ft); 50 ft RT w/ outriggers |  |  | 1500 lb platform | 50 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 523 | 1250 | 2500 | 2255 | 3750 | bare |  |  | COSTARS;SCAFEX;DOZR-SC | mixed: 3/2023-3/2024, Mar 2026, Sep 2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  | 7.67 | N | 200 | 200 | LF-AWP-DUR | DC = electric drive RT, RT = engine. FEMA has no scissor codes. Covers 50-53 ft RT. Rent: Median of 3 source points (COSTARS 523/1073/2255; SCAF 500/1500/3750; DOZRS 550/1250/2500). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-AB-EL-20 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 20 ft electric articulating | Platform height | 20 | ft |  |  |  |  | 20 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | Class listed only on the 2018 Kansas rate list ($146.11/$393.99/$1,087.27), excluded as outdated per notes. [KS18] | Needs rate; Needs rate (rental); Needs rate (owned)
AW-AB-EL-30 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 30 ft electric narrow (jib/rotajib) | Platform height | 30 | ft | jib/rotajib |  |  | 500 lb std; 1,000 lb restricted on HC3/XC models | 30 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 300 | 850 | 2076 | 1850 | 2200 | bare |  |  | COSTARS;DOZR-BM;SCAFEX | mixed: 3/2023-3/2024, Mar 2026, Sep 2026 | A |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. COSTARS jib + rotajib averaged within source (384/983/2191; 413/927/1961). Rent: Median of 3 source points (COSTARS 398.5/955/2076; DOZRB 300/825/1850; SCAF 300/850/2200). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-AB-EL-34 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 34-35 ft electric | Platform height | 34 | ft |  |  |  | 500 lb std; 1,000 lb restricted on HC3/XC models | 34 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 300 | 841 | 2200 | 1850 | 2777 | bare |  |  | COSTARS;DOZR-BM;SCAFEX | mixed: 3/2023-3/2024, Mar 2026, Sep 2026 | A |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. Rent: Median of 3 source points (COSTARS 472/841/2777; DOZRB 300/825/1850; SCAF 300/850/2200). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-AB-RT-34 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 34 ft engine (JLG 340AJ, 500 lb) | Platform height | 34 | ft | JLG 340AJ, 500 lb |  | 25 | 500 lb std; 1,000 lb restricted on HC3/XC models | 34 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 357 | 931 | 1973 | 1850 | 2096 | bare |  |  | COSTARS;DOZR-BM | mixed: 3/2023-3/2024, Mar 2026 | A | 8490 | 38.27 | FEMA 2025 | 0.43 | 0.56 | 0.73 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 36.22 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | HP from FEMA extraction (unlabeled column, verify). Working height = platform + ~6 ft. Rent: Median of 2 source points (COSTARS 413/1036/2096; DOZRB 300/825/1850). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). FEMA: JLG 340AJ 33 ft, 25 hp as extracted. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
AW-AB-EL-40 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 40 ft electric narrow (Genie Z-40/23N) | Platform height | 40 | ft | Genie Z-40/23N |  |  | 500 lb std; 1,000 lb restricted on HC3/XC models | 40 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 402 | 943 | 2111 | 1850 | 2172 | bare |  |  | COSTARS;BIGR-BM;DOZR-BM | mixed: 3/2023-3/2024, Dec 2022, Mar 2026 | A |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. COSTARS narrow + narrow jib averaged within source. BigRentz boom tables do not split articulating vs telescopic. Rent: Median of 3 source points (COSTARS 425.5/1049/2172; BIGRB 402/943/2111; DOZRB 300/825/1850). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). BigRentz = 23-city mean, Dec 2022 data, 'monthly' column. | Needs rate (owned)
AW-AB-EL-45 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 45 ft electric jib (Genie Z-45 DC) | Platform height | 45 | ft | Genie Z-45 DC |  |  | 500 lb std; 1,000 lb restricted on HC3/XC models | 45 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 419 | 1022 | 2349 | 2159 | 2900 | bare |  |  | COSTARS;BIGR-BM;SCAFEX;DOZR-BM | mixed: 3/2023-3/2024, Dec 2022, Mar 2026, Sep 2026 | A |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. Rent: Median of 4 source points (COSTARS 433/1037/2159; BIGRB 404/1007/2198; SCAF 375/1000/2500; DOZRB 525/1350/2900). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). BigRentz = 23-city mean, Dec 2022 data, 'monthly' column. | Needs rate (owned)
AW-AB-RT-45 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 45 ft engine w/ jib (Genie Z-45/25J RT; JLG 450AJ) | Platform height | 45 | ft | Genie Z-45/25J RT; JLG 450AJ |  | 60 | 500 lb std; 1,000 lb restricted on HC3/XC models | 45 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 430 | 1028 | 2349 | 2062 | 2900 | bare |  |  | COSTARS;BIGR-BM;SCAFEX;DOZR-BM | mixed: 3/2023-3/2024, Dec 2022, Mar 2026, Sep 2026 | A | 8491 | 48.28 | FEMA 2025 | 1.02 | 1.34 | 1.75 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 43.38 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | HP from FEMA extraction (unlabeled column, verify). Working height = platform + ~6 ft. Rent: Median of 4 source points (COSTARS 455/1048/2062; BIGRB 404/1007/2198; SCAF 375/1000/2500; DOZRB 525/1350/2900). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). BigRentz = 23-city mean, Dec 2022 data, 'monthly' column. FEMA: JLG 450AJ HC3, 60 hp. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
AW-AB-EL-60 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 60 ft electric/hybrid jib (Genie Z-60 DC/FE) | Platform height | 60 | ft | Genie Z-60 DC/FE |  |  | 500 lb std; 1,000 lb restricted on HC3/XC models | 60 | hybrid | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 518 | 1373 | 2751 | 2602 | 2900 | bare |  |  | COSTARS;DOZR-BM | mixed: 3/2023-3/2024, Mar 2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | Working height = platform + ~6 ft. Rent: Median of 2 source points (COSTARS 511/1395/2602; DOZRB 525/1350/2900). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-AB-RT-60 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 60 ft engine w/ jib (Genie Z-62/40; JLG 600AJ) | Platform height | 60 | ft | Genie Z-62/40; JLG 600AJ |  | 84 | 500 lb std; 1,000 lb restricted on HC3/XC models | 60 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 563 | 1370 | 2766 | 2632 | 2900 | bare |  |  | COSTARS;DOZR-BM | mixed: 3/2023-3/2024, Mar 2026 | A | 8492 | 59.1 | FEMA 2025 | 1.43 | 1.88 | 2.45 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 52.22 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | HP from FEMA extraction (unlabeled column, verify). Working height = platform + ~6 ft. Rent: Median of 2 source points (COSTARS 601/1390/2632; DOZRB 525/1350/2900). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). FEMA: JLG 600AJ HC3, 84 hp. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
AW-AB-RT-80 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 80 ft w/ jib (Genie Z-80/60; JLG 800AJ) | Platform height | 80 | ft | Genie Z-80/60; JLG 800AJ |  | 84 | 500 lb std; 1,000 lb restricted on HC3/XC models | 80 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 961 | 2206 | 4262 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B | 8493 | 65.19 | FEMA 2025 | 1.43 | 1.88 | 2.45 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 58.31 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-AWP-DUR | HP from FEMA extraction (unlabeled column, verify). Working height = platform + ~6 ft. Rent: Single source (COSTARS 961/2206/4262). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). FEMA: JLG 800AJ HC3, 84 hp. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
AW-AB-RT-86 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 86 ft articulating | Platform height | 86 | ft |  |  |  |  | 86 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-AWP-DUR | Known gap class: no specs or rates in notes. | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
AW-AB-RT-125 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 125 ft (JLG 1250AJP) | Platform height | 125 | ft | JLG 1250AJP |  | 75 | 500 lb std; 1,000 lb restricted on HC3/XC models | 125 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8494 | 68.1 | FEMA 2025 | 1.28 | 1.68 | 2.19 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 61.95 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-AWP-DUR | HP from FEMA extraction (unlabeled column, verify). Working height = platform + ~6 ft. Rental: only a 2018 Kansas list (excluded as outdated). FEMA: 125 ft rate barely above 80 ft (65.19) and far below 150 ft (104.55). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
AW-AB-RT-135 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 135 ft (Genie ZX-135/70) | Platform height | 135 | ft | Genie ZX-135/70 |  |  | 500 lb std; 1,000 lb restricted on HC3/XC models | 135 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 2032 | 4780 | 11755 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-AWP-DUR | Working height = platform + ~6 ft. DOZR 120-180 ft band not used (60 ft wide band; not a class source). Rent: Single source (COSTARS 2032/4780/11755). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-AB-RT-150 | Aerial work platforms | Boom lift, articulating | Articulating (Group B, Type 3) | 150 ft w/ jib (JLG 1500AJP) | Platform height | 150 | ft | JLG 1500AJP |  | 100 | 500 lb std; 1,000 lb restricted on HC3/XC models | 150 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 4598 | 11489 | 28435 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B | 8495 | 104.55 | FEMA 2025 | 1.7 | 2.24 | 2.92 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 96.35 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-AWP-DUR | HP from FEMA extraction (unlabeled column, verify). Working height = platform + ~6 ft. COSTARS single source (notes). DOZR 120-180 ft band not used as a class source. Rent: Single source (COSTARS 4598/11489/28435). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). FEMA: JLG 1500AJP, 100 hp. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
AW-TB-40 | Aerial work platforms | Boom lift, telescopic (straight) | Telescopic (Group B, Type 3) | 40 ft w/ jib (JLG 400S/460SJ) | Platform height | 40 | ft | JLG 400S/460SJ |  |  | 500-600 lb unrestricted; 1,000 lb restricted options | 40 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 362 | 905 | 1930 | 1850 | 2009 | bare |  |  | COSTARS;DOZR-BM | mixed: 3/2023-3/2024, Mar 2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | No FEMA telescopic codes (no owned proxy applied). DOZR: articulating ~10-20% dearer than telescopic at same height. Rent: Median of 2 source points (COSTARS 424/985/2009; DOZRB 300/825/1850). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-TB-60 | Aerial work platforms | Boom lift, telescopic (straight) | Telescopic (Group B, Type 3) | 60 ft w/ jib (JLG 600S: 59'8", 22,900 lb) | Platform height | 60 | ft | JLG 600S: 59'8", 22,900 lb | 22900 |  | 500-600 lb unrestricted; 1,000 lb restricted options | 60 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 525 | 1350 | 2900 | 2447 | 3500 | bare |  |  | COSTARS;SCAFEX;DOZR-BM | mixed: 3/2023-3/2024, Mar 2026, Sep 2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier | 22900 |  | N | 200 | 200 | LF-AWP-DUR | No FEMA telescopic codes (no owned proxy applied). DOZR: articulating ~10-20% dearer than telescopic at same height. JLG 600S 600 lb unrestricted / 1,000 lb restricted, 50'2" outreach. Rent: Median of 3 source points (COSTARS 558/1277/2447; SCAF 500/1350/3500; DOZRB 525/1350/2900). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Non-monotonic vs AW-TB-60E - source data; Needs rate (owned)
AW-TB-60E | Aerial work platforms | Boom lift, telescopic (straight) | Telescopic (Group B, Type 3) | 60 ft electric | Platform height | 60 | ft |  |  |  | 500-600 lb unrestricted; 1,000 lb restricted options | 60 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 666 | 1568 | 2541 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | No FEMA telescopic codes (no owned proxy applied). DOZR: articulating ~10-20% dearer than telescopic at same height. Rent: Single source (COSTARS 666/1568/2541). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-TB-66 | Aerial work platforms | Boom lift, telescopic (straight) | Telescopic (Group B, Type 3) | 66 ft (JLG 660SJ: 65'8", 25,341 lb) | Platform height | 66 | ft | JLG 660SJ: 65'8", 25,341 lb | 25341 |  | 500-600 lb unrestricted; 1,000 lb restricted options | 66 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier | 25341 |  | N | 200 | 200 | LF-AWP-DUR | No FEMA telescopic codes (no owned proxy applied). DOZR: articulating ~10-20% dearer than telescopic at same height. No 66 ft specific rate (gap); 60-65 ft ScaffoldExchange band not reused. | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
AW-TB-80 | Aerial work platforms | Boom lift, telescopic (straight) | Telescopic (Group B, Type 3) | 80 ft w/ jib (JLG 800S class) | Platform height | 80 | ft | JLG 800S class |  |  | 500-600 lb unrestricted; 1,000 lb restricted options | 80 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 821 | 2129 | 4820 | 4139 | 5500 | bare |  |  | COSTARS;SCAFEX | mixed: 3/2023-3/2024, Sep 2026 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-AWP-DUR | No FEMA telescopic codes (no owned proxy applied). DOZR: articulating ~10-20% dearer than telescopic at same height. Rent: Median of 2 source points (COSTARS 892/2108/4139; SCAF 750/2150/5500). Graded B: ScaffoldExchange cites Sunbelt/URI/BigRentz, so it is not independent of COSTARS/BigRentz. DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-TB-85 | Aerial work platforms | Boom lift, telescopic (straight) | Telescopic (Group B, Type 3) | 85-86 ft | Platform height | 85 | ft |  |  |  | 500-600 lb unrestricted; 1,000 lb restricted options | 85 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-AWP-DUR | No FEMA telescopic codes (no owned proxy applied). DOZR: articulating ~10-20% dearer than telescopic at same height. No 85/86 ft specific rate (gap). | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
AW-TB-120 | Aerial work platforms | Boom lift, telescopic (straight) | Telescopic (Group B, Type 3) | 120 ft w/ jib (JLG 1200SJP) | Platform height | 120 | ft | JLG 1200SJP |  |  | 500-600 lb unrestricted; 1,000 lb restricted options | 120 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 1608 | 4673 | 10143 | 10000 | 10285 | bare |  |  | COSTARS;SCAFEX | mixed: 3/2023-3/2024, Sep 2026 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-AWP-DUR | No FEMA telescopic codes (no owned proxy applied). DOZR: articulating ~10-20% dearer than telescopic at same height. Rent: Median of 2 source points (COSTARS 1966/5596/10285; SCAF 1250/3750/10000). Graded B: ScaffoldExchange cites Sunbelt/URI/BigRentz, so it is not independent of COSTARS/BigRentz. DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-TB-125 | Aerial work platforms | Boom lift, telescopic (straight) | Telescopic (Group B, Type 3) | 125 ft telescopic | Platform height | 125 | ft |  |  |  | 500-600 lb unrestricted; 1,000 lb restricted options | 125 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-AWP-DUR | No FEMA telescopic codes (no owned proxy applied). DOZR: articulating ~10-20% dearer than telescopic at same height. No separate 125 ft telescopic rate (gap). | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
AW-TB-135 | Aerial work platforms | Boom lift, telescopic (straight) | Telescopic (Group B, Type 3) | 135 ft (JLG 1350SJP) | Platform height | 135 | ft | JLG 1350SJP |  |  | 500-600 lb unrestricted; 1,000 lb restricted options | 135 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 1250 | 3750 | 10000 |  |  | bare |  |  | SCAFEX | Sep 2026 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-AWP-DUR | No FEMA telescopic codes (no owned proxy applied). DOZR: articulating ~10-20% dearer than telescopic at same height. 2018 Kansas 135 ft straight excluded (outdated). DOZR 120-180 ft band not used. Rent: Single source (SCAF 1250/3750/10000). DOZR/ScaffoldExchange values are range midpoints. | Needs fuel gal/hr; Needs rate (owned)
AW-TB-150 | Aerial work platforms | Boom lift, telescopic (straight) | Telescopic (Group B, Type 3) | 150 ft (JLG 1500SJ) | Platform height | 150 | ft | JLG 1500SJ |  |  | 500-600 lb unrestricted; 1,000 lb restricted options | 150 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 2721 | 8190 | 15057 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-AWP-DUR | No FEMA telescopic codes (no owned proxy applied). DOZR: articulating ~10-20% dearer than telescopic at same height. Rent: Single source (COSTARS 2721/8190/15057). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-TB-185 | Aerial work platforms | Boom lift, telescopic (straight) | Telescopic (Group B, Type 3) | 180-185 ft ultra (JLG 1850SJ) | Platform height | 185 | ft | JLG 1850SJ |  |  | 500-600 lb unrestricted; 1,000 lb restricted options | 185 | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 4477 | 9499 | 20328 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-AWP-DUR | No FEMA telescopic codes (no owned proxy applied). DOZR: articulating ~10-20% dearer than telescopic at same height. Rent: Single source (COSTARS 4477/9499/20328). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-TOW-34 | Aerial work platforms | Boom lift, towable (trailer) | Towable (Group B, Type 1) | 34 ft towable (Genie TZ-34) | Platform height | 34 | ft | 34 ft towable (Genie TZ-34) |  |  |  | 34 | dual | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 250 | 750 | 1850 | 1600 | 2403 | bare |  |  | COSTARS;SCAFEX;DOZR-BM | mixed: 3/2023-3/2024, Mar 2026, Sep 2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | LF-AWP-DUR | DOZR towable range is 30-55 ft (applied to both). Rent: Median of 3 source points (COSTARS 328/975/2403; SCAF 250/750/1850; DOZRB 250/650/1600). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-TOW-50 | Aerial work platforms | Boom lift, towable (trailer) | Towable (Group B, Type 1) | 50 ft towable (Genie TZ-50) | Platform height | 50 | ft | 50 ft towable (Genie TZ-50) |  |  |  | 50 | dual | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 350 | 950 | 2412 | 1600 | 2500 | bare |  |  | COSTARS;SCAFEX;DOZR-BM | mixed: 3/2023-3/2024, Mar 2026, Sep 2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | LF-AWP-DUR | DOZR towable range is 30-55 ft (applied to both). Rent: Median of 3 source points (COSTARS 386/1148/2412; SCAF 350/950/2500; DOZRB 250/650/1600). DOZR/ScaffoldExchange values are range midpoints. COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-SPIDER-34 | Aerial work platforms | Spider / atrium (tracked) lift | Atrium/spider (Group B) | 34 ft atrium/spider | Working/platform height (COSTARS class) | 34 | ft | Atrium/spider lift (COSTARS class) |  |  |  | 34 | dual | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 744 | 1845 | 4114 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | LF-AWP-DUR | Notes list spider/track lifts as having no rate data; COSTARS 'atrium' classes used as the spider/atrium row (single source). Rent: Single source (COSTARS 744/1845/4114). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-SPIDER-51 | Aerial work platforms | Spider / atrium (tracked) lift | Atrium/spider (Group B) | 51 ft atrium/spider | Working/platform height (COSTARS class) | 51 | ft | Atrium/spider lift (COSTARS class) |  |  |  | 51 | dual | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 1673 | 3086 | 6470 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | LF-AWP-DUR | Notes list spider/track lifts as having no rate data; COSTARS 'atrium' classes used as the spider/atrium row (single source). Rent: Single source (COSTARS 1673/3086/6470). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-SPIDER-60 | Aerial work platforms | Spider / atrium (tracked) lift | Atrium/spider (Group B) | 60 ft atrium/spider | Working/platform height (COSTARS class) | 60 | ft | Atrium/spider lift (COSTARS class) |  |  |  | 60 | dual | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 2284 | 4285 | 7722 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | LF-AWP-DUR | Notes list spider/track lifts as having no rate data; COSTARS 'atrium' classes used as the spider/atrium row (single source). Rent: Single source (COSTARS 2284/4285/7722). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-SPIDER-69 | Aerial work platforms | Spider / atrium (tracked) lift | Atrium/spider (Group B) | 69 ft atrium/spider | Working/platform height (COSTARS class) | 69 | ft | Atrium/spider lift (COSTARS class) |  |  |  | 69 | dual | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 3031 | 5228 | 9272 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | LF-AWP-DUR | Notes list spider/track lifts as having no rate data; COSTARS 'atrium' classes used as the spider/atrium row (single source). Rent: Single source (COSTARS 3031/5228/9272). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-SPIDER-77 | Aerial work platforms | Spider / atrium (tracked) lift | Atrium/spider (Group B) | 77 ft atrium/spider | Working/platform height (COSTARS class) | 77 | ft | Atrium/spider lift (COSTARS class) |  |  |  | 77 | dual | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 3079 | 5369 | 11583 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | LF-AWP-DUR | Notes list spider/track lifts as having no rate data; COSTARS 'atrium' classes used as the spider/atrium row (single source). Rent: Single source (COSTARS 3079/5369/11583). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs fuel gal/hr; Needs rate (owned)
AW-MAST-20 | Aerial work platforms | Vertical mast / personnel lift | Vertical mast, self-propelled (Group A) | 18-20 ft mast-style (self-propelled) | Platform/working height (COSTARS class) | 20 | ft | Genie GR/QS, JLG Toucan type (unverified) |  |  |  | 20 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 303 | 841 | 1367 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | COSTARS single source; some COSTARS day/week/4-week ratios are irregular (contract structuring). Rent: Single source (COSTARS 303/841/1367). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-MAST-26 | Aerial work platforms | Vertical mast / personnel lift | Vertical mast, self-propelled (Group A) | 26 ft mast-style | Platform/working height (COSTARS class) | 26 | ft | Genie GR/QS, JLG Toucan type (unverified) |  |  |  | 26 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 306 | 753 | 1664 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | COSTARS single source; some COSTARS day/week/4-week ratios are irregular (contract structuring). Rent: Single source (COSTARS 306/753/1664). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-MAST-33 | Aerial work platforms | Vertical mast / personnel lift | Vertical mast, self-propelled (Group A) | 33 ft mast-style | Platform/working height (COSTARS class) | 33 | ft | Genie GR/QS, JLG Toucan type (unverified) |  |  |  | 33 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 376 | 952 | 2529 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | COSTARS single source; some COSTARS day/week/4-week ratios are irregular (contract structuring). Rent: Single source (COSTARS 376/952/2529). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-1MAN-12 | Aerial work platforms | Vertical mast / personnel lift | One-man drivable (Group A, Type 3) | 12 ft one-man drivable | Platform/working height (COSTARS class) | 12 | ft | Genie GR/QS, JLG Toucan type (unverified) |  |  |  | 12 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 206 | 329 | 466 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | COSTARS single source; some COSTARS day/week/4-week ratios are irregular (contract structuring). Rent: Single source (COSTARS 206/329/466). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-1MAN-15 | Aerial work platforms | Vertical mast / personnel lift | One-man drivable (Group A, Type 3) | 15 ft one-man drivable | Platform/working height (COSTARS class) | 15 | ft | Genie GR/QS, JLG Toucan type (unverified) |  |  |  | 15 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 162 | 381 | 1024 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | COSTARS single source; some COSTARS day/week/4-week ratios are irregular (contract structuring). Rent: Single source (COSTARS 162/381/1024). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-1MAN-20 | Aerial work platforms | Vertical mast / personnel lift | One-man drivable (Group A, Type 3) | 20 ft one-man drivable | Platform/working height (COSTARS class) | 20 | ft | Genie GR/QS, JLG Toucan type (unverified) |  |  |  | 20 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 215 | 424 | 684 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | COSTARS single source; some COSTARS day/week/4-week ratios are irregular (contract structuring). Rent: Single source (COSTARS 215/424/684). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-PUSH-25 | Aerial work platforms | Vertical mast / personnel lift | Push-around vertical (Group A, Type 1) | 24-25 ft push-around | Platform/working height (COSTARS class) | 25 | ft | Genie GR/QS, JLG Toucan type (unverified) |  |  |  | 25 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 220 | 456 | 924 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | COSTARS single source; some COSTARS day/week/4-week ratios are irregular (contract structuring). Rent: Single source (COSTARS 220/456/924). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-PUSH-30 | Aerial work platforms | Vertical mast / personnel lift | Push-around vertical (Group A, Type 1) | 30 ft push-around | Platform/working height (COSTARS class) | 30 | ft | Genie GR/QS, JLG Toucan type (unverified) |  |  |  | 30 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 227 | 506 | 1221 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | COSTARS single source; some COSTARS day/week/4-week ratios are irregular (contract structuring). Rent: Single source (COSTARS 227/506/1221). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-PUSH-36 | Aerial work platforms | Vertical mast / personnel lift | Push-around vertical (Group A, Type 1) | 36 ft push-around | Platform/working height (COSTARS class) | 36 | ft | Genie GR/QS, JLG Toucan type (unverified) |  |  |  | 36 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 270 | 636 | 1810 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | COSTARS single source; some COSTARS day/week/4-week ratios are irregular (contract structuring). Rent: Single source (COSTARS 270/636/1810). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-PUSH-40 | Aerial work platforms | Vertical mast / personnel lift | Push-around vertical (Group A, Type 1) | 40 ft push-around | Platform/working height (COSTARS class) | 40 | ft | Genie GR/QS, JLG Toucan type (unverified) |  |  |  | 40 | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 289 | 807 | 1780 |  |  | bare |  |  | COSTARS | 3/2023-3/2024 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | delivered-by-supplier |  |  | N | 200 | 200 | LF-AWP-DUR | COSTARS single source; some COSTARS day/week/4-week ratios are irregular (contract structuring). Rent: Single source (COSTARS 289/807/1780). COSTARS = Sunbelt PA not-to-exceed contract caps (day rates are ceilings). | Needs rate (owned)
AW-BUCKET-55 | Aerial work platforms | Truck-mounted aerial (bucket truck) | Truck-mounted (Group B, Type 1) | 55 ft bucket truck | Working height | 55 | ft | Altec AA55 (incl. truck) |  |  |  | 55 | diesel | Truck Driver (per WD class/axles) / lineman (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8486 | 62.86 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-AWP-DUR | No bucket-truck rental rates found. FEMA: Includes truck. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
AW-BUCKET-80 | Aerial work platforms | Truck-mounted aerial (bucket truck) | Truck-mounted (Group B, Type 1) | 80 ft bucket truck | Working height | 80 | ft | Altec AH85B (incl. truck) |  |  |  | 80 | diesel | Truck Driver (per WD class/axles) / lineman (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8487 | 65.87 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-AWP-DUR | No bucket-truck rental rates found. FEMA: Includes truck. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
AW-BUCKET-100 | Aerial work platforms | Truck-mounted aerial (bucket truck) | Truck-mounted (Group B, Type 1) | 100 ft bucket truck | Working height | 100 | ft | Altec AN67-E100 (incl. truck) |  |  |  | 100 | diesel | Truck Driver (per WD class/axles) / lineman (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8488 | 68.03 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-AWP-DUR | No bucket-truck rental rates found. FEMA: Includes truck. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
AW-BUCKET-120 | Aerial work platforms | Truck-mounted aerial (bucket truck) | Truck-mounted (Group B, Type 1) | 120 ft bucket truck | Working height | 120 | ft | Altec AH125 (incl. truck) |  |  |  | 120 | diesel | Truck Driver (per WD class/axles) / lineman (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8489 | 78.43 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-AWP-DUR | No bucket-truck rental rates found. FEMA: Includes truck. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
AW-MCWP | Aerial work platforms | Mast-climbing work platform | MCWP | Mast-climbing work platform | Type | MCWP | [6 empty] | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HYLFT factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-AWP-DUR | Category named in notes; no specs or rates. | Needs rate; Needs rate (rental); Needs rate (owned)
TH-3K-13 | Lifting & material handling | Telehandler | Compact | 3,000 lb x 13 ft | Rated capacity | 3000 | lb |  |  |  | 3,000 lb | 13 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
TH-5K-19 | Lifting & material handling | Telehandler | Compact / variable reach | 5,000 lb x 19 ft | Rated capacity | 5000 | lb | Cat TH255; JCB/Cat TH627 (5,500 lb/18.8 ft); 5,000 lb/16.4 ft |  |  | 5,000 lb | 19 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 423 | 1175 | 2853 | 2500 | 3748 | bare |  |  | W25;B25;A26;DOZR-TH | 2025-2026 | A |  |  |  | 0.49 | 0.68 | 0.88 | Cat VisionLink Dec 2022, model TH255C [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 4 sources (W 446/1292/3748; B 345/1035/3105; A 450/1200/2500; D 400/1150/2600). | Needs rate (owned)
TH-5K-20E | Lifting & material handling | Telehandler | Electric | 5,000 lb x 20 ft | Rated capacity | 5000 | lb | UR electric class |  |  | 5,000 lb | 20 | electric | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). | Needs rate; Needs rate (rental); Needs rate (owned)
TH-6K-42 | Lifting & material handling | Telehandler | Variable reach | 6,000 lb x 42 ft | Rated capacity | 6000 | lb | Cat TL642 (6,500 lb/42 ft); SkyTrak 6034/6036 |  | 74 | 6,000 lb | 42 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 550 | 1500 | 3300 | 2370 | 5590 | bare |  |  | W25;B25;DOZR-TH | 2025-2026 | A | 8306 | 94.49 | FEMA 2025 | 3.64 | 4.93 | 6.23 | Cat VisionLink Dec 2022, model TL642D [CATFUEL22] | 76.45 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). Rent: Median of 3 sources (W 665/1928/5590; B 395/1185/2370; D 550/1500/3300). Burris 6k 4-week $2,370 is below its 8k rate - possible sheet error. FEMA: Cat TL642, 74 hp. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
TH-7K-44 | Lifting & material handling | Telehandler | Variable reach | 7,000 lb x 44 ft | Rated capacity | 7000 | lb |  |  |  | 7,000 lb | 44 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
TH-9K-43 | Lifting & material handling | Telehandler | Variable reach | 9,000 lb x 43 ft | Rated capacity | 9000 | lb | Cat TL943 (9,000 lb/43 ft); Cat TH0842; SkyTrak 8042 |  | 111 | 9,000 lb | 43 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 675 | 1500 | 3780 | 3300 | 5845 | bare |  |  | W25;B25;DOZR-TH | 2025-2026 | A | 8307 | 102.26 | FEMA 2025 | 2.87 | 3.84 | 4.82 | Cat VisionLink Dec 2022, model TL943D [CATFUEL22] | 88.21 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 3 sources (W TH0842/TL943 avg 694/2016/5844; B 420/1260/3780; D 675/1500/3300). Class 8,000-9,000 lb. FEMA: Cat TL943, 111 hp. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
TH-10K-55 | Lifting & material handling | Telehandler | Variable reach | 10,000 lb x 55 ft | Rated capacity | 10000 | lb | Cat TL1055; SkyTrak 10054; 10,000 lb/56 ft |  |  | 10,000 lb | 55 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 825 | 2100 | 4500 | 4250 | 8004 | bare |  |  | W25;B25;A26;DOZR-TH | 2025-2026 | A |  |  |  | 1.56 | 1.86 | 2.15 | Cat VisionLink Dec 2022, model TL1055D [CATFUEL22] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). Rent: Median of 4 sources (W 952/2760/8004; B 500/1500/4500; A 750/2100/4500; D 900/2100/4250). | Non-monotonic vs TH-10K-62 - source data; Needs rate (owned)
TH-10K-62 | Lifting & material handling | Telehandler | Variable reach, high lift | 10,000 lb x 62 ft | Rated capacity | 10000 | lb | Merlo TH 4,5.19 (62 ft) |  |  | 10,000 lb | 62 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 500 | 1200 | 3000 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). Rent: Columbus only. | Needs fuel gal/hr; Needs rate (owned)
TH-12K-55 | Lifting & material handling | Telehandler | Variable reach | 12,000 lb x 55 ft | Rated capacity | 12000 | lb | Cat TL1255 (12,000 lb); Skyjack SJ1256; 12,000 lb/56 ft |  | 134 | 12,000 lb | 55 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 900 | 2050 | 4625 | 3850 | 8639 | bare |  |  | W25;A26;R25;DOZR-TH | 2025-2026 | A | 8308 | 112.98 | FEMA 2025 | 1.58 | 1.89 | 2.2 | Cat VisionLink Dec 2022, model TL1255D [CATFUEL22] | 106.06 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). Cat TL1255D fuel (1.89 med) is far below TL642D (4.93) as published. Rent: Median of 4 sources (W 1027/2979/8639; A 800/2000/5000; R 600/1500/3850; D 1000/2100/4250). FEMA: Cat TL1255, 134 hp. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
TH-12K-61 | Lifting & material handling | Telehandler | Variable reach, high lift | 12,100 lb x 61 ft | Rated capacity | 12100 | lb | Merlo TH 5,5.19 (61 ft) |  |  | 12,100 lb | 61 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 575 | 1400 | 3500 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). Rent: Columbus only. | Needs fuel gal/hr; Needs rate (owned)
TH-14K-55 | Lifting & material handling | Telehandler | Variable reach | 14,000 lb x 55 ft | Rated capacity | 14000 | lb |  |  |  | 14,000 lb | 55 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
TH-16K-44 | Lifting & material handling | Telehandler | Heavy | 16,000 lb x 44 ft | Rated capacity | 16000 | lb | Cat TL1644 |  |  | 16,000 lb | 44 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 1027 | 2979 | 8639 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). Rent: Wheeler only (same price as TL1255). | Needs fuel gal/hr; Needs rate (owned)
TH-20K-43 | Lifting & material handling | Telehandler | Heavy | 20,000 lb x 43 ft | Rated capacity | 20000 | lb |  |  |  | 20,000 lb | 43 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
TH-GE-12K-78 | Lifting & material handling | Telehandler | Ground-engaging (stabilizers) | 12,000 lb x 78 ft | Rated capacity | 12000 | lb |  |  |  | 12,000 lb | 78 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
TH-HC-27K | Lifting & material handling | Telehandler | High-capacity | 27,000 lb x 33 ft | Rated capacity | 27000 | lb | Cat TL2733 |  |  | 27,000 lb | 33 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 1581 | 4585 | 13297 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). Rent: Wheeler only. | Needs fuel gal/hr; Non-monotonic vs TH-HC-35K - source data; Needs rate (owned)
TH-HC-35K | Lifting & material handling | Telehandler | High-capacity | 35,200 lb x 33 ft | Rated capacity | 35200 | lb | Merlo HTH 16.10 |  |  | 35,200 lb | 33 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 1775 | 4400 | 11000 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). Rent: Columbus only. Lift height not stated; UR class 35,000 lb/31-33 ft used. | Needs fuel gal/hr; Needs rate (owned)
TH-ROT-13K-82 | Lifting & material handling | Telehandler | Rotating | 13,200 lb x 82 ft | Rated capacity | 13200 | lb | Merlo RTH 6.25 |  |  | 13,200 lb | 82 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 1300 | 3200 | 8000 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). Rent: Columbus only. | Needs fuel gal/hr; Needs rate (owned)
TH-ROT-13K-96 | Lifting & material handling | Telehandler | Rotating | 13,200 lb x 96 ft | Rated capacity | 13200 | lb |  |  |  | 13,200 lb | 96 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
TH-ROT-127 | Lifting & material handling | Telehandler | Rotating | 13,200 lb x 127 ft | Rated capacity | 13200 | lb | Merlo RTH 6.39 |  |  | 13,200 lb | 127 | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 2100 | 5200 | 13000 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-TH-DUR | Class from United Rentals capacity x height list. Attachments extra (Burris $105/315/945 each; DOZR truss $75-150/day). Capacity unverified Rent: Columbus only. Capacity of RTH 6.39 not stated; 13,200 lb assumed from RTH series label (verify). | Needs fuel gal/hr; Capacity unverified; Needs rate (owned)
FK-IND-5K | Lifting & material handling | Forklift | Warehouse/industrial (cushion/pneumatic) | 5,000 lb | Rated capacity | 5000 | lb | Komatsu FG25; dual-fuel/propane 5,000 lb |  |  | 5,000 lb |  | propane | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 235 | 715 | 1969 | 1775 | 2115 | bare |  |  | W25;B25;N25 | 2025 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-FK-DUR | Rent: Median of 3 sources (W 407/895/1969; B 235/705/2115; N 225/715/1775). | Needs fuel gal/hr; Needs rate (owned)
FK-6K | Lifting & material handling | Forklift | Industrial / yard | 6,000 lb | Rated capacity | 6000 | lb | Toyota 8FGU30 (FEMA); 6,000 lb propane |  |  | 6,000 lb |  | propane | Operating Engineer - light/compact group (per WD) | day/wk/4wk | 250 | 875 | 2195 |  |  | bare |  |  | N25 | Jan 2025 | B | 8300 | 24.18 | FEMA 2025 | [5 empty] | B | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-FK-DUR | LPG unit: FEMA fuel back-out not possible (no propane basis or gal/hr). Rent: Nu-Way only. FEMA: Toyota 8FGU30 (LPG/gas). | Needs fuel gal/hr
FK-11K | Lifting & material handling | Forklift | Industrial / yard | 11,000 lb | Rated capacity | 11000 | lb | Toyota 8FG50U |  |  | 11,000 lb |  | propane | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8301 | 28.77 | FEMA 2025 | [5 empty] | B | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-FK-DUR | Caltrans FKLFT bands 1,000-75,000 lb. Fuel type for Toyota 8FG = LPG/gas (inferred from model code). | Needs fuel gal/hr; Needs rate (rental)
FK-17K | Lifting & material handling | Forklift | Industrial / yard | 17,500 lb | Rated capacity | 17500 | lb | Toyota 8FG80U |  |  | 17,500 lb |  | propane | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8302 | 32.32 | FEMA 2025 | [5 empty] | B | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-FK-DUR | Caltrans FKLFT bands 1,000-75,000 lb. Fuel type for Toyota 8FG = LPG/gas (inferred from model code). | Needs fuel gal/hr; Needs rate (rental)
FK-45K | Lifting & material handling | Forklift | Industrial / yard | 45,000 lb | Rated capacity | 45000 | lb | Taylor TE-450M (45,000-50,000 lb) |  |  | 45,000 lb |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8303 | 70.8 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: FKLFT factor 0.22. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-FK-DUR | Caltrans FKLFT bands 1,000-75,000 lb. Fuel type for Toyota 8FG = LPG/gas (inferred from model code). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
CR-CARRY-15T | Lifting & material handling | Carry-deck crane | Carry deck (8-18 t) | 8-15 t carry deck | Capacity | 15 | ton | Broderson/Shuttlelift type |  |  | 15 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-CRANE-DUR | URI/Sunstate prices behind login (gap). | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
CR-CARRY-20T | Lifting & material handling | Carry-deck crane | Yard / carry deck | 20 t yard crane | Capacity | 20 | ton | Shuttlelift CD5520 |  |  | 20 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8500 | 127.06 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-CRANE-DUR | Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
CR-RT-15T | Lifting & material handling | Rough-terrain crane | RT (small) | 15 t RT | Capacity | 15 | ton | Broderson RT-300-2C |  |  | 15 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8501 | 145.47 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | LF-CRANE-DUR | Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
CR-RT-50T-BARE | Lifting & material handling | Rough-terrain crane | RT, bare rental | 50 t RT (bare) | Capacity | 50 | ton | Link-Belt RTC-8050/8065 class (Columbus) |  |  | 50 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | 1200 | 3000 | 7500 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Weight not in notes; RT cranes assumed permitted moves (verify). Rent: Columbus only; sheet does not mention operator (treated as bare). ~$150-220/hr if spread over 160 hr. | Needs fuel gal/hr; Needs rate (owned)
CR-RT-65T-BARE | Lifting & material handling | Rough-terrain crane | RT, bare rental | 65 t RT (bare) | Capacity | 65 | ton | Link-Belt RTC-8050/8065 class (Columbus) |  |  | 65 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | 1375 | 3400 | 8500 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Weight not in notes; RT cranes assumed permitted moves (verify). Rent: Columbus only; sheet does not mention operator (treated as bare). ~$150-220/hr if spread over 160 hr. | Needs fuel gal/hr; Needs rate (owned)
CR-RT-85T-BARE | Lifting & material handling | Rough-terrain crane | RT, bare rental | 85 t RT (bare) | Capacity | 85 | ton | Link-Belt RTC-8050/8065 class (Columbus) |  |  | 85 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | 2000 | 5000 | 12500 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Weight not in notes; RT cranes assumed permitted moves (verify). Rent: Columbus only; sheet does not mention operator (treated as bare). ~$150-220/hr if spread over 160 hr. | Needs fuel gal/hr; Needs rate (owned)
CR-RT-100T-BARE | Lifting & material handling | Rough-terrain crane | RT, bare rental | 100 t RT (bare) | Capacity | 100 | ton | Link-Belt RTC-8050/8065 class (Columbus) |  |  | 100 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | 2250 | 5600 | 14000 |  |  | bare |  |  | C25 | Jun 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Weight not in notes; RT cranes assumed permitted moves (verify). Rent: Columbus only; sheet does not mention operator (treated as bare). ~$150-220/hr if spread over 160 hr. | Needs fuel gal/hr; Needs rate (owned)
CR-BOOMTRK-9T | Lifting & material handling | Boom truck (truck-mounted telescopic) | Boom truck | 19,000 lb (9.5 t) boom truck | Capacity | 9.5 | ton | Manitex (FEMA 8496) |  | 240 | 19,000 lb |  | diesel | Operating Engineer - crane group (per WD); oiler if required | hr (operated) / hr owned | [5 empty] | bare |  |  |  |  | D | 8496 | 54.67 | FEMA 2025 | 4.08 | 5.37 | 7 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 35.02 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR | No rental rate for this size. HP from FEMA (as extracted). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
CR-BOOMTRK-23T | Lifting & material handling | Boom truck (truck-mounted telescopic) | Boom truck | 46,000 lb (23 t) boom truck | Capacity | 23 | ton | Manitex (FEMA 8497) |  | 510 | 46,000 lb |  | diesel | Operating Engineer - crane group (per WD); oiler if required | hr (operated) / hr owned | [5 empty] | operated | 210 | 3 | NTXC;DEPC | 2025 | A | 8497 | 74.96 | FEMA 2025 | 8.68 | 11.4 | 14.87 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 33.24 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. HP from FEMA (as extracted). Rent (operated, incl. operator): Median (=mean) of NTX 23 t boom truck $155 (3 hr min) and Dependable 22 t $265 (1 hr min). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
CR-BOOMTRK-30T | Lifting & material handling | Boom truck (truck-mounted telescopic) | Boom truck | 60,000 lb (30 t) boom truck | Capacity | 30 | ton | Manitex (FEMA 8498) |  | 510 | 60,000 lb |  | diesel | Operating Engineer - crane group (per WD); oiler if required | hr (operated) / hr owned | [5 empty] | operated | 175 | 4 | NTXC | 2025 | B | 8498 | 111.64 | FEMA 2025 | 8.68 | 11.4 | 14.87 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 69.92 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. HP from FEMA (as extracted). Rent (operated, incl. operator): NTX 30 t boom truck $175 (4 hr min). Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
CR-HYD-40T-OP | Lifting & material handling | Hydraulic truck / all-terrain crane | Operated hourly | 40 t hydraulic (operated) | Capacity | 40 | ton | Hydraulic truck/AT crane (rate-card class) |  |  | 40 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required - included in operated rate | hr (operated) | [5 empty] | operated | 245 | 4 | NTXC;DEPC | 2025 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. CFCS FL bands (Jun 2026): <50 t $245-315/hr; 50-100 t $320-460/hr; large AT 1-operator $415-475/hr. Rate cards do not state carrier type. Rent (operated, incl. operator): Median (=mean) of NTX $205 (4 hr min) and Dependable $285 (2 hr min). | Needs rate (owned); Needs fuel gal/hr
CR-HYD-50T-OP | Lifting & material handling | Hydraulic truck / all-terrain crane | Operated hourly | 50 t hydraulic (operated) | Capacity | 50 | ton | Hydraulic truck/AT crane (rate-card class) |  |  | 50 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required - included in operated rate | hr (operated) | [5 empty] | operated | 225 | 4 | NTXC | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. CFCS FL bands (Jun 2026): <50 t $245-315/hr; 50-100 t $320-460/hr; large AT 1-operator $415-475/hr. Rate cards do not state carrier type. Rent (operated, incl. operator): NTX only. | Needs rate (owned); Needs fuel gal/hr
CR-HYD-60T-OP | Lifting & material handling | Hydraulic truck / all-terrain crane | Operated hourly | 60 t hydraulic (operated) | Capacity | 60 | ton | Hydraulic truck/AT crane (rate-card class) |  |  | 60 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required - included in operated rate | hr (operated) | [5 empty] | operated | 250 | 4 | NTXC | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. CFCS FL bands (Jun 2026): <50 t $245-315/hr; 50-100 t $320-460/hr; large AT 1-operator $415-475/hr. Rate cards do not state carrier type. Rent (operated, incl. operator): NTX only. | Needs rate (owned); Needs fuel gal/hr
CR-HYD-75T-OP | Lifting & material handling | Hydraulic truck / all-terrain crane | Operated hourly | 75 t hydraulic (operated) | Capacity | 75 | ton | Hydraulic truck/AT crane (rate-card class) |  |  | 75 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required - included in operated rate | hr (operated) | [5 empty] | operated | 330 | 4 | NTXC;DEPC | 2025 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. CFCS FL bands (Jun 2026): <50 t $245-315/hr; 50-100 t $320-460/hr; large AT 1-operator $415-475/hr. Rate cards do not state carrier type. Rent (operated, incl. operator): Median (=mean) of NTX $310 and Dependable $350 (4 hr min both). | Needs rate (owned); Needs fuel gal/hr
CR-HYD-80T-OP | Lifting & material handling | Hydraulic truck / all-terrain crane | Operated hourly | 80 t hydraulic (operated) | Capacity | 80 | ton | Hydraulic truck/AT crane (rate-card class) |  |  | 80 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required - included in operated rate | hr (operated) | [5 empty] | operated | 330 | 4 | NTXC | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. CFCS FL bands (Jun 2026): <50 t $245-315/hr; 50-100 t $320-460/hr; large AT 1-operator $415-475/hr. Rate cards do not state carrier type. Rent (operated, incl. operator): NTX only. | Needs rate (owned); Needs fuel gal/hr
CR-HYD-100T-OP | Lifting & material handling | Hydraulic truck / all-terrain crane | Operated hourly | 100 t hydraulic (operated) | Capacity | 100 | ton | Hydraulic truck/AT crane (rate-card class) |  |  | 100 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required - included in operated rate | hr (operated) | [5 empty] | operated | 355 | 4 | NTXC | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. CFCS FL bands (Jun 2026): <50 t $245-315/hr; 50-100 t $320-460/hr; large AT 1-operator $415-475/hr. Rate cards do not state carrier type. Rent (operated, incl. operator): NTX only. | Needs rate (owned); Needs fuel gal/hr
CR-HYD-110T-OP | Lifting & material handling | Hydraulic truck / all-terrain crane | Operated hourly | 110 t hydraulic (operated) | Capacity | 110 | ton | Hydraulic truck/AT crane (rate-card class) |  |  | 110 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required - included in operated rate | hr (operated) | [5 empty] | operated | 385 | 4 | NTXC | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. CFCS FL bands (Jun 2026): <50 t $245-315/hr; 50-100 t $320-460/hr; large AT 1-operator $415-475/hr. Rate cards do not state carrier type. Rent (operated, incl. operator): NTX only. | Needs rate (owned); Needs fuel gal/hr
CR-HYD-120T-OP | Lifting & material handling | Hydraulic truck / all-terrain crane | Operated hourly | 120 t hydraulic (operated) | Capacity | 120 | ton | Hydraulic truck/AT crane (rate-card class) |  |  | 120 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required - included in operated rate | hr (operated) | [5 empty] | operated | 445 | 4 | NTXC;DEPC | 2025 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. CFCS FL bands (Jun 2026): <50 t $245-315/hr; 50-100 t $320-460/hr; large AT 1-operator $415-475/hr. Rate cards do not state carrier type. Rent (operated, incl. operator): Median (=mean) of NTX 120 t $440 (4 hr) and Dependable 115 t $450 (8 hr min). | Needs rate (owned); Needs fuel gal/hr
CR-HYD-165T-OP | Lifting & material handling | Hydraulic truck / all-terrain crane | Operated hourly | 165 t hydraulic (operated) | Capacity | 165 | ton | Hydraulic truck/AT crane (rate-card class) |  |  | 165 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required - included in operated rate | hr (operated) | [5 empty] | operated | 520 | 4 | NTXC | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | crane-assembled |  |  | Y |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. CFCS FL bands (Jun 2026): <50 t $245-315/hr; 50-100 t $320-460/hr; large AT 1-operator $415-475/hr. Rate cards do not state carrier type. Rent (operated, incl. operator): NTX only. | Needs rate (owned); Needs fuel gal/hr
CR-HYD-210T-OP | Lifting & material handling | Hydraulic truck / all-terrain crane | Operated hourly | 210 t hydraulic (operated) | Capacity | 210 | ton | Hydraulic truck/AT crane (rate-card class) |  |  | 210 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required - included in operated rate | hr (operated) | [5 empty] | operated | 550 | 4 | NTXC | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | crane-assembled |  |  | Y |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. CFCS FL bands (Jun 2026): <50 t $245-315/hr; 50-100 t $320-460/hr; large AT 1-operator $415-475/hr. Rate cards do not state carrier type. Rent (operated, incl. operator): NTX only. | Needs rate (owned); Needs fuel gal/hr
CR-HYD-240T-OP | Lifting & material handling | Hydraulic truck / all-terrain crane | Operated hourly | 240 t hydraulic (operated) | Capacity | 240 | ton | Hydraulic truck/AT crane (rate-card class) |  |  | 240 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required - included in operated rate | hr (operated) | [5 empty] | operated | 575 | 4 | NTXC | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | crane-assembled |  |  | Y |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. CFCS FL bands (Jun 2026): <50 t $245-315/hr; 50-100 t $320-460/hr; large AT 1-operator $415-475/hr. Rate cards do not state carrier type. Rent (operated, incl. operator): NTX only. | Needs rate (owned); Needs fuel gal/hr
CR-HYD-275T-OP | Lifting & material handling | Hydraulic truck / all-terrain crane | Operated hourly | 275 t hydraulic (operated) | Capacity | 275 | ton | Hydraulic truck/AT crane (rate-card class) |  |  | 275 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required - included in operated rate | hr (operated) | [5 empty] | operated | 595 | 4 | NTXC | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | crane-assembled |  |  | Y |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. CFCS FL bands (Jun 2026): <50 t $245-315/hr; 50-100 t $320-460/hr; large AT 1-operator $415-475/hr. Rate cards do not state carrier type. Rent (operated, incl. operator): NTX only. | Needs rate (owned); Needs fuel gal/hr
CR-AT-35T | Lifting & material handling | All-terrain crane | AT (owned basis) | 35 t all-terrain | Capacity | 35 | ton | Grove GMK2035E (34.9 t) |  |  | 35 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8502 | 176.98 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | For operated rental use CR-HYD-*-OP rows. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
CR-AT-60T | Lifting & material handling | All-terrain crane | AT (owned basis) | 60 t all-terrain | Capacity | 60 | ton | Grove GMK3055 |  |  | 60 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8503 | 209.49 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,LF-STEEL-BEAM | For operated rental use CR-HYD-*-OP rows. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
CR-AT-HEAVY | Lifting & material handling | All-terrain crane | Heavy-lift AT (operated) | Heavy-lift AT (size not stated) | Capacity |  | ton | [5 empty] | diesel | Operating Engineer - crane group (per WD); oiler if required - included | hr (operated) | [5 empty] | operated | 1350 | 8 | CFCS | Jun 4 2026 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | crane-assembled |  |  | Y |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST | Operated hourly rate INCLUDES operator; add portal-to-portal travel, 7-10% fuel surcharge, OT +$50-85/hr/man (NTX) or +$74/hr (CFCS), riggers $88-160/hr (4 hr min). Do NOT add operator labor on top. Rent (operated, incl. operator): CFCS ~$1,350/hr (emergency $1,685); 8 hr minimum for heavy-lift. | Needs rate (owned); Needs fuel gal/hr
CR-CRAWL-125T | Lifting & material handling | Crawler crane | Lattice boom | 125 t lattice crawler | Capacity | 125 | ton | American HC-125 |  |  | 125 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8504 | 288.74 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17 / 0.16. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | crane-assembled |  |  | Y |  |  | LF-CRANE-DUR,LF-GIRDER-PRECAST,FD-PILE-DRIVE | Mob = multiple lowbeds + counterweight + boom + assist crane (counts not sourced). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
CR-CRAWL-CLAM-70T | Lifting & material handling | Crawler crane | Clamshell/dragline duty | 70 t crawler (clam/dragline) | Capacity | 70 | ton |  |  |  | 70 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8210 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | crane-assembled |  |  | Y |  |  | LF-CRANE-DUR | FEMA 8210: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
CR-CRAWL-CLAM-120T | Lifting & material handling | Crawler crane | Clamshell/dragline duty | 120 t crawler (clam/dragline) | Capacity | 120 | ton |  |  |  | 120 ton |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8211 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | crane-assembled |  |  | Y |  |  | LF-CRANE-DUR | FEMA 8211: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
CR-TRK-CLAM | Lifting & material handling | Truck crane | Truck-mounted clamshell | Truck-mounted clamshell | Type | clamshell |  | FEMA 8212 |  |  |  |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8212 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR | FEMA 8212: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
CR-TOWER | Lifting & material handling | Tower crane | Hammerhead/luffing/self-erecting | Tower crane (class not specified) | Type | tower | [6 empty] | electric | Operating Engineer - crane group (per WD); oiler if required | 4wk |  |  | 37500 | 15000 | 60000 | unspecified (bare/operated not stated) |  |  | BIGR-CR | Apr 27 2026 | B |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | crane-assembled |  |  | Y |  |  | LF-TOWER-LIFTS | Erection/dismantle, foundation, operator, climbing not included. Rent: BigRentz $15,000-60,000/month; midpoint used as 4-week; bare/operated not stated; page FAQ contradicts its tables. | Rate basis unclear; Rent basis unspecified (bare/operated not stated); verify before use; Needs rate (owned)
CR-SPIDER | Lifting & material handling | Mini / spider crane | Mini / spider crane | Mini / spider crane | Capacity |  | ton | [5 empty] | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | LF-CRANE-DUR | No capacity classes or rates in notes. | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
CR-KNUCKLE | Lifting & material handling | Knuckle-boom (articulating) truck crane | Knuckle-boom (articulating) truck crane | Knuckle-boom (articulating) truck crane | Capacity |  | ton | [5 empty] | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | LF-CRANE-DUR | No capacity classes or rates in notes. | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
CR-KNUCKLE-LDR | Lifting & material handling | Knuckleboom loader | Forestry knuckleboom | Knuckleboom loader | Model | 595ML |  | Barko 595ML (FEMA 8208) |  |  |  |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8208 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCETD/HCECL factor 0.12 truck / 0.17 crawler. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 |  | FEMA 8208: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
HOIST-PERS | Lifting & material handling | Personnel / material hoist | Rack & pinion hoist | Personnel/material hoist | Capacity |  | lb | [5 empty] | electric | Hoist operator (Operating Engineer, per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | LF-CRANE-DUR | No classes or rates in notes. | Needs rate; Needs rate (rental); Needs rate (owned)
TR-WB-6x36 | Utilities & trenching | Trencher | Walk-behind (tracked) | ~6 in x 36 in walk-behind | Max depth | 36 | in | Toro TRX; tracked walk-behind |  |  | 6 in wide x 36 in deep |  | gas | Laborer (per WD group) | day/wk/4wk | 250 | 750 | 2250 | 1575 | 2279 | bare |  |  | W25;B25;N25 | 2025-2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | UT-TRENCH-SMALL | Rent: Median of 3 sources (W 271/786/2279; B 250/750/2250; N 175/625/1575). | Needs fuel gal/hr; Needs rate (owned)
TR-SSL-4FT | Utilities & trenching | Trencher | Skid-steer attachment | 4 ft SSL trencher | Max depth | 48 | in | SSL/CTL trencher attachment |  |  |  |  | none (attachment) | None (non-operated item) | day/wk/4wk | 200 | 795 | 2395 |  |  | bare |  |  | R25 | Spring 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | UT-TRENCH-SMALL | Rent: RTL only. | Needs rate (owned)
TR-RIDE-V120 | Utilities & trenching | Trencher | Ride-on wheel-mounted chain | 60 in depth (~116 hp) | Max depth | 60 | in | Vermeer V120 |  | 116 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8514 | 286.18 | FEMA 2025 | 1.97 | 2.59 | 3.38 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 276.7 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | UT-TRENCH-CHAIN | FEMA: Very high for a 116 hp trencher (above a D8 dozer); possible code/rate misalignment in extraction. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged: implausibly high for 116 hp; verify; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
TR-FEMA-8650 | Utilities & trenching | Trencher | Ride-on (FEMA) | Seaman-Parsons trencher (FEMA 8650) | FEMA code | 8650 |  | Seaman-Parsons trencher |  |  |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8650 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | UT-TRENCH-CHAIN | FEMA 8650: FEMA rate not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
TR-FEMA-8651 | Utilities & trenching | Trencher | Ride-on (FEMA) | Seaman-Parsons trencher (FEMA 8651) | FEMA code | 8651 |  | Seaman-Parsons trencher |  |  |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8651 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | UT-TRENCH-CHAIN | FEMA 8651: FEMA rate not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
TR-FEMA-8652 | Utilities & trenching | Trencher | Ride-on (FEMA) | Trencher/ditcher (FEMA 8652) | FEMA code | 8652 |  | Trencher/ditcher |  |  |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8652 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | UT-TRENCH-CHAIN | FEMA 8652: FEMA rate not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
TR-FEMA-8653 | Utilities & trenching | Trencher | Ride-on (FEMA) | Trencher/ditcher (FEMA 8653) | FEMA code | 8653 |  | Trencher/ditcher |  |  |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8653 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | UT-TRENCH-CHAIN | FEMA 8653: FEMA rate not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
TR-PLOW-8661 | Utilities & trenching | Cable plow | Vibratory plow | DP-60 (18 in, 82 hp) | Plow depth | 18 | in | DP-60 |  | 82 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8661 |  |  | 1.39 | 1.83 | 2.39 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | UT-PLOW | FEMA 8661: Rate not captured. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
TR-PLOW-8662 | Utilities & trenching | Cable plow | Vibratory plow | DP-100 (42 in, 110 hp) | Plow depth | 42 | in | DP-100 |  | 110 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8662 |  |  | 1.87 | 2.46 | 3.21 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | UT-PLOW | FEMA 8662: Rate not captured. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
TR-PLOW-8660 | Utilities & trenching | Cable plow | Vibratory plow | Case Maxi-Sneaker (24 in, 210 hp) | Plow depth | 24 | in | Case Maxi-Sneaker |  | 210 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8660 |  |  | 3.57 | 4.69 | 6.12 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | UT-PLOW | FEMA 8660: Rate not captured. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
HDD-COMPACT | Utilities & trenching | Horizontal directional drill (HDD) | Compact/mini (<20,000 lb pullback) | 7,000 lb pullback (~25 hp) | Thrust/pullback | 7000 | lb | FEMA 8067 7,000 lb directional drill |  | 25 |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8067 |  |  | 0.43 | 0.56 | 0.73 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 | UT-HDD | FEMA 8067: Rate not captured. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
HDD-SMALL | Utilities & trenching | Horizontal directional drill (HDD) | Small (20,000-40,000 lb pullback) | 24,000 lb class (Vermeer D24x40) | Thrust/pullback | 24000 | lb | Vermeer D24x40A (4,000 ft-lb, 125 hp) |  | 125 | 4,000 ft-lb |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8067.1 |  |  | 2.13 | 2.79 | 3.65 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | UT-HDD | FEMA 8067.1: Rate not captured. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
HDD-MED | Utilities & trenching | Horizontal directional drill (HDD) | Medium/midi (40,000-100,000 lb) | 40,000-100,000 lb pullback | Thrust/pullback | 70000 | lb | 4,000-20,000 ft-lb; 50-200 gpm; up to 16 in, ~2,000 ft |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 | UT-HDD | Spec value = mid of band. | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
HDD-LARGE | Utilities & trenching | Horizontal directional drill (HDD) | Large/maxi (>100,000 lb) | 100,000 lb pullback (Vermeer D-140B 250x100 class) | Thrust/pullback | 100000 | lb | Vermeer D-140B (to 300 hp); >20,000 ft-lb; >200 gpm; 16-48 in, to ~6,500 ft |  | 300 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8065 |  |  | 5.1 | 6.71 | 8.75 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy |  |  | Y | 1913 | 1913 | UT-HDD | FEMA 8065: Rate not captured. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
AUGER-BORE | Utilities & trenching | Auger boring machine | Horizontal auger (jack & bore) | To 30 ft flight | Flight length | 30 | ft | Caltrans AUGHZ |  |  |  |  | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-JACKBORE |  | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
PIPEBURST-50T | Utilities & trenching | Pipe bursting rig | Static | 50-ton rig (4-8 in pipe) | Pull force | 50 | ton | [5 empty] | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-BURST-50 |  | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
PIPEBURST-100T | Utilities & trenching | Pipe bursting rig | Static | 100-ton rig (8-12 in, to 16 in) | Pull force | 100 | ton | [5 empty] | diesel | Operating Engineer - light/compact group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-BURST-100 |  | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
PIPELAYER | Utilities & trenching | Pipelayer / sideboom | Sideboom | Sideboom (class not sourced) | Lift capacity |  | lb | Cat PL-series |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 |  | No lift classes sourced. | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
VAC-TRAILER | Utilities & trenching | Vacuum / sewer | Vacuum excavator trailer | Vac-ex trailer | Tank |  | gal | [5 empty] | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | UT-VACEX | Tank/CFM classes not sourced. | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
VAC-HYDROVAC | Utilities & trenching | Vacuum / sewer | Hydro-vac truck | 500 gal debris tank | Debris tank | 500 | gal | FEMA 8715 |  |  |  |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8715 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | UT-VACEX | FEMA 8715: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
VAC-COMBO-VACTOR | Utilities & trenching | Vacuum / sewer | Combination sewer cleaner | Vactor 2100 Plus (12-13 CY, 310 hp) | Debris body | 12.5 | CY | Vactor 2100 Plus |  | 310 | 12-13 CY |  | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8714.1 |  |  | 5.27 | 6.93 | 9.04 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | UT-VACEX,UT-SEWERCLEAN | FEMA 8714.1: Rate not captured. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
VAC-COMBO-8714 | Utilities & trenching | Vacuum / sewer | Combination sewer cleaner | Combination sewer cleaner 800 gal spoils / 400 gal water | FEMA code | 8714 | [6 empty] | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8714 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | UT-SEWERCLEAN | FEMA 8714: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
VAC-COMBO-8714-2 | Utilities & trenching | Vacuum / sewer | Combination sewer cleaner | Combination unit 500-1,500 gal water | FEMA code | 8714.2 | [6 empty] | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8714.2 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | UT-SEWERCLEAN | FEMA 8714.2: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
VAC-COMBO-8714-3 | Utilities & trenching | Vacuum / sewer | Combination sewer cleaner | Combination unit 500-1,500 gal water | FEMA code | 8714.3 | [6 empty] | diesel | Truck Driver (per WD class/axles) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8714.3 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | UT-SEWERCLEAN | FEMA 8714.3: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
VAC-JET-8712 | Utilities & trenching | Vacuum / sewer | Sewer jetter (trailer) | Jetter 12 GPM @ 3,000 psi, 150 gal | Flow | 12 | gpm |  |  | 24 |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8712 |  |  | 0.41 | 0.54 | 0.7 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | UT-SEWERCLEAN | FEMA 8712: Rate not captured. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
VAC-JET-8713 | Utilities & trenching | Vacuum / sewer | Sewer jetter (trailer) | Jetter 25 GPM @ 4,000 psi, 300-600 gal | Flow | 25 | gpm |  |  | 74 |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8713 |  |  | 1.26 | 1.65 | 2.16 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | UT-SEWERCLEAN | FEMA 8713: Rate not captured. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
SEWERCAM-1 | Utilities & trenching | Vacuum / sewer | Sewer inspection | Sewer camera truck | FEMA code | 8711.1 | [6 empty] | electric | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8711.1 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8711.1: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
SEWERCAM-2 | Utilities & trenching | Vacuum / sewer | Sewer inspection | Sewer camera (Aries Pathfinder) | FEMA code | 8711.2 | [6 empty] | electric | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8711.2 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8711.2: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
WIRE-8943 | Utilities & trenching | Wire / cable placement | Puller/tensioner | Underground wire puller 5,000 lb | Tension/reel | 5000 | lb | [5 empty] | diesel | Lineman / Operator (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8943 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8943: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
WIRE-8944 | Utilities & trenching | Wire / cable placement | Puller/tensioner | Wire tensioner 8,000 lb reel | Tension/reel | 8000 | lb | [5 empty] | diesel | Lineman / Operator (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8944 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8944: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
DERRICK-8670 | Utilities & trenching | Digger derrick | Hydraulic digger derrick | Digger derrick (FEMA 8670) | FEMA code | 8670 | [6 empty] | diesel | Lineman / Operator (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8670 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8670: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
DERRICK-8671 | Utilities & trenching | Digger derrick | Hydraulic digger derrick | Digger derrick (FEMA 8671) | FEMA code | 8671 | [6 empty] | diesel | Lineman / Operator (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8671 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8671: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
TB-STL-8x12 | Utilities & trenching | Trench box / shield | Steel | Steel trench box 8x12 | Height x length | 8x12 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 148 | 429 | 1245 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Depth rating not sourced. Required at 5 ft+ depth, 18 in above grade (URI page). Rent: Wheeler only. | Needs rate (owned)
TB-STL-8x16 | Utilities & trenching | Trench box / shield | Steel | Steel trench box 8x16 | Height x length | 8x16 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 170 | 493 | 1429 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Depth rating not sourced. Required at 5 ft+ depth, 18 in above grade (URI page). Rent: Wheeler only. | Needs rate (owned)
TB-STL-8x20 | Utilities & trenching | Trench box / shield | Steel | Steel trench box 8x20 | Height x length | 8x20 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 219 | 635 | 1842 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Depth rating not sourced. Required at 5 ft+ depth, 18 in above grade (URI page). Rent: Wheeler only. | Needs rate (owned)
TB-STL-8x24 | Utilities & trenching | Trench box / shield | Steel | Steel trench box 8x24 | Height x length | 8x24 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 253 | 734 | 2128 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Depth rating not sourced. Required at 5 ft+ depth, 18 in above grade (URI page). Rent: Wheeler only. | Needs rate (owned)
TB-STACK-4x12 | Utilities & trenching | Trench box / shield | Steel | 4 ft stacker 4x12 | Height x length | 4x12 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 119 | 344 | 997 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Depth rating not sourced. Required at 5 ft+ depth, 18 in above grade (URI page). Rent: Wheeler only. | Needs rate (owned)
TB-STACK-4x24 | Utilities & trenching | Trench box / shield | Steel | 4 ft stacker 4x24 | Height x length | 4x24 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 185 | 537 | 1556 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Depth rating not sourced. Required at 5 ft+ depth, 18 in above grade (URI page). Rent: Wheeler only. | Needs rate (owned)
TB-MH-8x8 | Utilities & trenching | Trench box / shield | Manhole box | Manhole box 8x8 | Height x length | 8x8 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 134 | 388 | 1126 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Depth rating not sourced. Required at 5 ft+ depth, 18 in above grade (URI page). Rent: Wheeler only. | Needs rate (owned)
TB-MH-10x10 | Utilities & trenching | Trench box / shield | Manhole box | Manhole box 10x10 | Height x length | 10x10 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 185 | 538 | 1559 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Depth rating not sourced. Required at 5 ft+ depth, 18 in above grade (URI page). Rent: Wheeler only. | Needs rate (owned)
TB-ALU-6x6 | Utilities & trenching | Trench box / shield | Aluminum | Aluminum trench shield 6x6 | Height x length | 6x6 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 162 | 470 | 1363 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Depth rating not sourced. Required at 5 ft+ depth, 18 in above grade (URI page). Rent: Wheeler only. | Needs rate (owned)
TB-ALU-8x12 | Utilities & trenching | Trench box / shield | Aluminum | Aluminum trench shield 8x12 | Height x length | 8x12 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 224 | 651 | 1887 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Depth rating not sourced. Required at 5 ft+ depth, 18 in above grade (URI page). Rent: Wheeler only. | Needs rate (owned)
TB-ALU-4x7 | Utilities & trenching | Trench box / shield | Aluminum | Aluminum trench box 4x7 | Height x length | 4x7 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 110 | 330 | 990 |  |  | bare |  |  | B25 | Mar 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | UT-SHORING-DUR | Rent: Burris only. | Needs rate (owned)
PLATE-5x10 | Utilities & trenching | Road plate / trench cover | Steel | Steel trench plate 5x10 | Size | 5x10 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 21 | 61 | 178 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Rent: Wheeler only; thickness not stated. | Needs rate (owned)
PLATE-8x12 | Utilities & trenching | Road plate / trench cover | Steel | Steel trench plate 8x12 | Size | 8x12 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 39 | 114 | 330 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Rent: Wheeler only; thickness not stated. | Needs rate (owned)
PLATE-8x20 | Utilities & trenching | Road plate / trench cover | Steel | Steel trench plate 8x20 | Size | 8x20 | ft | [5 empty] | none | None (non-operated item) | day/wk/4wk | 64 | 186 | 541 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Rent: Wheeler only; thickness not stated. | Needs rate (owned)
SHORE-HYD | Utilities & trenching | Shoring | Hydraulic vertical shores / manhole braces | Hydraulic vertical shores / manhole braces | Type | [7 empty] | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Category from URI; no rates or size classes. | Needs rate; Needs rate (rental); Needs rate (owned)
SHORE-SLIDERAIL | Utilities & trenching | Shoring | Slide-rail system | Slide-rail system | Type | [7 empty] | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Category from URI; no rates or size classes. | Needs rate; Needs rate (rental); Needs rate (owned)
SHORE-ARCH | Utilities & trenching | Shoring | Arch spreaders | Arch spreaders (22-120 in) | Type | [7 empty] | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | UT-SHORING-DUR | Category from URI; no rates or size classes. | Needs rate; Needs rate (rental); Needs rate (owned)
FD-VIBRO-EXC | Foundations & piling | Vibratory hammer | Excavator-mounted | Movax SP-60 sheet pile driver (28-32 t head, 178 hp) | Head class | 30 | ton | Movax SP-60 |  | 178 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8672 |  |  | 3.03 | 3.98 | 5.19 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HAMMR factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | FD-SHEET | Carrier excavator priced separately. FEMA 8672: Rate not captured. Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
FD-VIBRO-NF-S | Foundations & piling | Vibratory hammer | Crane-suspended | Normal-frequency vibro, small (ICE 55NF class) | Eccentric moment | 14 | kg-m | ICE 55NF class |  |  |  |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HAMMR factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | FD-SHEET,FD-PILE-DRIVE | Dieseko range 14-500 kgm, 1,400-1,700 rpm. Power pack and crane priced separately. | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
FD-VIBRO-NF-M | Foundations & piling | Vibratory hammer | Crane-suspended | Normal-frequency vibro, medium (ICE 170NF / PVE 150M class) | Eccentric moment | 150 | kg-m | ICE 170NF / PVE 150M class |  |  |  |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HAMMR factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | FD-SHEET,FD-PILE-DRIVE | Dieseko range 14-500 kgm, 1,400-1,700 rpm. Power pack and crane priced separately. | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
FD-VIBRO-NF-L | Foundations & piling | Vibratory hammer | Crane-suspended | Normal-frequency vibro, large (PVE 500MU class) | Eccentric moment | 500 | kg-m | PVE 500MU class |  |  |  |  | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HAMMR factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | FD-SHEET,FD-PILE-DRIVE | Dieseko range 14-500 kgm, 1,400-1,700 rpm. Power pack and crane priced separately. | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
FD-HAMMER-DIESEL | Foundations & piling | Impact pile hammer | Diesel impact hammer | Diesel impact hammer | Rated energy |  | ft-lb | [5 empty] | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HAMMR factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | FD-PILE-DRIVE | No energy-class breakpoints sourced. | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
FD-HAMMER-HYD | Foundations & piling | Impact pile hammer | Hydraulic impact hammer | Hydraulic impact hammer | Rated energy |  | ft-lb | [5 empty] | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HAMMR factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | FD-PILE-DRIVE | No energy-class breakpoints sourced. | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
FD-HAMMER-AIR | Foundations & piling | Impact pile hammer | Air/steam | Air/steam (drop) hammer (ram 500-50,000 lb) | Rated energy |  | ft-lb | [5 empty] | diesel | Operating Engineer - crane group (per WD); oiler if required | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HAMMR factor 0.21. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | FD-PILE-DRIVE | No energy-class breakpoints sourced. | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
FD-LEADS-FIX-24 | Foundations & piling | Pile leads | Fixed | Fixed leads 0-24 ft | Lead height (max) | 24 | ft | Caltrans LEADS band |  |  |  | 24 | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LEADS factor 0.45. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | FD-PILE-DRIVE |  | Needs rate; Needs rate (rental); Needs rate (owned)
FD-LEADS-FIX-49 | Foundations & piling | Pile leads | Fixed | Fixed leads 25-49 ft | Lead height (max) | 49 | ft | Caltrans LEADS band |  |  |  | 49 | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LEADS factor 0.45. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | FD-PILE-DRIVE |  | Needs rate; Needs rate (rental); Needs rate (owned)
FD-LEADS-FIX-74 | Foundations & piling | Pile leads | Fixed | Fixed leads 50-74 ft | Lead height (max) | 74 | ft | Caltrans LEADS band |  |  |  | 74 | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LEADS factor 0.45. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | FD-PILE-DRIVE |  | Needs rate; Needs rate (rental); Needs rate (owned)
FD-LEADS-SW-20 | Foundations & piling | Pile leads | Swinging | Swinging leads 0-20 ft | Lead height (max) | 20 | ft | Caltrans LEADS band |  |  |  | 20 | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LEADS factor 0.45. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | FD-PILE-DRIVE |  | Needs rate; Needs rate (rental); Needs rate (owned)
FD-LEADS-SW-30 | Foundations & piling | Pile leads | Swinging | Swinging leads 21-30 ft | Lead height (max) | 30 | ft | Caltrans LEADS band |  |  |  | 30 | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LEADS factor 0.45. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | FD-PILE-DRIVE |  | Needs rate; Needs rate (rental); Needs rate (owned)
FD-LEADS-SW-50 | Foundations & piling | Pile leads | Swinging | Swinging leads 31-50 ft | Lead height (max) | 50 | ft | Caltrans LEADS band |  |  |  | 50 | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: LEADS factor 0.45. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | FD-PILE-DRIVE |  | Needs rate; Needs rate (rental); Needs rate (owned)
FD-DRILL-KELLY | Foundations & piling | Drill rig (drilled shaft) | Kelly / caisson rig | Drilled shaft rig (class not sourced) | Torque |  | ft-lb | [5 empty] | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy |  |  | Y | 1913 | 1913 | FD-SHAFT-SOIL,FD-SHAFT-ROCK |  | Needs rate; Needs rate (rental); Needs rate (owned); Needs fuel gal/hr
FD-AUGER-TRK-24 | Foundations & piling | Auger (truck-mounted) | Truck-mounted auger | 24 in truck-mounted auger (with drop hammer) | Auger diameter | 24 | in | FEMA 8063 |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8063 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8063: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
FD-POSTDRIVER | Foundations & piling | Post driver | Hydraulic | Hydraulic post driver | Type | post |  | FEMA 8064 |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8064 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8064: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
AUG-8060 | Foundations & piling | Earth auger | One-man wheel-mount | One-man wheel-mount auger 16 in | Auger diameter | 16 | in | [5 empty] | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8060 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8060: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
AUG-8061 | Foundations & piling | Earth auger | Portable earth | Portable earth auger 18 in | Auger diameter | 18 | in | [5 empty] | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8061 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8061: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
AUG-8062 | Foundations & piling | Earth auger | Tractor-mounted TLB | Tractor-mounted TLB auger 36 in | Auger diameter | 36 | in | [5 empty] | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8062 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8062: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
DM-UHD-330 | Demolition & attachments | High-reach demolition excavator (UHD) | Ultra-high demolition | 330 UHD (66.8 ft pin) | Max pin height | 66.8 | ft | Cat 330 UHD | 101400 |  |  | 66.8 | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 101400 |  | Y | 1913 | 1913 | DM-BLDG |  | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
DM-UHD-340 | Demolition & attachments | High-reach demolition excavator (UHD) | Ultra-high demolition | 340 UHD (72.2 ft pin) | Max pin height | 72.2 | ft | Cat 340 UHD | 122600 |  |  | 72.2 | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 122600 |  | Y | 1913 | 1913 | DM-BLDG |  | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
DM-UHD-352 | Demolition & attachments | High-reach demolition excavator (UHD) | Ultra-high demolition | 352 UHD (90.8 ft pin) | Max pin height | 90.8 | ft | Cat 352 UHD | 142200 |  |  | 90.8 | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 142200 |  | Y | 1913 | 1913 | DM-BLDG |  | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
DM-SB-340 | Demolition & attachments | Demolition excavator, straight boom | Straight boom | 340 Straight Boom (39.4 ft) | Operating weight | 87800 | lb | Cat 340 Straight Boom | 87800 |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted | 87800 |  | Y | 1800 | 1800 | DM-BLDG |  | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
DM-SB-352 | Demolition & attachments | Demolition excavator, straight boom | Straight boom | 352 Straight Boom (42.2 ft) | Operating weight | 121000 | lb | Cat 352 Straight Boom | 121000 |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: HCECL factor 0.17. Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy | 121000 |  | Y | 1913 | 1913 | DM-BLDG |  | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned)
DM-ROBOT | Demolition & attachments | Demolition robot | Remote | Demolition robot (Brokk/Husqvarna type) | Machine weight |  | lb | [5 empty] | electric | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 |  | Unsourced category. | Needs rate; Needs rate (rental); Needs rate (owned)
AT-BRK-MINI | Demolition & attachments | Attachment | Hydraulic breaker | Hydraulic breaker, mini-ex/SSL (~500-1,000 ft-lb) | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 303 | 833 | 2375 | 1665 | 3303 | bare |  |  | W25;B25;C25;A26;N25;R25 | 2025-2026 | A |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | DM-PAVE-CONC | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 6 sources (W 393/1139/3303; B 280/840/2520; C 325/775/1900; A 338/1025/2375; N 190/665/1665; R 205/825/2375). | Needs rate (owned)
AT-BRK-BH | Demolition & attachments | Attachment | Hydraulic breaker | Hydraulic breaker, backhoe | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 589 | 1708 | 4995 |  |  | bare |  |  | W25 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | DM-PAVE-CONC | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Wheeler only. | Needs rate (owned)
AT-BRK-13T | Demolition & attachments | Attachment | Hydraulic breaker for 13-17 t excavator | Hydraulic breaker for 13-17 t excavator (MB-1000) | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 800 | 1975 | 4900 |  |  | bare |  |  | C25 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | DM-PAVE-CONC | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Columbus MB-1000 (PC138/170) only. | Needs rate (owned)
AT-BRK-20T | Demolition & attachments | Attachment | Hydraulic breaker for 20-30 t excavator | Hydraulic breaker for 20-30 t excavator | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 1050 | 2575 | 6400 | 5500 | 10440 | bare |  |  | W25;C25;A26 | 2025-2026 | A |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | DM-PAVE-CONC | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Median of 3 sources (W 1241/3600/10440; C 1050/2575/6400; A 5-6K lb 800/2000/5500). Carrier priced separately. | Needs rate (owned)
AT-BRK-36T | Demolition & attachments | Attachment | Hydraulic breaker for ~36 t excavator | Hydraulic breaker for ~36 t excavator (HB-3100) | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 1600 | 3975 | 9900 |  |  | bare |  |  | C25 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | DM-PAVE-CONC | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Columbus HB-3100 (PC360) only. | Needs rate (owned)
AT-BRK-10KLB | Demolition & attachments | Attachment | Hydraulic breaker ~10 | Hydraulic breaker ~10,000 lb hammer | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 900 | 3200 | 8500 |  |  | bare |  |  | A26 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | DM-PAVE-CONC | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Ahearn only. | Needs rate (owned)
AT-BRK-15KLB | Demolition & attachments | Attachment | Hydraulic breaker ~15 | Hydraulic breaker ~15,000 lb hammer | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 2000 | 4000 | 13000 |  |  | bare |  |  | A26 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | DM-PAVE-CONC | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Ahearn only. | Needs rate (owned)
AT-AUGER-SSL | Demolition & attachments | Attachment | Skid-steer auger drive | Skid-steer auger drive (bits extra) | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 137 | 393 | 913 | 745 | 1825 | bare |  |  | W25;R25;A26;N25 | 2025-2026 | A |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 4 sources (W 98/285/826; R 175/625/1825; A 250/500/1000; N 80/280/745). RTL bit $50/225/975 each. | Needs rate (owned)
AT-AUGER-MINI | Demolition & attachments | Attachment | Mini-ex auger with 1 bit | Mini-ex auger with 1 bit | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 110 | 319 | 924 |  |  | bare |  |  | W25 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Wheeler only. | Needs rate (owned)
AT-GRAPPLE-SSL | Demolition & attachments | Attachment | Skid-steer grapple bucket | Skid-steer grapple bucket | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 163 | 441 | 1053 | 750 | 1995 | bare |  |  | W25;R25;A26;N25 | 2025-2026 | A |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 4 sources (W 131/381/1105; R 195/700/1995; A 200/500/1000; N 85/295/750). | Needs rate (owned)
AT-GRAPPLE-20T | Demolition & attachments | Attachment | Box grapple | Box grapple, 20-24 t excavator | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 400 | 975 | 2400 |  |  | bare |  |  | C25 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Columbus PC210/238 only. | Needs rate (owned)
AT-GRAPPLE-36T | Demolition & attachments | Attachment | Box grapple | Box grapple, ~36 t excavator | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 450 | 1100 | 2700 |  |  | bare |  |  | C25 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Columbus PC360 only. | Needs rate (owned)
AT-THUMB-MINI | Demolition & attachments | Attachment | Mini-ex thumb | Mini-ex thumb | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 105 | 315 | 945 |  |  | bare |  |  | B25 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Burris only. | Needs rate (owned)
AT-THUMB-30T | Demolition & attachments | Attachment | Excavator thumb | Excavator thumb (320-340) | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 242 | 701 | 2033 |  |  | bare |  |  | W25 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Wheeler only. | Needs rate (owned)
AT-COMPWHEEL-24 | Demolition & attachments | Attachment | 24 in compaction wheel | 24 in compaction wheel (13-24 t carrier) | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 300 | 750 | 1900 |  |  | bare |  |  | C25 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Columbus only. | Needs rate (owned)
AT-PLATECOMP-EXC | Demolition & attachments | Attachment | Excavator hydraulic plate compactor | Excavator hydraulic plate compactor | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 429 | 1177 | 3273 | 1750 | 4796 | bare |  |  | C25;W25 | 2025 | A |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Mean of 2 sources: C HC-350/HC-850 avg 287.5/700/1750 (HC-350 250/600/1500; HC-850 325/800/2000); W 570/1653/4796. Half-up rounding. | Needs rate (owned)
AT-DRUMCUTTER | Demolition & attachments | Attachment | Drum cutter | Drum cutter (ER-650) | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 900 | 2200 | 5500 |  |  | bare |  |  | C25 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Columbus only. | Needs rate (owned)
AT-TILTBUCKET-10K | Demolition & attachments | Attachment | Tilt grade bucket | Tilt grade bucket, 8-10K class | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 200 | 450 | 1000 |  |  | bare |  |  | A26 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Ahearn only. | Needs rate (owned)
AT-TILTBUCKET-20K | Demolition & attachments | Attachment | Tilt grade bucket | Tilt grade bucket, 20K+ class | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 325 | 950 | 2050 |  |  | bare |  |  | A26 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Ahearn only. | Needs rate (owned)
AT-FORKS-WL | Demolition & attachments | Attachment | Wheel-loader forks | Wheel-loader forks | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 64 | 186 | 540 |  |  | bare |  |  | W25 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Wheeler only. | Needs rate (owned)
AT-FORKS-SSL | Demolition & attachments | Attachment | SSL pallet forks | SSL pallet forks | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 75 | 295 | 895 |  |  | bare |  |  | R25 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: RTL only. | Needs rate (owned)
AT-GPS-DOZER | Demolition & attachments | Attachment | GPS/machine-control kit for dozer | GPS/machine-control kit for dozer | Type | attachment | [6 empty] | none (attachment) | None (non-operated item) | day/wk/4wk | 560 | 1670 | 5000 |  |  | bare |  |  | C25 | 2025-2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | Attachments are generally rented only with the vendor's carrier; carrier priced separately. Rent: Columbus only. | Needs rate (owned)
BRK-HAND-8419 | Demolition & attachments | Pneumatic hand breaker | Hand-held | Hand-held pavement breaker 25-30 lb | Tool weight | 25-30 | lb | [5 empty] | none (air) | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8419 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | Needs compressor (AIR rows). FEMA 8419: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
BRK-HAND-8420 | Demolition & attachments | Pneumatic hand breaker | Hand-held | Hand-held pavement breaker 80-90 lb | Tool weight | 80-90 | lb | [5 empty] | none (air) | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8420 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | Needs compressor (AIR rows). FEMA 8420: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
BRK-HAND-8517 | Demolition & attachments | Pneumatic hand breaker | Hand-held | Jackhammer dry 25 lb | Tool weight | 25 | lb | [5 empty] | none (air) | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8517 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | Needs compressor (AIR rows). FEMA 8517: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
BRK-HAND-8518 | Demolition & attachments | Pneumatic hand breaker | Hand-held | Jackhammer wet 30 lb | Tool weight | 30 | lb | [5 empty] | none (air) | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8518 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | Needs compressor (AIR rows). FEMA 8518: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
LC-CHIP-8201 | Land clearing & forestry | Brush chipper | Towed drum chipper | Brush chipper 12 in (Vermeer BC1000XL) | Capacity | 12 | in | Vermeer BC1000XL |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8201 | 24.74 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | EW-CLR-CHIP | Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
LC-CHIP-8202 | Land clearing & forestry | Brush chipper | Towed drum chipper | Brush chipper 15 in (Vermeer BC1500) | Capacity | 15 | in | Vermeer BC1500 |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8202 | 49.8 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | EW-CLR-CHIP | Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
LC-CHIP-8203 | Land clearing & forestry | Brush chipper | Towed drum chipper | Brush chipper 19 in (Vermeer BC1800XL) | Capacity | 19 | in | Vermeer BC1800XL |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8203 | 48.64 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | EW-CLR-CHIP | FEMA: 19 in rate below the 15 in rate. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged: 19 in below 15 in; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
LC-CHIP-8200 | Land clearing & forestry | Brush chipper | Towed | Vermeer BC900XL (~9 in) | Capacity | 9 | in | Vermeer BC900XL |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8200 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | EW-CLR-CHIP | FEMA 8200: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
LC-RECYCLER-2460 | Land clearing & forestry | Whole-tree chipper / recycler | Track | Bandit 2460T (560 hp) | Net HP | 560 | hp | Bandit 2460T |  | 560 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8823 | 167.84 | FEMA 2025 | 9.53 | 12.52 | 16.33 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 122.02 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 |  | Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
LC-GRIND-8621 | Land clearing & forestry | Grinder | Tub/horizontal | Tub grinder up to 40 t/hr (Morbark 1000) | Throughput | 40 | t/hr | Morbark 1000 |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8621 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 |  | FEMA 8621: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
LC-GRIND-8622 | Land clearing & forestry | Grinder | Tub/horizontal | Tub grinder up to 80 t/hr (Morbark 1300) | Throughput | 80 | t/hr | Morbark 1300 |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8622 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 |  | FEMA 8622: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
LC-GRIND-8623 | Land clearing & forestry | Grinder | Tub/horizontal | Tub grinder up to 190 t/hr (Morbark 1600) | Throughput | 190 | t/hr | Morbark 1600 |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8623 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 |  | FEMA 8623: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
LC-GRIND-8627 | Land clearing & forestry | Grinder | Tub/horizontal | Horizontal grinder (Vermeer HG6000) | Model | HG6000 |  | Vermeer HG6000 |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8627 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-permitted |  |  | Y | 1800 | 1800 |  | FEMA 8627: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
LC-STUMP-23 | Land clearing & forestry | Stump grinder | Self-propelled | 23 in cutter wheel | Cutter wheel | 23 | in | Vermeer SC852 |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8628 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 |  | FEMA 8628: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
LC-STUMP-26 | Land clearing & forestry | Stump grinder | Self-propelled | 26 in cutter wheel | Cutter wheel | 26 | in | Vermeer SC1052 |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8629 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | tilt-trailer |  |  | N | 500 | 500 |  | FEMA 8629: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
LC-BUSHHOG-8068 | Land clearing & forestry | Rotary cutter (bush hog) | Tractor-towed | Bush hog 72 in | Cut width | 72 | in | [5 empty] | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8068 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8068: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
LC-BUSHHOG-8069 | Land clearing & forestry | Rotary cutter (bush hog) | Tractor-towed | Bush hog 12 ft | Cut width | 12 | ft | [5 empty] | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8069 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8069: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
LC-BUSHHOG-8069-1 | Land clearing & forestry | Rotary cutter (bush hog) | Tractor-towed | Bush hog 85 in | Cut width | 85 | in | [5 empty] | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8069.1 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 |  | FEMA 8069.1: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
LC-MULCH-D1 | Land clearing & forestry | Mulching dozer | Dedicated mulcher | Cat D1 Mulcher (104 hp) | Net HP | 104 | hp | Cat D1 Mulcher |  | 104 |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 1.77 | 2.33 | 3.03 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 |  | Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). | Needs rate; Needs rate (rental); Needs rate (owned)
LC-8195 | Land clearing & forestry | Wheel mulcher | Forestry | Wheel mulcher (Barko 930B) | FEMA code | 8195 |  | Wheel mulcher (Barko 930B) |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8195 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 |  | FEMA 8195: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
LC-8198 | Land clearing & forestry | Feller buncher | Forestry | Feller buncher (Cat 511) | FEMA code | 8198 |  | Feller buncher (Cat 511) |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8198 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 |  | FEMA 8198: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
LC-8824 | Land clearing & forestry | Log skidder | Forestry | Log skidder 237 hp | FEMA code | 8824 |  | Log skidder 237 hp |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8824 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 |  | FEMA 8824: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
LC-8825 | Land clearing & forestry | Log skidder | Forestry | Log skidder 300 hp | FEMA code | 8825 |  | Log skidder 300 hp |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8825 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 |  | FEMA 8825: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
LC-8654 | Land clearing & forestry | Air curtain destructor / trench burner | Forestry | Air curtain destructor / trench burner | FEMA code | 8654 |  | Air curtain destructor / trench burner |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8654 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 |  | FEMA 8654: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
AIR-41 | Air & power | Air compressor | Tank-mounted | 41 CFM | Free air delivery | 41 | CFM @100 psi |  |  |  | 41 CFM |  | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8010 | 1.8 | FEMA 2025 | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) | 1.8 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: AIRCP factor 0.14 (book) / 0.13 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-AIR-DUR | Duration-priced (tie to the tool-using activity). No compressor gal/hr in notes; HP not captured so HP method not applicable. FEMA: Tank-mounted. Ex-fuel = incl-fuel rate (no liquid fuel to back out). | Needs rate (rental)
AIR-100 | Air & power | Air compressor | Towable | 103 CFM | Free air delivery | 103 | CFM @100 psi |  |  |  | 103 CFM |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8011 | 20.23 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: AIRCP factor 0.14 (book) / 0.13 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-AIR-DUR | Duration-priced (tie to the tool-using activity). No compressor gal/hr in notes; HP not captured so HP method not applicable. FEMA: Multiquip DIS100SSK4F. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
AIR-130 | Air & power | Air compressor | Towable | 130 CFM | Free air delivery | 130 | CFM @100 psi |  |  |  | 130 CFM |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8012 | 27.71 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: AIRCP factor 0.14 (book) / 0.13 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-AIR-DUR | Duration-priced (tie to the tool-using activity). No compressor gal/hr in notes; HP not captured so HP method not applicable. FEMA: 130 CFM ($27.71) above 175 CFM ($26.29). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; FEMA value flagged; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
AIR-185 | Air & power | Air compressor | Towable | 185 CFM | Free air delivery | 185 | CFM @100 psi |  |  |  | 185 CFM |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 133 | 423 | 1145 | 816 | 2255 | bare |  |  | W25;B25;N25;RENTD | 2025-2026 | A | 8013 | 26.29 | FEMA 2025 | 1.4 | 1.68 | 2.8 | Sullair 185 (Cat) 2.8; Kubota 2.7; Doosan P185 ~2.8 derived gal/hr at full load = high; med = 0.60 x full and low = 0.50 x full (assumed 50-70% jobsite load, not published) [COMP-SHEETS] | 20.14 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: AIRCP factor 0.14 (book) / 0.13 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-AIR-DUR | Duration-priced (tie to the tool-using activity). No compressor gal/hr in notes; HP not captured so HP method not applicable. Rounded half-up (Excel rule) in revision; may differ by 1 from the notes table, which used banker's rounding. Rent: Median of 4 sources (W 268/778/2255; B 160/480/1440; N 105/365/850; rentd mid 90/308/816). FEMA 8013 is 175 CFM. FEMA: Grimmer-Schmidt 175 CFM mapped to 185 class. Fuel (C): full-load 2.8 gal/hr x Settings B31-B33 load fractions. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
AIR-375 | Air & power | Air compressor | Towable | 400 CFM | Free air delivery | 400 | CFM @100 psi |  |  |  | 400 CFM |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 227 | 721 | 2046 | 1450 | 3378 | bare |  |  | W25;B25;N25;RENTD | 2025-2026 | A | 8014 | 58.41 | FEMA 2025 | 2.95 | 3.54 | 5.9 | Sullair 375H 5.9 (400HH 7.4; 425H 7.7) gal/hr at full load = high; med = 0.60 x full and low = 0.50 x full (assumed 50-70% jobsite load, not published) [COMP-SHEETS] | 45.45 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: AIRCP factor 0.14 (book) / 0.13 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-AIR-DUR | Duration-priced (tie to the tool-using activity). No compressor gal/hr in notes; HP not captured so HP method not applicable. Rent: Median of 4 sources (W 375/1126/3378; B 260/780/2340; N 165/575/1450; rentd mid 194/662/1752). FEMA: Sullivan-Palatek D375 (400 CFM). Fuel (C): full-load 5.9 gal/hr x Settings B31-B33 load fractions. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
AIR-575 | Air & power | Air compressor | Towable | 575 CFM | Free air delivery | 575 | CFM @100 psi |  |  |  | 575 CFM |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8015 | 105.25 | FEMA 2025 | 5.38 | 6.45 | 10.75 | Derived (C): linear interpolation by free air delivery between AIR-375 and AIR-750 (spec-sheet endpoints) [GEN-SHEETS; COMP-SHEETS] | 81.64 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: AIRCP factor 0.14 (book) / 0.13 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-AIR-DUR | Duration-priced (tie to the tool-using activity). No compressor gal/hr in notes; HP not captured so HP method not applicable. Fuel interpolated between AIR-375 and AIR-750; the 750 CFM datum is a 350 psi high-pressure unit (XHP750), so this likely overstates. FEMA: Grimmer-Schmidt 800 (575 CFM). Fuel gal/hr interpolated (C) between AIR-375 and AIR-750 by Spec_value. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
AIR-750 | Air & power | Air compressor | Towable | 750 CFM | Free air delivery | 750 | CFM @100 psi |  |  |  | 750 CFM |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 297 | 1016 | 2688 | 2219 | 3157 | bare |  |  | RENTD | Jul 2026 | B |  |  |  | 7.8 | 9.36 | 15.6 | Doosan XHP750 (350 psi, high-pressure) 15.6 gal/hr at full load = high; med = 0.60 x full and low = 0.50 x full (assumed 50-70% jobsite load, not published) [COMP-SHEETS] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: AIRCP factor 0.14 (book) / 0.13 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-AIR-DUR | Duration-priced (tie to the tool-using activity). No compressor gal/hr in notes; HP not captured so HP method not applicable. Rent: rentd 750 CFM range midpoint only. Dealer 860-900 CFM (AIR-900) is >2x higher; see notes conflict. Fuel (C): full-load 15.6 gal/hr x Settings B31-B33 load fractions. | Needs rate (owned)
AIR-900 | Air & power | Air compressor | Towable | 880 CFM | Free air delivery | 880 | CFM @100 psi |  |  |  | 880 CFM |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 723 | 2169 | 6505 | 6300 | 6710 | bare |  |  | W25;B25 | 2025-2026 | A |  |  |  | 12 | 14.4 | 24 | Sullair 900XHH (500 psi) 24 gal/hr at full load = high; med = 0.60 x full and low = 0.50 x full (assumed 50-70% jobsite load, not published) [COMP-SHEETS] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: AIRCP factor 0.14 (book) / 0.13 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-AIR-DUR | Duration-priced (tie to the tool-using activity). No compressor gal/hr in notes; HP not captured so HP method not applicable. Rent: Median (=mean) of 2 dealer sources: W 860 CFM 746/2237/6710; B 900 CFM 700/2100/6300. Notes recommend these over rentd's 750 CFM figure. Fuel (C): full-load 24.0 gal/hr x Settings B31-B33 load fractions. | Needs rate (owned)
AIR-1000 | Air & power | Air compressor | Towable | 1,000 CFM | Free air delivery | 1000 | CFM @100 psi |  |  |  | 1,000 CFM |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 1184 | 3552 | 10655 |  |  | bare |  |  | W25 | 2025 | B | 8016 | 187.83 | FEMA 2025 | 12.2 | 14.64 | 24.4 | mean of Doosan XHP1170 24.3 and Sullair 1150XH 24.5 (1,150-1,170 CFM units mapped to the 1,000-1,100 CFM class) gal/hr at full load = high; med = 0.60 x full and low = 0.50 x full (assumed 50-70% jobsite load, not published) [COMP-SHEETS] | 134.25 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: AIRCP factor 0.14 (book) / 0.13 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | SP-AIR-DUR | Duration-priced (tie to the tool-using activity). No compressor gal/hr in notes; HP not captured so HP method not applicable. Rent: Wheeler only. FEMA: Ingersoll Rand XP1200 (1,100 CFM). Fuel (C): full-load 24.4 gal/hr x Settings B31-B33 load fractions. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
AIR-1400 | Air & power | Air compressor | Towable | 1,426 CFM | Free air delivery | 1426 | CFM @100 psi |  |  |  | 1,426 CFM |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 1421 | 4262 | 12786 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 12.06 | 14.47 | 24.12 | Derived (C): linear interpolation by free air delivery between AIR-1000 and AIR-1600 (spec-sheet endpoints) [GEN-SHEETS; COMP-SHEETS] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: AIRCP factor 0.14 (book) / 0.13 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | SP-AIR-DUR | Duration-priced (tie to the tool-using activity). No compressor gal/hr in notes; HP not captured so HP method not applicable. Rent: Wheeler only. Fuel gal/hr interpolated (C) between AIR-1000 and AIR-1600 by Spec_value. | Non-monotonic vs AIR-1600 - source data; Needs rate (owned)
AIR-1600 | Air & power | Air compressor | Towable | 1,600 CFM | Free air delivery | 1600 | CFM @100 psi |  |  |  | 1,600 CFM |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 386 | 1319 | 3491 | 2992 | 3990 | bare |  |  | RENTD | Jul 2026 | B | 8017 | 200.97 | FEMA 2025 | 12 | 14.4 | 24 | Sullair 1600H 24; Doosan HP1600 ~23-25 derived gal/hr at full load = high; med = 0.60 x full and low = 0.50 x full (assumed 50-70% jobsite load, not published) [COMP-SHEETS] | 148.27 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: AIRCP factor 0.14 (book) / 0.13 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | SP-AIR-DUR | Duration-priced (tie to the tool-using activity). No compressor gal/hr in notes; HP not captured so HP method not applicable. Rent: rentd 1,600 CFM range midpoint only (marketplace; likely understates vs dealer). FEMA: Sullair 1600. Fuel (C): full-load 24.0 gal/hr x Settings B31-B33 load fractions. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
GEN-5_5 | Air & power | Generator | Towable | 5.5 kW | Prime output | 5.5 | kW |  |  |  | 5.5 kW |  | gas | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8310 | 4.1 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | Needs fuel gal/hr; Needs rate (rental)
GEN-17 | Air & power | Generator | Towable | 17 kW | Prime output | 17 | kW |  |  |  | 17 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8311 | 8.81 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. FEMA: 17-45 kW FEMA rows are not monotonic. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged (non-monotonic 17-45 kW); Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
GEN-25 | Air & power | Generator | Towable | 25 kW | Prime output | 25 | kW |  |  |  | 25 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 185 | 554 | 1634 | 1075 | 1665 | bare |  |  | W25;B25;N25 | 2025-2026 | A | 8312 | 31.23 | FEMA 2025 | 0.7 | 1 | 1.4 | Atlas Copco QAS 25 (20 kW): low/med/high = 25/50/75% prime load (med = 50% is a load-factor choice); 100% = 1.6 [GEN-SHEETS] | 27.57 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Rent: Median of 3 sources for 20-25 kW (W 20/25 avg 188/554/1634; B 20 kW 185/555/1665; N 115/345/1075). B on 10/50/200 hr basis. FEMA: 17-45 kW FEMA rows are not monotonic. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged (non-monotonic 17-45 kW); FEMA ⚠ value kept as published; verify vs PDF
GEN-40 | Air & power | Generator | Towable | 40 kW | Prime output | 40 | kW |  |  |  | 40 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8313 | 30.53 | FEMA 2025 | 1.2 | 1.8 | 2.15 | Atlas Copco QAS 45 (36 kW): low/med/high = 25/50/75% prime load (med = 50% is a load-factor choice); 100% = 2.76 [GEN-SHEETS] | 23.94 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. FEMA: 17-45 kW FEMA rows are not monotonic. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged (non-monotonic 17-45 kW); Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
GEN-45 | Air & power | Generator | Towable | 45 kW | Prime output | 45 | kW |  |  |  | 45 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 259 | 752 | 2179 | 1865 | 2610 | bare |  |  | W25;B25;N25 | 2025-2026 | A | 8314 | 12.52 | FEMA 2025 |  | 1.97 | 2.45 | Derived (C): linear interpolation by prime output between GEN-40 and GEN-80 (spec-sheet endpoints) [GEN-SHEETS; COMP-SHEETS] | 5.31 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Rent: Median of 3 sources for 45-70 kW (W 45/56-70 avg 259/752/2179; B 58 kW 290/870/2610; N 64 kW 195/650/1865). FEMA: 17-45 kW FEMA rows are not monotonic. Fuel gal/hr interpolated (C) between GEN-40 and GEN-80 by Spec_value. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged (non-monotonic 17-45 kW); FEMA ⚠ value kept as published; verify vs PDF
GEN-80 | Air & power | Generator | Towable | 80 kW | Prime output | 80 | kW |  |  |  | 80 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 395 | 1185 | 3555 |  |  | bare |  |  | B25 | Mar 2025 | B |  |  |  |  | 3.17 | 4.51 | Generac MDG100DF4 (80 kW): low/med/high = 25/50/75% prime load (med = 50% is a load-factor choice); 100% = 6.01 [GEN-SHEETS] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Rent: Burris 80 kW only (10/50/200 hr basis). Fuel low (25% load) not published for this model; left blank. | Needs rate (owned)
GEN-100 | Air & power | Generator | Towable | 100 kW | Prime output | 100 | kW |  |  |  | 100 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 506 | 1518 | 4554 |  |  | bare |  |  | W25 | 2025 | B | 8315 | 60.69 | FEMA 2025 |  | 4.08 | 5.62 | Derived (C): linear interpolation by prime output between GEN-80 and GEN-125 (spec-sheet endpoints) [GEN-SHEETS; COMP-SHEETS] | 45.76 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Rent: Wheeler only. Fuel gal/hr interpolated (C) between GEN-80 and GEN-125 by Spec_value. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
GEN-125 | Air & power | Generator | Towable | 125 kW | Prime output | 125 | kW |  |  |  | 125 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 569 | 1649 | 4782 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 3.6 | 5.225 | 7 | mean of Generac MDG150DF4 (3.4/5.25/7.1/8.7) and Atlas Copco QAS 150 (3.8/5.2/6.9/8.2), both 120 kW: low/med/high = 25/50/75% prime load (med = 50% is a load-factor choice); 100% = 8.45 [GEN-SHEETS] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Rent: Wheeler only. | Needs rate (owned)
GEN-150 | Air & power | Generator | Towable | 150 kW | Prime output | 150 | kW |  |  |  | 150 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 629 | 1849 | 5436 |  |  | bare |  |  | W25 | 2025 | C | 8316 | 84.66 | FEMA 2025 | 4.6 | 6.4 | 8.2 | Atlas Copco QAS 200 (160 kW): low/med/high = 25/50/75% prime load (med = 50% is a load-factor choice); 100% = 10.9 [GEN-SHEETS] | 61.24 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Rent day/week/4wk interpolated (C) between GEN-125 and GEN-200 by Spec_value. Wheeler has no 150 kW line (144 kW 623/1954/5863 and 184 kW 727/2182/6546 exist). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
GEN-200 | Air & power | Generator | Towable | 200 kW | Prime output | 200 | kW |  |  |  | 200 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 749 | 2248 | 6743 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 4.4 | 7.2 | 10.4 | Generac MDG250DF4 (200 kW): low/med/high = 25/50/75% prime load (med = 50% is a load-factor choice); 100% = 13.9 [GEN-SHEETS] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Rent: Wheeler only. | Needs rate (owned)
GEN-225 | Air & power | Generator | Towable | 225 kW | Prime output | 225 | kW |  |  |  | 225 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8317 | 117.25 | FEMA 2025 | 4.65 | 7.8 | 11.15 | Derived (C): linear interpolation by prime output between GEN-200 and GEN-300 (spec-sheet endpoints) [GEN-SHEETS; COMP-SHEETS] | 88.7 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Fuel gal/hr interpolated (C) between GEN-200 and GEN-300 by Spec_value. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
GEN-300 | Air & power | Generator | Towable | 300 kW | Prime output | 300 | kW |  |  |  | 300 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 1050 | 3150 | 9450 |  |  | bare |  |  | W25 | 2025 | B | 8318 | 154.14 | FEMA 2025 | 5.4 | 9.6 | 13.4 | Atlas Copco QAS 330 (264 kW): low/med/high = 25/50/75% prime load (med = 50% is a load-factor choice); 100% = 18.4 [GEN-SHEETS] | 119 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Rent: Wheeler only. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
GEN-350 | Air & power | Generator | Towable | 350 kW | Prime output | 350 | kW |  |  |  | 350 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8319 | 172.74 | FEMA 2025 |  | 11.77 | 16.49 | Derived (C): linear interpolation by prime output between GEN-300 and GEN-500 (spec-sheet endpoints) [GEN-SHEETS; COMP-SHEETS] | 129.66 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Fuel gal/hr interpolated (C) between GEN-300 and GEN-500 by Spec_value. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
GEN-400 | Air & power | Generator | Towable | 400 kW | Prime output | 400 | kW |  |  |  | 400 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 1290 | 3871 | 11613 |  |  | bare |  |  | W25 | 2025 | B | 8320 | 175.49 | FEMA 2025 |  | 13.95 | 19.57 | Derived (C): linear interpolation by prime output between GEN-300 and GEN-500 (spec-sheet endpoints) [GEN-SHEETS; COMP-SHEETS] | 124.43 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Rent: Wheeler only. Fuel gal/hr interpolated (C) between GEN-300 and GEN-500 by Spec_value. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5).
GEN-455 | Air & power | Generator | Towable | 455 kW | Prime output | 455 | kW |  |  |  | 455 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 1488 | 4463 | 13389 |  |  | bare |  |  | W25 | 2025 | B |  |  |  |  | 16.33 | 22.96 | Derived (C): linear interpolation by prime output between GEN-300 and GEN-500 (spec-sheet endpoints) [GEN-SHEETS; COMP-SHEETS] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Rent: Wheeler only. Fuel gal/hr interpolated (C) between GEN-300 and GEN-500 by Spec_value. | Needs rate (owned)
GEN-500 | Air & power | Generator | Towable | 500 kW | Prime output | 500 | kW |  |  |  | 500 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8321 | 296.15 | FEMA 2025 |  | 18.29 | 25.74 | Atlas Copco QAS 625 VD (500 kW): low/med/high = 25/50/75% prime load (med = 50% is a load-factor choice); 100% = 33.54 [GEN-SHEETS] | 229.21 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | flatbed |  |  | N | 400 | 400 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Fuel low (25% load) not published for this model; left blank. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
GEN-700 | Air & power | Generator | Large (containerized/skid) | 700 kW | Prime output | 700 | kW |  |  |  | 700 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8322 | 386.08 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
GEN-800 | Air & power | Generator | Large (containerized/skid) | 800 kW | Prime output | 800 | kW |  |  |  | 800 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8323 | 431.25 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
GEN-900 | Air & power | Generator | Large (containerized/skid) | 900 kW | Prime output | 900 | kW |  |  |  | 900 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8324 | 542.81 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
GEN-1000 | Air & power | Generator | Large (containerized/skid) | 1000 kW | Prime output | 1000 | kW |  |  |  | 1000 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8325 | 654.36 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
GEN-1150 | Air & power | Generator | Large (containerized/skid) | 1150 kW | Prime output | 1150 | kW | Cat XQC1200 |  |  | 1150 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8326 | 644.98 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
GEN-1500 | Air & power | Generator | Large (containerized/skid) | 1500 kW | Prime output | 1500 | kW |  |  |  | 1500 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8327 | 698.66 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
GEN-2000 | Air & power | Generator | Large (containerized/skid) | 2000 kW | Prime output | 2000 | kW |  |  |  | 2000 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | 4919 | 14756 | 44267 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Rent: Wheeler only. | Needs fuel gal/hr; Needs rate (owned)
GEN-2500 | Air & power | Generator | Large (containerized/skid) | 2500 kW | Prime output | 2500 | kW |  |  |  | 2500 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8328 | 801.68 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. 8328 fuel type not stated. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
GEN-3000 | Air & power | Generator | Large (containerized/skid) | 3000 kW | Prime output | 3000 | kW | Cummins QSK95 |  |  | 3000 kW |  | diesel | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8329 | 802.74 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | lowboy-legal |  |  | maybe | 550 | 550 | SP-GEN-DUR | Duration-priced; often 24/7 (3-shift) - check overtime basis. No generator gal/hr in notes (needs mfr load tables). Wheeler single-shift; double/triple shift extra. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
LT-4x1000 | Air & power | Light tower | Diesel, metal halide/LED | 4 x 1,000-1,250 W, 25-30 ft mast | Lamps | 4 | lamps | Generac MLT-type |  |  |  | 25 | diesel | None (non-operated item) | day/wk/4wk | 125 | 435 | 1095 | 630 | 1271 | bare |  |  | W25;B25;N25 | 2025-2026 | A |  |  |  |  | 0.61 |  | Allmand NLV metal halide 4x1,250 W ~0.60-0.62 gal/hr, derived from 45 gal tank / runtime [LT-SHEETS] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-LIGHT-DUR | Rent: Median of 3 sources (W 151/438/1271; B 105/315/630; N 125/435/1095). | Needs rate (owned)
LT-8KW | Air & power | Light tower | Diesel LED | 8 kW, 25 ft (13 hp) | Generator | 8 | kW | Generac MLT4080 LED |  | 13 |  | 25 | diesel | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8870 | 5.55 | FEMA 2025 | 0.2 | 0.335 | 0.6 | low = Generac MLT6SMDS lights-only 0.2; med = Allmand NLV LED midpoint 0.29-0.38; high = MLT6SMDS 100% 0.6 [LT-SHEETS] | 4.32 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-LIGHT-DUR | Fuel replaced in revision with light-tower spec sheets (was HP-derived). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
LT-20KW | Air & power | Light tower | Diesel | 20 kW, 25 ft (40 hp) | Generator | 20 | kW | Generac MLT4200 |  | 40 |  | 25 | diesel | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8871 | 8.66 | FEMA 2025 | 0.68 | 0.89 | 1.17 | Derived (C): Net_HP x 0.0486 diesel gal/bhp-hr x load factor 0.35/0.46/0.60 [USACE-EP] | 5.4 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: ELGEN factor 0.13 (book) / 0.12 (interim). Rental: accrues by calendar period (no idle discount). FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-LIGHT-DUR | Fuel gal/hr derived (C): Net_HP x USACE fuel factor x load factor (Settings B11-B15). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs rate (rental)
WELD-230 | Air & power | Welder | Engine-driven | 230 A (11 kW peak) | Output | 230 | A | [5 empty] | gas | Welder / trade using it | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8770 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-GEN-DUR | Welders above 300 A: no rental rates (gap). Florida Air Tool 500 A $80/day is 2019 (excluded). FEMA 8770: FEMA welder rates not reliably extracted. | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned; FEMA code exists)
WELD-250 | Air & power | Welder | Engine-driven | 250 A gas | Output | 250 | A | [5 empty] | gas | Welder / trade using it | day/wk/4wk | 65 | 220 | 550 |  |  | bare |  |  | N25 | Jan 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-GEN-DUR | Welders above 300 A: no rental rates (gap). Florida Air Tool 500 A $80/day is 2019 (excluded). Rent: Nu-Way only. | Needs fuel gal/hr; Needs rate (owned)
WELD-300 | Air & power | Welder | Engine-driven | 300 A diesel welder/generator | Output | 300 | A | [5 empty] | diesel | Welder / trade using it | day/wk/4wk | 95 | 335 | 850 |  |  | bare |  |  | N25 | Jan 2025 | B | 8771 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-GEN-DUR | Welders above 300 A: no rental rates (gap). Florida Air Tool 500 A $80/day is 2019 (excluded). Rent: Nu-Way only. FEMA 8771: FEMA rate not reliably extracted. | Needs fuel gal/hr; Needs rate (owned; FEMA code exists)
WELD-600 | Air & power | Welder | Engine-driven | 600 A | Output | 600 | A | [5 empty] | diesel | Welder / trade using it | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8772 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-GEN-DUR | Welders above 300 A: no rental rates (gap). Florida Air Tool 500 A $80/day is 2019 (excluded). FEMA 8772: FEMA rate not reliably extracted. | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned; FEMA code exists)
WELD-800 | Air & power | Welder | Engine-driven | 800 A | Output | 800 | A | [5 empty] | diesel | Welder / trade using it | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8773 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-GEN-DUR | Welders above 300 A: no rental rates (gap). Florida Air Tool 500 A $80/day is 2019 (excluded). FEMA 8773: FEMA rate not reliably extracted. | Needs rate; Needs fuel gal/hr; Needs rate (rental); Needs rate (owned; FEMA code exists)
HTR-FA-175K | Air & power | Construction heater | Forced-air | Forced-air 150-210k BTU (LP/kerosene) | Output | 150-210k | BTU/hr | [5 empty] | propane/diesel | None (non-operated item) | day/wk/4wk | 55 | 220 | 440 | 225 | 693 | bare |  |  | W25;B25;N25 | 2025-2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-HEAT-DUR | Fuel consumption not in notes (BTU-based burn needed). Rent: Median of 3 sources (W 82/239/693; B 55/220/440; N 30/95/225). | Needs fuel gal/hr; Needs rate (owned)
HTR-DF-400K | Air & power | Construction heater | Direct-fired | Direct-fired 400k BTU | Output | 400k | BTU/hr | [5 empty] | propane/diesel | None (non-operated item) | day/wk/4wk | 99 | 288 | 835 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-HEAT-DUR | Fuel consumption not in notes (BTU-based burn needed). Rent: Wheeler only. | Needs fuel gal/hr; Needs rate (owned)
HTR-IND-400K | Air & power | Construction heater | Indirect-fired | Indirect-fired ~400k BTU diesel | Output | ~400k | BTU/hr | [5 empty] | propane/diesel | None (non-operated item) | day/wk/4wk | 158 | 425 | 1309 | 1095 | 1523 | bare |  |  | W25;N25 | 2025-2026 | A | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-HEAT-DUR | Fuel consumption not in notes (BTU-based burn needed). Rent: Median (=mean) of 2 sources: W 181/525/1523; N 135/325/1095. | Needs fuel gal/hr; Needs rate (owned)
HTR-MUA-1M | Air & power | Construction heater | Make-up | Make-up air 1M BTU | Output | air | BTU/hr | [5 empty] | propane/diesel | None (non-operated item) | day/wk/4wk | 310 | 688 | 2048 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-HEAT-DUR | Fuel consumption not in notes (BTU-based burn needed). Rent: Wheeler only. | Needs fuel gal/hr; Needs rate (owned)
SANDBLAST | Air & power | Sandblaster | Pot blaster | Sandblasting equipment (Caltrans SANBL) | Type | [7 empty] | none (air) | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | Category only. | Needs rate; Needs rate (rental); Needs rate (owned)
PMP-TRASH-2 | Pumps & dewatering | Pump | trash, gas | 2 in trash, gas (~211 GPM) | Discharge size | 2 | in | [5 empty] | gas | Laborer (per WD group) | day/wk/4wk | 50 | 197 | 572 | 350 | 600 | bare |  |  | W25;B25;N25 | 2025-2026 | A | 8468 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. Rent: Median of 3 sources (W 68/197/572; B 50/200/600; N 40/140/350). FEMA 8468: FEMA diesel trash pump rates not reliably extracted. | Needs fuel gal/hr; Needs rate (owned; FEMA code exists)
PMP-TRASH-3 | Pumps & dewatering | Pump | trash, gas | 3 in trash, gas (~396 GPM) | Discharge size | 3 | in | [5 empty] | gas | Laborer (per WD group) | day/wk/4wk | 65 | 239 | 693 | 425 | 780 | bare |  |  | W25;B25;N25 | 2025-2026 | A | 8467 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. Rent: Median of 3 sources (W 82/239/693; B 65/260/780; N 45/165/425). FEMA 8467: FEMA rate not reliably extracted. | Needs fuel gal/hr; Needs rate (owned; FEMA code exists)
PMP-TRASH-4 | Pumps & dewatering | Pump | trash, gas | 4 in trash, gas (~555 GPM) | Discharge size | 4 | in | [5 empty] | gas | Laborer (per WD group) | day/wk/4wk | 80 | 279 | 809 | 525 | 960 | bare |  |  | W25;B25;N25 | 2025-2026 | A | 8466 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. Rent: Median of 3 sources (W 96/279/809; B 80/320/960; N 75/240/525). FEMA 8466: FEMA rate not reliably extracted. | Needs fuel gal/hr; Needs rate (owned; FEMA code exists)
PMP-SP-4D | Pumps & dewatering | Pump | diesel self-priming trailer | 4 in diesel self-priming trailer (550 GPM) | Discharge size | 4 | in | [5 empty] | diesel | Laborer (per WD group) | day/wk/4wk | 318 | 922 | 2674 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. Rent: Wheeler only. | Needs fuel gal/hr; Needs rate (owned)
PMP-SP-6D | Pumps & dewatering | Pump | trash/self-priming, diesel trailer | 6 in trash/self-priming, diesel trailer (~1,425 GPM) | Discharge size | 6 | in | [5 empty] | diesel | Laborer (per WD group) | day/wk/4wk | 380 | 1112 | 3253 | 1710 | 4796 | bare |  |  | W25;B25 | 2025-2026 | A | 8465 |  |  |  | 1.7 |  | AMT/Depco 5588-D6 6 in diesel: 20 gal tank / 12 hr runtime = 1.7 gal/hr, derived (load not stated) [AMT-5588] |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. Rent: Median (=mean) of 2 sources: W 570/1654/4796; B 190/570/1710. Wide spread. FEMA 8465: FEMA 8465 6 in diesel trash pump: rate not reliably extracted. | Needs rate (owned; FEMA code exists)
PMP-CENT-4-40M | Pumps & dewatering | Pump | centrifugal | 4 in centrifugal (40M) | Discharge size | 4 | in | FEMA 8476 (to 60 hp) |  | 60 |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8476 | 4.1 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Split from PMP-SP-4D in revision (FEMA centrifugal is not the rented self-priming trash pump). FEMA: 4 in centrifugal at $4.10/hr looks implausibly low. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged: implausibly low; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
PMP-CENT-6-90M | Pumps & dewatering | Pump | centrifugal | 6 in centrifugal (90M) | Discharge size | 6 | in | FEMA 8477 (to 95 hp) |  | 95 |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8477 | 5.35 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Split from PMP-SP-6D in revision. FEMA: 6 in centrifugal at $5.35/hr looks implausibly low. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged: implausibly low; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
PMP-12D | Pumps & dewatering | Pump | diesel centrifugal | 12 in diesel centrifugal (to 140 hp) | Discharge size | 12 | in | [5 empty] | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8478 | 4.75 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. FEMA: 12 in pump at $4.75/hr implausibly low (notes ⚠). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged: implausibly low; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
PMP-CENT-2-6M | Pumps & dewatering | Pump | lightweight centrifugal | 2 in lightweight centrifugal (6M) | Discharge size | 2 | in | [5 empty] | gas | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8470 | 6.83 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | Needs fuel gal/hr; Needs rate (rental)
PMP-CENT-2-8M | Pumps & dewatering | Pump | lightweight centrifugal | 2 in lightweight centrifugal (8M) | Discharge size | 2 | in | [5 empty] | gas | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8471 | 3.53 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | Needs fuel gal/hr; Needs rate (rental)
PMP-CENT-3-18M | Pumps & dewatering | Pump | lightweight centrifugal | 3 in lightweight centrifugal (18M) | Discharge size | 3 | in | [5 empty] | gas | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8472 | 4.74 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | Needs fuel gal/hr; Needs rate (rental)
PMP-CENT-3-HD | Pumps & dewatering | Pump | heavy-duty centrifugal | 3 in heavy-duty centrifugal (20M) | Discharge size | 3 | in | [5 empty] | gas | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8473 | 5.91 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | Needs fuel gal/hr; Needs rate (rental)
PMP-SUB-2E | Pumps & dewatering | Pump | electric submersible | 2 in electric submersible | Discharge size | 2 | in | [5 empty] | electric | Laborer (per WD group) | day/wk/4wk | 40 | 130 | 360 | 315 | 405 | bare |  |  | B25;N25 | 2025-2026 | A |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. Rent: Median (=mean) of 2 sources: B 45/135/405; N 35/125/315. | Needs rate (owned)
PMP-SUB-2G | Pumps & dewatering | Pump | gas submersible | 2 in gas submersible | Discharge size | 2 | in | [5 empty] | gas | Laborer (per WD group) | day/wk/4wk | 74 | 263 | 609 |  |  | bare |  |  | W25 | 2025 | B | [8 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. Rent: Wheeler only. | Needs fuel gal/hr; Needs rate (owned)
PMP-SUB-4E | Pumps & dewatering | Pump | electric submersible | 4 in electric submersible (25 hp) | Discharge size | 4 | in | [5 empty] | electric | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8474 | 4.35 | FEMA 2025 | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) | 4.35 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. Ex-fuel = incl-fuel rate (no liquid fuel to back out). | Needs rate (rental)
PMP-SUB-6E | Pumps & dewatering | Pump | electric submersible | 6 in electric submersible (35 hp) | Discharge size | 6 | in | [5 empty] | electric | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8475 | 3.86 | FEMA 2025 | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) | 3.86 | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 | SP-PUMP-DUR | Hoses not included (FEMA). Dewatering often runs 24 hr/day: price 3 shifts or 24/7 (inference). FEMA small-pump rates look like hourly fractions of tiny units; treat with care. FEMA: 6 in/35 hp below 4 in/25 hp. Ex-fuel = incl-fuel rate (no liquid fuel to back out). | FEMA value flagged: implausibly low; verify; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
PMP-STORM | Pumps & dewatering | Pump | Stormwater (large) | Stormwater pump 1,740 CFS | Capacity | 1740 | CFS | FEMA 8469 |  |  |  |  | diesel | Operating Engineer - heavy equip. group (per WD) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8469 | 1743.1 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | multi-axle-heavy |  |  | Y | 1913 | 1913 |  | FEMA: Large flood-control unit; out of normal construction scope. Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
HOSE-3IN | Pumps & dewatering | Pump hose | Discharge/suction hose, per 50 ft | 3 in hose (50 ft) | Diameter | 3 | in | FEMA 8350-8361 series |  |  | per 50 ft |  | none | None (non-operated item) | each/day | [5 empty] | bare |  |  |  |  | D | 8350-8361 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8350-8361: FEMA hose rates not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
HOSE-4IN | Pumps & dewatering | Pump hose | Discharge/suction hose, per 50 ft | 4 in hose (50 ft) | Diameter | 4 | in | FEMA 8350-8361 series |  |  | per 50 ft |  | none | None (non-operated item) | each/day | [5 empty] | bare |  |  |  |  | D | 8350-8361 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8350-8361: FEMA hose rates not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
HOSE-6IN | Pumps & dewatering | Pump hose | Discharge/suction hose, per 50 ft | 6 in hose (50 ft) | Diameter | 6 | in | FEMA 8350-8361 series |  |  | per 50 ft |  | none | None (non-operated item) | each/day | [5 empty] | bare |  |  |  |  | D | 8350-8361 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8350-8361: FEMA hose rates not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
HOSE-8IN | Pumps & dewatering | Pump hose | Discharge/suction hose, per 50 ft | 8 in hose (50 ft) | Diameter | 8 | in | FEMA 8350-8361 series |  |  | per 50 ft |  | none | None (non-operated item) | each/day | [5 empty] | bare |  |  |  |  | D | 8350-8361 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8350-8361: FEMA hose rates not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
HOSE-12IN | Pumps & dewatering | Pump hose | Discharge/suction hose, per 50 ft | 12 in hose (50 ft) | Diameter | 12 | in | FEMA 8350-8361 series |  |  | per 50 ft |  | none | None (non-operated item) | each/day | [5 empty] | bare |  |  |  |  | D | 8350-8361 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8350-8361: FEMA hose rates not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
HOSE-16IN | Pumps & dewatering | Pump hose | Discharge/suction hose, per 50 ft | 16 in hose (50 ft) | Diameter | 16 | in | FEMA 8350-8361 series |  |  | per 50 ft |  | none | None (non-operated item) | each/day | [5 empty] | bare |  |  |  |  | D | 8350-8361 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8350-8361: FEMA hose rates not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
TRK-PU-8801 | Trucks & vehicles | Pickup truck | 4x2 | Pickup 4x2 1/2-ton | Ton rating | 1/2-ton | ton | [5 empty] | gas | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8801 | 17.79 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8800: any pickup $0.70/mile alternative. Fuel type for 4x2 rows not stated in notes (gas assumed - verify). FEMA: Pickup rates do not rise with size (notes ⚠). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | FEMA value flagged: pickup rates non-monotonic; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
TRK-PU-8802 | Trucks & vehicles | Pickup truck | 4x2 | Pickup 4x2 1-ton | Ton rating | 1-ton | ton | [5 empty] | gas | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8802 | 15.74 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8800: any pickup $0.70/mile alternative. Fuel type for 4x2 rows not stated in notes (gas assumed - verify). FEMA: Pickup rates do not rise with size (notes ⚠). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | FEMA value flagged: pickup rates non-monotonic; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
TRK-PU-8803 | Trucks & vehicles | Pickup truck | 4x2 | Pickup 4x2 1-1/4-ton | Ton rating | 1-1/4-ton | ton | [5 empty] | gas | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8803 | 19.77 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8800: any pickup $0.70/mile alternative. Fuel type for 4x2 rows not stated in notes (gas assumed - verify). FEMA: Pickup rates do not rise with size (notes ⚠). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | FEMA value flagged: pickup rates non-monotonic; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
TRK-PU-8804 | Trucks & vehicles | Pickup truck | 4x2 | Pickup 4x2 1-1/2-ton | Ton rating | 1-1/2-ton | ton | [5 empty] | gas | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8804 | 31.37 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8800: any pickup $0.70/mile alternative. Fuel type for 4x2 rows not stated in notes (gas assumed - verify). FEMA: Pickup rates do not rise with size (notes ⚠). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | FEMA value flagged: pickup rates non-monotonic; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
TRK-PU-8805 | Trucks & vehicles | Pickup truck | 4x2 | Pickup 4x2 1-3/4-ton | Ton rating | 1-3/4-ton | ton | [5 empty] | gas | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8805 | 41.23 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8800: any pickup $0.70/mile alternative. Fuel type for 4x2 rows not stated in notes (gas assumed - verify). FEMA: Pickup rates do not rise with size (notes ⚠). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | FEMA value flagged: pickup rates non-monotonic; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
TRK-PU-8806 | Trucks & vehicles | Pickup truck | 4x2 | Pickup 4x2 3/4-ton | Ton rating | 3/4-ton | ton | [5 empty] | gas | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8806 | 47.36 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8800: any pickup $0.70/mile alternative. Fuel type for 4x2 rows not stated in notes (gas assumed - verify). FEMA: Pickup rates do not rise with size (notes ⚠). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | FEMA value flagged: pickup rates non-monotonic; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
TRK-PU-8807 | Trucks & vehicles | Pickup truck | 4x4 | Pickup 4x4 3/4-ton crew, gas | Ton rating | 3/4-ton | ton | [5 empty] | gas | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8807 | 30.44 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8800: any pickup $0.70/mile alternative. Fuel type for 4x2 rows not stated in notes (gas assumed - verify). FEMA: Pickup rates do not rise with size (notes ⚠). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | FEMA value flagged: pickup rates non-monotonic; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
TRK-PU-8808 | Trucks & vehicles | Pickup truck | 4x4 | Pickup 4x4 1-ton crew, diesel | Ton rating | 1-ton | ton | [5 empty] | diesel | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8808 | 40.45 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8800: any pickup $0.70/mile alternative. Fuel type for 4x2 rows not stated in notes (gas assumed - verify). FEMA: Pickup rates do not rise with size (notes ⚠). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | FEMA value flagged: pickup rates non-monotonic; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
TRK-PU-8809 | Trucks & vehicles | Pickup truck | 4x4 | Pickup 4x4 1-1/4-ton crew, gas | Ton rating | 1-1/4-ton | ton | [5 empty] | gas | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8809 | 48.61 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8800: any pickup $0.70/mile alternative. Fuel type for 4x2 rows not stated in notes (gas assumed - verify). FEMA: Pickup rates do not rise with size (notes ⚠). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | FEMA value flagged: pickup rates non-monotonic; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
TRK-PU-8810 | Trucks & vehicles | Pickup truck | 4x4 | Pickup 4x4 1-1/2-ton crew, gas | Ton rating | 1-1/2-ton | ton | [5 empty] | gas | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8810 | 40.8 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8800: any pickup $0.70/mile alternative. Fuel type for 4x2 rows not stated in notes (gas assumed - verify). FEMA: Pickup rates do not rise with size (notes ⚠). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | FEMA value flagged: pickup rates non-monotonic; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
TRK-PU-8811 | Trucks & vehicles | Pickup truck | 4x4 | Pickup 4x4 1-3/4-ton crew, gas | Ton rating | 1-3/4-ton | ton | [5 empty] | gas | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8811 | 28.72 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8800: any pickup $0.70/mile alternative. Fuel type for 4x2 rows not stated in notes (gas assumed - verify). FEMA: Pickup rates do not rise with size (notes ⚠). Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | FEMA value flagged: pickup rates non-monotonic; verify; Needs fuel gal/hr; Needs rate (rental); FEMA ⚠ value kept as published; verify vs PDF
TRK-PU-8800 | Trucks & vehicles | Pickup truck | Any size (mileage rate) | Pickup, any size - per mile | Unit | mile |  | FEMA 8800 |  |  |  |  | gas | Truck Driver (per WD class/axles) | mile | [5 empty] | bare |  |  |  |  | D | 8800 | 0.7 | FEMA 2025 - $ per MILE | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | B | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Mileage rate includes fuel; no gal/hr applies. FEMA: Unit is $ per MILE (not per hour); see Owned_rate_unit. No ex-fuel value: FEMA 8800 is a per-mile rate that includes fuel. | Needs rate (rental)
TRK-FLAT-8700 | Trucks & vehicles | Flatbed truck | Flatbed | Flatbed 4x2 15K GVW diesel | GVW | 15000 | lb | [5 empty] | diesel | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8700 | 60.54 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
TRK-FLAT-8701 | Trucks & vehicles | Flatbed truck | Flatbed | Flatbed 4x2 25K GVW gas | GVW | 25000 | lb | [5 empty] | gas | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8701 | 71.91 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x gasoline back-out price (Settings B10). | Needs fuel gal/hr; Needs rate (rental)
TRK-FLAT-8701-1 | Trucks & vehicles | Flatbed truck | Flatbed | Flatbed 4x2 25K GVW diesel | GVW | 25000 | lb | [5 empty] | diesel | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8701.1 | 49.04 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
TRK-FLAT-8702 | Trucks & vehicles | Flatbed truck | Flatbed | Flatbed 4x2 30K GVW diesel | GVW | 30000 | lb | [5 empty] | diesel | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8702 | 81.87 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
TRK-FLAT-8703 | Trucks & vehicles | Flatbed truck | Flatbed | Flatbed 6x4 45K GVW diesel | GVW | 45000 | lb | [5 empty] | diesel | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8703 | 88.03 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
TRK-TRAC-8789 | Trucks & vehicles | Truck tractor | 4x2 | Truck tractor 4x2 26,001-33,000 lb (Freightliner M2 106+) | GVW | 33000 | lb | Freightliner M2 106 |  |  |  |  | diesel | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8789 | 75.13 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-HAUL-TRK-10 | Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
TRK-TRAC-8790 | Trucks & vehicles | Truck tractor | 6x4 | Truck tractor 6x4 33,001-52,000 lb (Freightliner M2 106) | GVW | 52000 | lb | Freightliner M2 106 |  |  |  |  | diesel | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8790 | 91.1 | FEMA 2025 | [5 empty] | B | C | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  | EW-HAUL-TRK-10 | Ex-fuel (C) = FEMA incl-fuel rate - Fuel_gal_hr_med x diesel back-out price (Settings B5). | Needs fuel gal/hr; Needs rate (rental)
TRK-8840 | Trucks & vehicles | Service truck | Truck | Service truck | FEMA code | 8840 | [6 empty] | diesel | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8840 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8840: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
TRK-8841 | Trucks & vehicles | Fuel truck | Truck | Fuel truck | FEMA code | 8841 | [6 empty] | diesel | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8841 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8841: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
TRK-8736 | Trucks & vehicles | Rollback tow truck | Truck | Rollback tow truck | FEMA code | 8736 | [6 empty] | diesel | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8736 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8736: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
TRK-8795 | Trucks & vehicles | Backhoe carrier truck | Truck | Backhoe carrier truck | FEMA code | 8795 | [6 empty] | diesel | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8795 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8795: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
TRK-8734 | Traffic control | Truck-mounted attenuator | Truck | Truck-mounted attenuator (Scorpion II TMA) | FEMA code | 8734 | [6 empty] | diesel | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8734 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8734: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
TRK-8735 | Traffic control | Attenuator truck | Truck | Attenuator truck | FEMA code | 8735 | [6 empty] | diesel | Truck Driver (per WD class/axles) | hr | [5 empty] | bare |  |  |  |  | D | 8735 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | FEMA 8735: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
TRK-ATV-UTV | Trucks & vehicles | ATV / UTV | By engine cc | ATV/UTV | Engine |  | cc | FEMA 8080-8087 |  |  |  |  | gas | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8080-8087 | [7 empty] | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8080-8087: Rates not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
TRL-8600 | Trailers | Equipment trailer | Towed | Equipment trailer, tilt bed 17,500 lb GVWR | FEMA code | 8600 | [6 empty] | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8600 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Tow vehicle priced separately. FEMA 8600: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
TRL-8601 | Trailers | Equipment trailer | Towed | Equipment trailer, tri-axle 30 ft / 62,000 lb GVWR | FEMA code | 8601 | [6 empty] | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8601 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Tow vehicle priced separately. FEMA 8601: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
TRL-8602 | Trailers | Lowboy drop-deck 60 ton | Towed | Lowboy drop-deck 60 ton | FEMA code | 8602 | [6 empty] | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8602 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Tow vehicle priced separately. FEMA 8602: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
TRL-8603 | Trailers | Lowboy flush-deck 120 ton | Towed | Lowboy flush-deck 120 ton | FEMA code | 8603 | [6 empty] | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8603 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Tow vehicle priced separately. FEMA 8603: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
TRL-8708 | Trailers | Semi trailer | Towed | Semi trailer 48 ft flatbed | FEMA code | 8708 | [6 empty] | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8708 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Tow vehicle priced separately. FEMA 8708: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
TRL-8709 | Trailers | Semi trailer enclosed | Towed | Semi trailer enclosed | FEMA code | 8709 | [6 empty] | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8709 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Tow vehicle priced separately. FEMA 8709: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
TRL-8711 | Trailers | Utility trailer | Towed | Utility trailer | FEMA code | 8711 | [6 empty] | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8711 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Tow vehicle priced separately. FEMA 8711: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
TRL-8644 | Trailers | Covered utility trailer | Towed | Covered utility trailer 7x16 ft | FEMA code | 8644 | [6 empty] | none (towed) | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8644 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Owned: USACE standby = 0.5 x DEPR + FCCM, max 40 hr/wk [USACE-EP]; with only an all-in rate use Caltrans delay factor x rate, max 8 hr/day & 40 hr/wk [CALT-2627]: no class factor captured, use 0.10-0.22 band (inference). Rental: accrues by calendar period. FEMA: not eligible unless intermittent use [FEMA-PG]. | self-propelled |  |  | N |  |  |  | Tow vehicle priced separately. FEMA 8644: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
OFF-8x20 | Site & temporary facilities | Office trailer | Mobile office | Office trailer 8x20 | Size | 8x20 | ft | [5 empty] | electric (site power) | None (non-operated item) | 4wk |  |  | 350 | 200 | 500 | bare |  |  | PRICER-OT | Oct 1 2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Accrues monthly. | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | Rent: ThePricer $200-500/month; midpoint used as 4-week (monthly != 4-week). Delivery single-wide ~$500-1,500; delivery+setup $1,000-5,000+; pickup ~= delivery. | Needs rate (owned)
OFF-10x40 | Site & temporary facilities | Office trailer | Mobile office | Office trailer 10x40 | Size | 10x40 | ft | [5 empty] | electric (site power) | None (non-operated item) | 4wk |  |  | 500 | 300 | 700 | bare |  |  | PRICER-OT | Oct 1 2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Accrues monthly. | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | Rent: ThePricer $300-700/month; midpoint used as 4-week (monthly != 4-week). Delivery single-wide ~$500-1,500; delivery+setup $1,000-5,000+; pickup ~= delivery. | Needs rate (owned)
OFF-12x60 | Site & temporary facilities | Office trailer | single-wide | Office trailer 12x60 single-wide | Size | 12x60 | ft | [5 empty] | electric (site power) | None (non-operated item) | 4wk |  |  | 675 | 450 | 900 | bare |  |  | PRICER-OT | Oct 1 2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Accrues monthly. | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | Rent: ThePricer $450-900/month; midpoint used as 4-week (monthly != 4-week). Delivery single-wide ~$500-1,500; delivery+setup $1,000-5,000+; pickup ~= delivery. | Needs rate (owned)
OFF-24x60 | Site & temporary facilities | Office trailer | double-wide | Office trailer 24x60 double-wide | Size | 24x60 | ft | [5 empty] | electric (site power) | None (non-operated item) | 4wk |  |  | 1300 | 800 | 1800 | bare |  |  | PRICER-OT | Oct 1 2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Accrues monthly. | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | Rent: ThePricer $800-1,800/month; midpoint used as 4-week (monthly != 4-week). Delivery single-wide ~$500-1,500; delivery+setup $1,000-5,000+; pickup ~= delivery. | Needs rate (owned)
OFF-FEMA-8640 | Site & temporary facilities | Office / facility trailer | FEMA | Office trailer 8x24 (FEMA) | FEMA code | 8640 | [6 empty] | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8640 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D |  | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | FEMA 8640: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
OFF-FEMA-8641 | Site & temporary facilities | Office / facility trailer | FEMA | Office trailer 7x12 (FEMA) | FEMA code | 8641 | [6 empty] | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8641 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D |  | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | FEMA 8641: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
OFF-FEMA-8642 | Site & temporary facilities | Office / facility trailer | FEMA | Command trailer (FEMA) | FEMA code | 8642 | [6 empty] | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8642 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D |  | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | FEMA 8642: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
OFF-FEMA-8645 | Site & temporary facilities | Office / facility trailer | FEMA | Restroom/shower trailer, 12 stations (FEMA) | FEMA code | 8645 | [6 empty] | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8645 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D |  | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | FEMA 8645: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
CONT-STORAGE | Site & temporary facilities | Storage container | 20-40 ft | Storage container 20-40 ft | Length | 20-40 | ft | [5 empty] | none | None (non-operated item) | 4wk |  |  | 288 | 75 | 500 | bare |  |  | BNB-CONT | Mar 27 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Accrues monthly. | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | Rent: Boom & Bucket $75-500/mo by size/mods; midpoint as 4-week. Delivery $100-500. (ThePricer Dec 2022 excluded as outdated.) | Needs rate (owned)
FENCE-CHAIN-LF | Site & temporary facilities | Temporary fence | Chain-link panels | Chain-link panel fence (per LF) | Unit | LF | [6 empty] | none | Laborer (per WD group) | LF/4wk |  |  | 2.25 | 1 | 3.5 | bare |  |  | PRICER-FN | Jun 30 2026 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D | Accrues monthly. | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | Rate is $ per LF per month, not per unit. Rent: $1-3.50/LF/month; midpoint as 4-week $/LF. In-ground $2-5+/LF/mo; privacy screen +$0.50-2.50/LF; gates vehicle $100-500+, ped $50-250+; delivery/pickup $150-600+; setup/removal $200-1,000+. | Needs rate (owned)
SCAF-FRAME-6 | Site & temporary facilities | Scaffolding | Interior frame | 6 ft frame section | Section height | 6 | ft | [5 empty] | none | Carpenter/Laborer (scaffold erector, per WD) | each/day/wk/4wk | 35 | 115 | 285 |  |  | bare |  |  | N25 | Jan 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D |  | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | Rent: Nu-Way only. 3 ft pony $15/30/90; outriggers set of 4 $5/15/45; guardrail/toeboard $5/15/45. | Needs rate (owned)
TRAF-ARROW | Site & temporary facilities | Arrow board | Trailer, solar | Solar arrow board | Type | arrow |  | FEMA 8050 |  |  |  |  | solar | None (non-operated item) | day/wk/4wk | 95 | 285 | 855 |  |  | bare |  |  | B25 | Mar 2025 | B | 8050 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D |  | pickup-towed |  |  | N | 200 | 200 | SITE-DUR | Rent: Burris only. FEMA 8050: Rate not captured. | Needs rate (owned; FEMA code exists)
TRAF-CMS | Site & temporary facilities | Message board (CMS) | Trailer | Changeable message sign | Type | CMS |  | FEMA 8051 |  |  |  |  | solar | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8051 |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D |  | pickup-towed |  |  | N | 200 | 200 | SITE-DUR | FEMA 8051: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists)
TANK-FUEL-1200 | Site & temporary facilities | Fuel tank | Fuel cube | Fuel Cube 1,204 gal | Capacity | 1204 | gal | [5 empty] | none | None (non-operated item) | wk/4wk |  | 360 | 1080 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D |  | delivered-by-supplier |  |  | N | 200 | 200 |  | Rent: Wheeler only ($360/wk, $1,080/4-wk; no day rate). | Needs rate (owned)
TANK-DEF-132 | Site & temporary facilities | DEF tank | DEF cube | DEF Cube 132 gal | Capacity | 132 | gal | [5 empty] | none | None (non-operated item) | wk/4wk |  | 267 | 800 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D |  | delivered-by-supplier |  |  | N | 200 | 200 |  | Rent: Wheeler only. | Needs rate (owned)
TANK-TACK-TT300 | Site & temporary facilities | Tack/asphalt tank | Trailer tank | Weiler TT300 tank | Model | TT300 |  | Weiler TT300 |  |  |  |  | none | None (non-operated item) | day/wk/4wk | 332 | 964 | 2795 |  |  | bare |  |  | W25 | 2025 | B |  |  |  | 0 | 0 | 0 | No engine (towed / attachment / non-powered) |  | D | D |  | pickup-towed |  |  | N | 200 | 200 | PV-TACK | Rent: Wheeler only. | Needs rate (owned)
ERO-HS-8630 | Site & temporary facilities | Hydroseeder | Erosion control | Hydroseeder Reinco HG-5 | Model | HG-5 |  | Hydroseeder Reinco HG-5 |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8630 | [7 empty] | D | D |  | pickup-towed |  |  | N | 200 | 200 | SITE-HYDROSEED | FEMA 8630: FEMA rate not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
ERO-HS-8631 | Site & temporary facilities | Hydroseeder | Erosion control | Hydroseeder Reinco HG-10 | Model | HG-10 |  | Hydroseeder Reinco HG-10 |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8631 | [7 empty] | D | D |  | pickup-towed |  |  | N | 200 | 200 | SITE-HYDROSEED | FEMA 8631: FEMA rate not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
ERO-HS-8632 | Site & temporary facilities | Hydroseeder | Erosion control | Hydroseeder Reinco HG-30 | Model | HG-30 |  | Hydroseeder Reinco HG-30 |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8632 | [7 empty] | D | D |  | pickup-towed |  |  | N | 200 | 200 | SITE-HYDROSEED | FEMA 8632: FEMA rate not reliably extracted. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
ERO-MULCH-8633 | Site & temporary facilities | Straw mulcher | Erosion control | Straw mulcher Finn B70 | Model | B70 |  | Straw mulcher Finn B70 |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8633 | [7 empty] | D | D |  | pickup-towed |  |  | N | 200 | 200 | SITE-HYDROSEED | FEMA 8633: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
ERO-MULCH-8634 | Site & temporary facilities | Straw mulcher | Erosion control | Straw mulcher Reinco M65 | Model | M65 |  | Straw mulcher Reinco M65 |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8634 | [7 empty] | D | D |  | pickup-towed |  |  | N | 200 | 200 | SITE-HYDROSEED | FEMA 8634: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
ERO-MULCH-8635 | Site & temporary facilities | Straw mulcher | Erosion control | Straw mulcher Reinco M90 | Model | M90 |  | Straw mulcher Reinco M90 |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8635 | [7 empty] | D | D |  | pickup-towed |  |  | N | 200 | 200 | SITE-HYDROSEED | FEMA 8635: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
SITE-SANDBAGGER | Site & temporary facilities | Sandbagger | Machine | Sandbagger | Type |  |  | FEMA 8872 |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8872 | [7 empty] | D | D |  | pickup-towed |  |  | N | 200 | 200 |  | FEMA 8872: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
SITE-DUSTCTRL | Site & temporary facilities | Dust-control unit | Misting cannon | Dust-control unit | Type |  |  | FEMA 8569 |  |  |  |  | diesel | Laborer (per WD group) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | 8569 | [7 empty] | D | D |  | pickup-towed |  |  | N | 200 | 200 | EW-DUST | FEMA 8569: Rate not captured. | Needs rate; Needs rate (rental); Needs rate (owned; FEMA code exists); Needs fuel gal/hr
SITE-GPS-BASE | Site & temporary facilities | GPS / machine-control base & rover | Survey/MC | GPS base station + rover | Type | [7 empty] | electric | Trade using it (self-operated; no dedicated operator) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D |  |  |  | 0 | 0 | 0 | Electric/battery - no liquid fuel (charging/power not modeled) |  | D | D |  | pickup-towed |  |  | N | 200 | 200 |  | Unsourced category (see AT-GPS-DOZER for dozer kit). | Needs rate; Needs rate (rental); Needs rate (owned)
SITE-RESTROOM | Site & temporary facilities | Portable restroom | Site | Portable restroom | Type | [7 empty] | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D |  | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | Category named in taxonomy gaps; no classes or rates in notes. | Needs rate; Needs rate (rental); Needs rate (owned)
SITE-BARRICADE | Site & temporary facilities | Barricades Type I/II/III | Site | Barricades Type I/II/III | Type | [7 empty] | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D |  | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | Category named in taxonomy gaps; no classes or rates in notes. | Needs rate; Needs rate (rental); Needs rate (owned)
SITE-PRESSWASH | Site & temporary facilities | Pressure washer | Site | Pressure washer | Type | [7 empty] | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D |  | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | Category named in taxonomy gaps; no classes or rates in notes. | Needs rate; Needs rate (rental); Needs rate (owned)
SITE-DEHUM | Site & temporary facilities | Dehumidifier | Site | Dehumidifier | Type | [7 empty] | none | None (non-operated item) | day/wk/4wk | [5 empty] | bare |  |  |  |  | D | [8 empty] | D | D |  | delivered-by-supplier |  |  | N | 200 | 200 | SITE-DUR | Category named in taxonomy gaps; no classes or rates in notes. | Needs rate; Needs rate (rental); Needs rate (owned)
Note on O1: Label only. Wages come from the project's wage set (labor), never from this sheet.
Note on Q1: Bare rental: no operator, no fuel. Blue = sourced value; black = formula.
Note on T1: Min/max of the source values used; or a single source's own published range (noted); blank when there is only one value.
Note on W1: Operated hourly rate INCLUDES operator/driver - do not add labor for these rows.
Note on AA1: A = 2+ sources not derived from each other (median); B = single source or non-independent sources; C = derived (method in Notes); D = no basis (blank, Flags 'Needs rate').
Note on AC1: FEMA 2025 published all-in hourly (ownership + operating + fuel), operator excluded.
Note on AI1: Formula: incl-fuel rate - Fuel_gal_hr_med x Settings!B5 (EIA 2025 avg diesel). App adds gal/hr x user fuel price (Settings!B4).
Note on AJ1: Confidence of Owned_rate_hr_incl_fuel: B = FEMA as published; C = interpolated; D = none.
Note on AK1: Confidence of Owned_rate_hr_excl_fuel: always C (derived by fuel back-out) when present; D when blank.
Note on AQ1: Formula: MAX(class minimum, $/mile x Settings!B6 miles) + permit (if Permit_likely=Y) + escorts + load/unload. See Mob_Demob.

## Activities
Activity_ID | Group | Activity_name | Output_unit | Norm_basis | Method_formula | Required_inputs | Source_ids | Activity_type
EW-CLR-MED | Earthwork: clearing | Clear & grub with medium tractor dozer (straight blade) | acre/hr | Handbook quick method (FM Table 2-1), per hour | acre/hr = 1 / (hours per acre): light 2.5, medium 5.0, heavy 10.0 hr/acre. Strip-type clearing +60%; grubbing +25%. DOT: C&G 3-9 STA/day (WisDOT) | Vegetation (light <=12 in, medium 12-18, heavy >=18) | FM5434;WISDOT;TXDOT | Production
EW-CLR-HVY | Earthwork: clearing | Clear & grub with heavy tractor dozer (straight blade) | acre/hr | Handbook quick method (FM Table 2-1), per hour | acre/hr = 1 / (hours per acre): light 1.5, medium 3.0, heavy 8.0 hr/acre. Shear (KG) blade: 0.3/0.5/0.8 hr/acre | Vegetation | FM5434 | Production
EW-STRIP | Earthwork: strip | Strip topsoil with dozer (short push, 50 ft) | LCY/hr | Per hour at 50-min hour (E) | LCY/hr = Blade_LCY x 60 / (t_fixed + D/(v_doze x 88) + D/(v_return x 88)) x E; D = 50 ft; material factor 1.0 | Blade LCY, push distance, speeds | KSU-4;FM5434 | Production
EW-PUSH-100 | Earthwork: push | Dozer push / bulk doze, 100 ft average push | LCY/hr | Per hour at 50-min hour (E) | Same dozer cycle equation, D = 100 ft. Low = x0.75 avg operator x0.80 hard-to-drift; High = x1.20 slot dozing | Blade LCY, D, speeds, factors | KSU-4;FM5434 | Production
EW-PUSH-200 | Earthwork: push | Dozer push, 200 ft average push | LCY/hr | Per hour at 50-min hour (E) | As EW-PUSH-100 with D = 200 ft |  | KSU-4;FM5434 | Production
EW-PUSH-300 | Earthwork: push | Dozer push, 300 ft average push | LCY/hr | Per hour at 50-min hour (E) | As EW-PUSH-100 with D = 300 ft |  | KSU-4;FM5434 | Production
EW-SPREAD | Earthwork: spread | Spread dumped fill / topsoil with dozer (50 ft, loose material) | LCY/hr | Per hour at 50-min hour (E) | Dozer cycle at D = 50 ft x loose-stockpile material factor 1.20 (FM Table 2-4). DOT cross-check: topsoil placement 120-700 CY/day, typical 280 (WisDOT) | Blade LCY | KSU-4;FM5434;WISDOT | Production
EW-RGRADE | Earthwork: spread | Rough grade with dozer | SY/hr | n/a | No sourced dozer grading rate (Cat curves not obtained). Price by duration or use grader rows. |  | FM5434 | Production
EW-RIP | Earthwork: rock rip | Rip rock with single-shank ripper (large dozer) | BCY/hr | Indicative (seismic velocity), single tractor | Indicative: 5,000 fps -> 500 BCY/hr; 6,500 fps -> 300; 8,500 fps -> 150 (model not stated). Pass-geometry: BCY/hr = (D x S x Lp/27) x 60 / (Lp/(mph x 88) + t_turn) x E | Seismic velocity or pass geometry | GEOM;FM5434;WYDOT-RIP | Production
EW-CUTLOAD | Earthwork: cut/load | Bulk cut and load trucks (hydraulic excavator) | BCY/hr | Per hour at 50-min hour (E) | LCY/hr = 3600/cycle_s x Bucket_CY x Fill x E; BCY = LCY x Load factor (L->B). Cycle 14 s (<1 CY), 15 s (1-2.5 CY) at 40-60% depth, 30-60 deg swing | Bucket CY, fill factor, soil | FM5434-8;KSU-3;FM5434 | Production
EW-MASS | Earthwork: cut/load | Mass excavation, cast to spoil/stockpile (hydraulic excavator) | BCY/hr | Per hour at 50-min hour (E) | Same as EW-CUTLOAD (no sourced differential between loading trucks and casting; truck exchange limits are handled by fleet balance) | Bucket CY, fill, soil | FM5434-8;KSU-3 | Production
EW-TRENCH-5 | Earthwork: trench | Trench excavation, up to ~5 ft deep | BCY/hr | Per hour at 50-min hour (E) | Excavator equation x trench factor 0.98 (0.95-1.0). LF/hr = BCY/hr x 27 / trench cross-section (ft2) incl. slope/bench | Bucket CY, fill, soil, cross-section for LF | KSU-3;KSU-T3;FM5434-8 | Production
EW-TRENCH-10 | Earthwork: trench | Trench excavation, 6-10 ft deep | BCY/hr | Per hour at 50-min hour (E) | As EW-TRENCH-5; machine must reach depth at <=60% of max dig depth for the FM cycle to hold (deeper = slower, not quantified) |  | KSU-3;KSU-T3;FM5434-8 | Production
EW-TRENCH-15 | Earthwork: trench | Trench excavation, 11-15 ft deep (shored/boxed) | BCY/hr | Per hour at 50-min hour (E) | As EW-TRENCH-5; restricted to >=20 t classes |  | KSU-3;KSU-T3;FM5434-8 | Production
EW-STRUCT | Earthwork: cut/load | Structural excavation (footings, pits; confined swing) | BCY/hr | Per hour at 50-min hour (E) | Excavator equation x confined/trench factor 0.95 (low end of 0.95-1.0) |  | KSU-3;KSU-T3 | Production
EW-BACKFILL | Earthwork: backfill | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | LCY/hr | Per hour at 50-min hour (E) | LCY/hr = 3600/cycle x Bucket x Fill(loose 0.95) x E (bucket-handling equation applied to loose material; inference) | Bucket CY | FM5434-8;CAT-FILL;CAT-WL | Production
EW-LOAD-TRK | Earthwork: cut/load | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | LCY/hr | Per hour at 50-min hour (E) | LCY/hr = Bucket x Fill x 3600/cycle_s x E; Cat basic cycle 27-33 s (typ 30) | Bucket CY (sourced for loaders), fill, cycle | CAT-WL;CAT-FILL;KSU-EQ | Production
EW-STOCKPILE | Earthwork: cut/load | Stockpile / rehandle with loader (minimum travel) | LCY/hr | Per hour at 50-min hour (E) | Same as EW-LOAD-TRK (basic cycle includes minimum travel; add travel time for load-and-carry) |  | CAT-WL;CAT-FILL | Production
EW-SCR-1000 | Earthwork: scraper | Scraper load-haul-dump, 1,000 ft one-way | BCY/hr | Per hour, trips = 60 x E / cycle | Cycle = load + turn/dump 0.81 + L/(v_haul x 88) + L/(v_return x 88); load 0.85 min (D8 push) / 1.0 (D7); payload LCY = MIN(heaped x 0.833 (FM 621B 20 LCY / 24 yd3), rated load lb / 2,300 lb per LCY); trips/hr x E; BCY = LCY x 0.80 | Bowl, speeds (ASSUMED), load time | FM5434;USMC-PE;KSU-T6 | Production
EW-SCR-2000 | Earthwork: scraper | Scraper load-haul-dump, 2,000 ft one-way | BCY/hr | Per hour | As EW-SCR-1000, L = 2,000 ft |  | FM5434;USMC-PE | Production
EW-SCR-3000 | Earthwork: scraper | Scraper load-haul-dump, 3,000 ft one-way | BCY/hr | Per hour | As EW-SCR-1000, L = 3,000 ft |  | FM5434;USMC-PE | Production
EW-HAUL-TRK-05 | Earthwork: haul | Haul with on-road dump truck, 0.5 mi one-way | BCY/hr per truck | Per hour per truck (E) | Cycle = load (capacity / 2.7 LCY per pass x 0.5 min per pass; Settings B36-B37) + dump/maneuver 1.5 + mi x 60/v_loaded + mi x 60/v_empty; LCY/hr = Cap x 60 x E / cycle; BCY = x0.80. Trucks needed N = cycle / load time | Truck capacity, speeds (ASSUMED) | OEP;KSU-T5;KSU-EQ;KSU-T6 | Production
EW-HAUL-TRK-10 | Earthwork: haul | Haul with on-road dump truck, 1 mi one-way | BCY/hr per truck | Per hour per truck (E) | As EW-HAUL-TRK-05, 1.0 mi |  | OEP;KSU-T5 | Production
EW-HAUL-TRK-20 | Earthwork: haul | Haul with on-road dump truck, 2 mi one-way | BCY/hr per truck | Per hour per truck (E) | As EW-HAUL-TRK-05, 2.0 mi |  | OEP;KSU-T5 | Production
EW-HAUL-ADT-05 | Earthwork: haul | Haul with ADT, 0.5 mi one-way | BCY/hr per truck | Per hour per truck (E) | As on-road truck; capacity LCY = payload tons x 2000 / 2,300 lb/LCY (FM standard material weight) | Payload, speeds (ASSUMED) | OEP;FM5434;KSU-T5 | Production
EW-HAUL-ADT-10 | Earthwork: haul | Haul with ADT, 1 mi one-way | BCY/hr per truck | Per hour per truck (E) | As EW-HAUL-ADT-05, 1.0 mi |  | OEP;FM5434 | Production
EW-HAUL-ADT-20 | Earthwork: haul | Haul with ADT, 2 mi one-way | BCY/hr per truck | Per hour per truck (E) | As EW-HAUL-ADT-05, 2.0 mi |  | OEP;FM5434 | Production
EW-HAUL-RDT-10 | Earthwork: haul | Haul with rigid off-highway truck, 1 mi one-way | BCY/hr per truck | Per hour per truck (E) | As ADT haul, 1.0 mi |  | OEP;FM5434 | Production
EW-FGRADE | Earthwork: fine grade | Fine grade subgrade/base with motor grader | SY/hr | Per hour (E) | ft2/hr = mph x (Le - 2 ft overlap) x 5,280 x E; SY/hr = ft2/hr / 9 / passes. Finish speed 0-2.5 mph; blade at 30 deg | Moldboard, speed, passes | CAT-MG;KSU-T7 | Production
EW-RGRADE-GR | Earthwork: fine grade | Rough grade / heavy blading with motor grader (PER PASS) | SY/hr per pass | Per hour per pass (E) | SY per hour per pass = mph x (L x cos45 - 2) x 5,280 x E / 9; heavy blading 0-6 mph. Hours = area / rate x number of passes (passes entered by the estimator) | Moldboard, speed, number of passes | CAT-MG | Production
EW-SPREAD-BASE | Earthwork: spread | Spread and shape aggregate base (grader-led spread) | CY/day | DOT field daily (crew) | TxDOT flex base Low/Med/High per day |  | TXDOT;WISDOT | Production
EW-COMP-SOIL-6 | Earthwork: compact | Compact soil, 6 in compacted lifts (ride-on roller) | CCY/hr | Per hour (E) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Vibratory speed from 1 impact/in at 1,200-2,500 vpm (typ 1,850 -> 1.75 mph); P = 5 (4-6) | Drum width, speed, lift, passes | KSU-T7;STORMW;EDUREV | Production
EW-COMP-SOIL-8 | Earthwork: compact | Compact soil, 8 in compacted lifts | CCY/hr | Per hour (E) | As EW-COMP-SOIL-6, L = 8 in |  | KSU-T7;STORMW;EDUREV | Production
EW-COMP-SOIL-12 | Earthwork: compact | Compact soil, 12 in compacted lifts (granular, heavy rollers) | CCY/hr | Per hour (E) | As EW-COMP-SOIL-6, L = 12 in |  | KSU-T7;STORMW;KFUPM | Production
EW-COMP-SOIL-SM | Earthwork: compact | Compact soil with small roller/attachment, 6 in lifts | CCY/hr | Per hour (E) | As EW-COMP-SOIL-6 |  | KSU-T7;STORMW | Production
EW-COMP-TRENCH | Earthwork: compact | Compact trench backfill (trench roller / reversible plate), 4-5 in lifts | CCY/hr | Per hour (E) | 16.3 formula with lifts <=4-5 in (trench compactors) |  | KSU-T7;MST-GE441;STORMW | Production
EW-COMP-PLATE | Earthwork: compact | Compact with vibratory plate (structural/trench backfill) | CCY/hr | Per hour (E) | CCY/hr = ft2/hr (single-pass spec for the plate size) / passes x E x lift(in)/12 / 27; WP1550AW 19.5 in 9,750 ft2/hr; ATE TP-1830H 18 in 8,550 ft2/hr | Plate area rate, lift 2-6 in, passes | ATE-PLATE;WN-WP1550;MST-GE441;EDUREV | Production
EW-COMP-RAMMER | Earthwork: compact | Compact with rammer (2-3 in lifts) | CCY/hr | Per hour (E) | CCY/hr = area rate ft2/hr (single pass) / passes x E x lift(in)/12 / 27; Wacker BS60-4As ~1,590 ft2/hr | Area rate, lift, passes | MST-GE441;WN-BS60 | Production
EW-WATER | Earthwork: water | Moisture-condition fill (water for compaction) | gal/CCY | Quantity method | gal/CCY = dry density (pcf) x 27 x (w_target - w_insitu) / 8.33. 120 pcf, +7% -> ~27 gal/CCY. Trucks = gal/hr needed / (truck gal x trips/hr) | Dry density, moisture delta | FM5434-11;CPUC-WATER | Quantity/method
EW-DUST | Earthwork: water | Dust control watering | gal/acre/day | Quantity method | 1,815 gal/acre/day active area (1,210 staging), 3 applications/day, ~10% of graded area active |  | CPUC-WATER | Quantity/method
EW-PROOFROLL | Earthwork: compact | Proof roll | SY/hr | n/a | No proof-rolling production source |  |  | Production
EW-SPREAD-SSL | Earthwork: spread | Spread/backfill with skid steer or CTL | LCY/hr | n/a | No skid steer bucket sizes or production source |  |  | Production
EW-CLR-CHIP | Earthwork: clearing | Chip brush | ton/hr | n/a | No chipper production source (tub grinder throughput classes only) |  |  | Production
PV-HMA-ROAD | Paving | Place HMA, highway/road paving spread | TON/day | DOT field daily median | Paver output = min(plant tph, truck delivery tph, placement). DOT medians ~1,000-1,300 TON/day; trucks = daily tons / (floor(shift/cycle) x payload) | Plant tph, trucks, mat | WISDOT;TXDOT;WSDOT;NCDOT;FHWA-CFL;PSU-SP | Production
PV-HMA-LOT | Paving | Place HMA, small urban / lots / thin overlay | TON/day | DOT field daily | NCDOT small urban 200-500 TON/day; TxDOT thin overlay 200/500/750 |  | NCDOT;TXDOT | Production
PV-ROLL-HMA | Paving | Compact HMA mat (breakdown/intermediate/finish roller) | SY/hr | Per hour | SY/hr = mph x 5,280 x drum width(ft) / 9 x E / passes; 2.5-4 mph working speed (Roads & Bridges; AI 3 mph); 7 passes (Penn State example) | Drum width, speed, passes | AI-ROLL;PSU-SP;RB-HMA | Production
PV-MILL-SMALL | Paving | Cold plane (mill), small/compact machine | SY/hr | Per hour (geometric) | SY/hr = drum width(ft) x cutting speed(fpm) x 60 x E / 9; speed 30 fpm (notes example; PM310 max 108 fpm); truck loading often governs on deep cuts | Drum width, fpm | CAT-PM310;WSDOT | Production
PV-MILL-MID | Paving | Cold plane, compact/mid (3-5 ft drum) | SY/hr | Per hour (geometric) | As PV-MILL-SMALL |  | CAT-PM310 | Production
PV-MILL-LARGE | Paving | Cold plane, half/full-lane machine | SY/day | DOT field daily | WSDOT 7,000-13,000 normal 9,000; WisDOT thin median 17,000, thick 14,000; TxDOT 2,450/7,430/12,075 |  | WSDOT;WISDOT;TXDOT | Production
PV-TACK | Paving | Tack coat | gal/SY | Quantity method | 0.03-0.08 gal/SY residual, >=6 in beyond mat width (PennDOT 460) |  | PSU-SP | Quantity/method
PV-PRIME | Paving | Prime coat (distributor) | GAL/day | DOT field daily | TxDOT 1,000 / 4,500 / 8,000 GAL/day |  | TXDOT | Production
PV-CHIPSEAL | Paving | Seal coat / chip seal (spreader) | SY/day | DOT field daily | TxDOT 14,000/36,000/140,000 SY/day; NCDOT 5,000-10,000 (major), 2,000-5,000 (small urban) |  | TXDOT;NCDOT | Production
PV-SWEEP | Paving | Sweep pavement | lane-mi/hr | n/a | No sweeper production source |  |  | Production
PV-STRIPE-TRUCK | Paving | Paint striping, truck | LF/day | DOT field daily | TxDOT 12,500/50,000/100,000; WSDOT 14,000-100,000 West (>=5,000 LF/hr at 5-10 mph) |  | TXDOT;WSDOT | Production
PV-STRIPE-SMALL | Paving | Striping, walk/ride-behind or push cart | LF/day | DOT field daily | WSDOT plastic line push cart 400 LF/day (paint walk-behind not sourced) |  | WSDOT | Production
PV-STABILIZE | Paving | Subgrade lime/cement treatment (stabilizer) | SY/day | DOT field daily | TxDOT lime 688/2,495/4,108; cement 1,585/2,529/3,325 SY/day |  | TXDOT | Production
CN-PUMP-BOOM | Concrete | Place concrete by boom pump (direct from boom) | CY/hr | Practitioner field range | 60-100 CY/hr; rated ~133 CY/hr at 150 bar; realistic 45-75% of rated |  | FCP-CONC;ACI-S21 | Production
CN-PUMP-LINE | Concrete | Place concrete by line pump / downline | CY/hr | Practitioner field range | Pump with downline 40-60 CY/hr |  | FCP-CONC | Production
CN-PLACE-LASER | Concrete | Truck dump + laser screed placement | CY/hr | Practitioner field range | 80-160 CY/hr (200 seen, rarely sustained) |  | FCP-CONC | Production
CN-PLACE-SLAB | Concrete | Wet screed (hand/roller/vibratory screed) slab placement | CY/hr | Practitioner field range | Wet screed (hand) 30-60 CY/hr |  | FCP-CONC | Production
CN-FINISH-WB | Concrete | Power trowel finish, walk-behind 36 in | SF/day | Trade press (2002) | 700-1,500 SF/day (vs 300-600 by hand) |  | RER-TROWEL | Production
CN-FINISH-RIDE | Concrete | Power trowel finish, ride-on | SF/day | Trade press (2002), derived | Ride-on covers 3-5x a walk-behind |  | RER-TROWEL | Production
CN-SLIPFORM-PAVE | Concrete | Slipform concrete paving | SY/day | DOT field daily median | WisDOT 850-4,000 median 2,300; TxDOT 972/2,463/4,170; WSDOT ~1 mile of 24 ft/day |  | WISDOT;TXDOT;WSDOT;NCDOT | Production
CN-CURB | Concrete | Slipform curb & gutter | LF/day | DOT field daily median | WisDOT 330-1,500 median 800; TxDOT 288/554/1,000; WSDOT 1,500 West |  | WISDOT;TXDOT;WSDOT | Production
CN-SAWCUT | Concrete | Saw cut concrete/asphalt | LF/hr | n/a | No sourced LF/hr by depth |  |  | Production
CN-PLACE-BUGGY | Concrete | Place concrete by power buggy | CY/hr | n/a | No buggy CY/hr source |  |  | Production
CN-PLACE-BELT | Concrete | Place concrete by conveyor (Telebelt) | CY/hr | n/a | No conveyor placement rate source |  |  | Production
CN-MIX-SMALL | Concrete | Mix mortar/concrete on site | cu ft/hr | n/a | No source |  |  | Production
UT-PIPE-STORM | Utilities | Lay storm sewer 12-36 in (excavator-led crew) | LF/day | DOT field daily (8-hr day) | WSDOT 300-1,500 West, normal 800 (East 500-2,000, normal 1,500) |  | WSDOT | Production
UT-PIPE-STORM-L | Utilities | Lay storm sewer 42-72 in | LF/day | DOT field daily | WSDOT 50-200 LF/day |  | WSDOT | Production
UT-PIPE-SAN | Utilities | Lay sanitary sewer 6-48 in | LF/day | DOT field daily | WSDOT 200-400 LF/day |  | WSDOT | Production
UT-PIPE-WATER | Utilities | Lay water main | LF/day | DOT field daily | WSDOT 100-800, normal 300 LF/day |  | WSDOT | Production
UT-HDD | Utilities | HDD ream & pullback (12 in reamer, sand/dirt, 40 gpm) | LF/hr | Trade example (derived) | 500 ft bore pullback 3-6 machine hr -> 83-167 ft/hr; ~7 of 10 hours productive; fluid gal/ft = D^2/24.5 |  | DRILLER-BP | Production
UT-JACKBORE | Utilities | Jack and bore (auger boring) | LF/day | DOT field daily | TxDOT 20/40/70 LF/day |  | TXDOT | Production
UT-BURST-50 | Utilities | Pipe bursting, 50-ton rig (4-8 in) | LF/day | Contractor-reported | 300-400 LF/day |  | CLEANER-PB | Production
UT-BURST-100 | Utilities | Pipe bursting, 100-ton rig (8-12 in, to 16 in) | LF/day | Contractor-reported | 500-750 LF/day |  | CLEANER-PB | Production
UT-VACEX | Utilities | Vacuum (hydro) excavation, pure dig time | CY/hr | Measured test (GTI), converted | Water 0.78-2.96 ft3/min -> 1.7-6.6 CY/hr; air 0.43-4.43 ft3/min -> 0.9-9.8 CY/hr |  | GTI-VAC | Production
UT-TRENCH-SMALL | Utilities | Trench with walk-behind / SSL trencher | LF/hr | n/a | No trencher LF/hr source (operating guidance only) |  | CE-TRENCH | Production
UT-TRENCH-CHAIN | Utilities | Trench with ride-on chain trencher | LF/hr | n/a | No trencher LF/hr source |  | CE-TRENCH | Production
UT-PLOW | Utilities | Vibratory cable plow | LF/hr | n/a | No source |  |  | Production
UT-SEWERCLEAN | Utilities | Sewer cleaning / jetting | LF/hr | Duration | Price by duration (no rate source) |  |  | Duration
UT-SHORING-DUR | Utilities | Trench box / plates / shoring on site | days | Duration | Duration = open-trench duration (pipe LF / crew LF per day) + set/move days |  | WSDOT | Duration
FD-PILE-DRIVE | Foundations | Drive piles (crane + hammer + leads spread) | LF/day | DOT field daily median | WisDOT 190-400 median 280; TxDOT 100/150/200 LF/day; NCDOT 2-3 days per bent of 6-10 piles |  | WISDOT;TXDOT;NCDOT | Production
FD-SHEET | Foundations | Drive/extract sheet piling | SF/day | DOT field daily median | WisDOT 220-690 median 340; TxDOT 250/350/650; NCDOT 640 (incl. extraction) |  | WISDOT;TXDOT;NCDOT | Production
FD-SHAFT-SOIL | Foundations | Drill shafts in soil | LF/day | DOT field daily | TxDOT 33/104/203; NCDOT <=60 in 25 LF/day, >60 in 18 |  | TXDOT;NCDOT | Production
FD-SHAFT-ROCK | Foundations | Drill shafts in rock | LF/day | DOT field daily | NCDOT <=60 in 5 LF/day, >60 in 3 |  | NCDOT | Production
LF-GIRDER-PRECAST | Lifting | Erect precast bridge girders | EA/day | DOT field daily median | WisDOT 5-8, median 6 |  | WISDOT | Production
LF-STEEL-BEAM | Lifting | Erect structural steel bridge beams | EA/day | DOT field daily | WisDOT 6-12 EA/day |  | WISDOT | Production
LF-TOWER-LIFTS | Lifting | Tower crane hook (lifts per hour) | lifts/hr | Measured study, derived | >50% of lifts <4 min; effective crane time 70-75% -> ~10-12 lifts/hr theoretical; precast much lower |  | VTT-CRANE | Production
LF-CRANE-DUR | Lifting | Mobile crane on site (picks, setting) | hr/day | Duration | Duration = pieces / pieces per day + mob/assembly; hourly minimums apply |  | NTXC;CFCS | Duration
LF-AWP-DUR | Lifting | Aerial work platform on site | days | Duration | Duration = trade crew duration served (finishes, MEP, envelope) |  | COSTARS | Duration
LF-TH-DUR | Lifting | Telehandler on site | days | Duration | Duration = trade crew duration served (framing, masonry, roofing, MEP) |  | DOZR-TH | Duration
LF-FK-DUR | Lifting | Forklift on site | days | Duration | Duration of material-handling need |  |  | Duration
DM-PAVE-CONC | Demolition | Remove concrete pavement | SY/day | DOT field daily median | WisDOT 410-2,500 median 1,000; TxDOT 1,510/1,974/4,000; WSDOT 600 SY/day |  | WISDOT;TXDOT;WSDOT | Production
DM-PAVE-ASPH | Demolition | Remove asphalt pavement | SY/day | DOT field daily | WSDOT 2,500-3,000 SY/day |  | WSDOT | Production
DM-CURB | Demolition | Remove concrete curb & gutter | LF/day | DOT field daily | WSDOT 1,200 LF/day |  | WSDOT | Production
DM-BLDG | Demolition | Building demolition (high-reach / excavator) | SF/day | n/a | No building demolition SF/day source |  |  | Production
SITE-HYDROSEED | Site | Hydroseed / seed, fertilize & mulch | acre/day | DOT field daily | WSDOT 4-10 acres/day West, normal 5; NCDOT 1-3; 800-gal tank covers 3,485-11,616 SF per load |  | WSDOT;NCDOT;PROFILE-HS | Production
SITE-DUR | Site | Site facility / temporary item on site | months | Duration | Duration = project or phase duration |  |  | Duration
SP-AIR-DUR | Site | Compressor on site (tools) | days | Duration | Duration = tool-using activity duration |  | EW-TIME | Duration
SP-GEN-DUR | Site | Generator / welder on site | days | Duration | Duration = powered activity or project phase; 24/7 standby power = 3 shifts |  | EW-TIME | Duration
SP-LIGHT-DUR | Site | Light tower on site | nights | Duration | Duration = night-shift duration |  |  | Duration
SP-HEAT-DUR | Site | Temporary heat | days | Duration | Duration = cold-weather protection period |  |  | Duration
SP-PUMP-DUR | Site | Dewatering pump | days | Duration | Duration = excavation open below water table; often 24 hr/day |  | EW-TIME | Duration

## Production
Equip_ID | Activity_ID | Size_class | Activity_name | Input_capacity | Input_unit | Prod_low | Prod_typical | Prod_high | Unit | Basis | Default_conditions | Calc_shown | Source_ids | Confidence | Flags
DZ-CRAWL-D1 | EW-STRIP | D1 class (~80 hp) | Strip topsoil with dozer (short push, 50 ft) | 1.99 | LCY blade capacity (SAE J1265) | 151.4905 | 189.3631 | 302.981 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 1.99 LCY blade (Cat D1 std blade 1.99 yd3 (LGP 2.17)) x 60/0.393 x 0.83 x 1.0 x 0.75 = 189.4 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D1 | EW-PUSH-100 | D1 class (~80 hp) | Dozer push / bulk doze, 100 ft average push | 1.99 | LCY blade capacity (SAE J1265) | 80.8979 | 101.1224 | 161.7958 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Typ: 1.99 LCY blade (Cat D1 std blade 1.99 yd3 (LGP 2.17)) x 60/0.735 x 0.83 x 1.0 x 0.75 = 101.1 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D1 | EW-SPREAD | D1 class (~80 hp) | Spread dumped fill / topsoil with dozer (50 ft, loose material) | 1.99 | LCY blade capacity (SAE J1265) | 181.7886 | 227.2358 | 363.5772 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 1.99 LCY blade (Cat D1 std blade 1.99 yd3 (LGP 2.17)) x 60/0.393 x 0.83 x 1.2 x 0.75 = 227.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D1 | EW-RGRADE | D1 class (~80 hp) | Rough grade with dozer | [5 empty] | SY/hr | n/a |  | No dozer grading rate source | FM5434 | D | Needs production rate
DZ-CRAWL-D2 | EW-STRIP | D2 class (85+ hp) | Strip topsoil with dozer (short push, 50 ft) | 2.59 | LCY blade capacity (SAE J1265) | 197.166 | 246.4575 | 394.3321 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 2.59 LCY blade (Cat D2 std 2.59 yd3 (LGP 2.42)) x 60/0.393 x 0.83 x 1.0 x 0.75 = 246.5 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D2 | EW-PUSH-100 | D2 class (85+ hp) | Dozer push / bulk doze, 100 ft average push | 2.59 | LCY blade capacity (SAE J1265) | 105.2892 | 131.6115 | 210.5784 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Typ: 2.59 LCY blade (Cat D2 std 2.59 yd3 (LGP 2.42)) x 60/0.735 x 0.83 x 1.0 x 0.75 = 131.6 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D2 | EW-SPREAD | D2 class (85+ hp) | Spread dumped fill / topsoil with dozer (50 ft, loose material) | 2.59 | LCY blade capacity (SAE J1265) | 236.5992 | 295.7491 | 473.1985 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 2.59 LCY blade (Cat D2 std 2.59 yd3 (LGP 2.42)) x 60/0.393 x 0.83 x 1.2 x 0.75 = 295.7 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D2 | EW-RGRADE | D2 class (85+ hp) | Rough grade with dozer | [5 empty] | SY/hr | n/a |  | No dozer grading rate source | FM5434 | D | Needs production rate
DZ-CRAWL-D3 | EW-STRIP | D3 class (~100-104 hp, 20-24k lb) | Strip topsoil with dozer (short push, 50 ft) | 2.86 | LCY blade capacity (SAE J1265) | 217.72 | 272.15 | 435.44 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 2.86 LCY blade (Cat D3 std 2.86 yd3 (LGP 3.06)) x 60/0.393 x 0.83 x 1.0 x 0.75 = 272.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D3 | EW-PUSH-100 | D3 class (~100-104 hp, 20-24k lb) | Dozer push / bulk doze, 100 ft average push | 2.86 | LCY blade capacity (SAE J1265) | 116.2653 | 145.3316 | 232.5306 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Typ: 2.86 LCY blade (Cat D3 std 2.86 yd3 (LGP 3.06)) x 60/0.735 x 0.83 x 1.0 x 0.75 = 145.3 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D3 | EW-PUSH-200 | D3 class (~100-104 hp, 20-24k lb) | Dozer push, 200 ft average push | 2.86 | LCY blade capacity (SAE J1265) | 60.1795 | 75.2244 | 120.3591 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.49x88) + 200/(4.97x88)) x E x factors; cycle = 1.420 min. Typ: 2.86 LCY blade (Cat D3 std 2.86 yd3 (LGP 3.06)) x 60/1.420 x 0.83 x 1.0 x 0.75 = 75.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D3 | EW-SPREAD | D3 class (~100-104 hp, 20-24k lb) | Spread dumped fill / topsoil with dozer (50 ft, loose material) | 2.86 | LCY blade capacity (SAE J1265) | 261.264 | 326.58 | 522.5281 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 2.86 LCY blade (Cat D3 std 2.86 yd3 (LGP 3.06)) x 60/0.393 x 0.83 x 1.2 x 0.75 = 326.6 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D3 | EW-RGRADE | D3 class (~100-104 hp, 20-24k lb) | Rough grade with dozer | [5 empty] | SY/hr | n/a |  | No dozer grading rate source | FM5434 | D | Needs production rate
DZ-CRAWL-D4 | EW-CLR-MED | D4 class (~130 hp, ~30k lb) | Clear & grub with medium tractor dozer (straight blade) |  |  | 0.1 | 0.2 | 0.4 | acre/hr | Handbook ideal (FM Table 2-1) | Medium tractor, straight blade; low = heavy (>=18 in), typ = medium (12-18 in), high = light (<=12 in) vegetation | acre/hr = 1 / hr per acre: 1/10.0, 1/5.0, 1/2.5. Strip-type +60% time; grubbing +25%. Tractor-size mapping (D4-D7 medium, D8+ heavy) is an inference. | FM5434 | B
DZ-CRAWL-D4 | EW-STRIP | D4 class (~130 hp, ~30k lb) | Strip topsoil with dozer (short push, 50 ft) |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Per 1.0 LCY of blade (typ): 95.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-CRAWL-D4 | EW-PUSH-100 | D4 class (~130 hp, ~30k lb) | Dozer push / bulk doze, 100 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Per 1.0 LCY of blade (typ): 50.8 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-CRAWL-D4 | EW-PUSH-200 | D4 class (~130 hp, ~30k lb) | Dozer push, 200 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.49x88) + 200/(4.97x88)) x E x factors; cycle = 1.420 min. Per 1.0 LCY of blade (typ): 26.3 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-CRAWL-D4 | EW-SPREAD | D4 class (~130 hp, ~30k lb) | Spread dumped fill / topsoil with dozer (50 ft, loose material) |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Per 1.0 LCY of blade (typ): 114.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-CRAWL-D4 | EW-RGRADE | D4 class (~130 hp, ~30k lb) | Rough grade with dozer | [5 empty] | SY/hr | n/a |  | No dozer grading rate source | FM5434 | D | Needs production rate
DZ-CRAWL-D5 | EW-CLR-MED | D5 class (~170 hp, ~40k lb) | Clear & grub with medium tractor dozer (straight blade) |  |  | 0.1 | 0.2 | 0.4 | acre/hr | Handbook ideal (FM Table 2-1) | Medium tractor, straight blade; low = heavy (>=18 in), typ = medium (12-18 in), high = light (<=12 in) vegetation | acre/hr = 1 / hr per acre: 1/10.0, 1/5.0, 1/2.5. Strip-type +60% time; grubbing +25%. Tractor-size mapping (D4-D7 medium, D8+ heavy) is an inference. | FM5434 | B
DZ-CRAWL-D5 | EW-STRIP | D5 class (~170 hp, ~40k lb) | Strip topsoil with dozer (short push, 50 ft) | 4.6 | LCY blade capacity (SAE J1265) | 350.1791 | 437.7238 | 700.3581 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 4.6 LCY blade (Cat D5 VPAT 4.6 yd3 (LGP VPAT 5.5; push-arm SU 5.6)) x 60/0.393 x 0.83 x 1.0 x 0.75 = 437.7 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D5 | EW-PUSH-100 | D5 class (~170 hp, ~40k lb) | Dozer push / bulk doze, 100 ft average push | 4.6 | LCY blade capacity (SAE J1265) | 187.0001 | 233.7502 | 374.0003 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Typ: 4.6 LCY blade (Cat D5 VPAT 4.6 yd3 (LGP VPAT 5.5; push-arm SU 5.6)) x 60/0.735 x 0.83 x 1.0 x 0.75 = 233.8 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D5 | EW-PUSH-200 | D5 class (~170 hp, ~40k lb) | Dozer push, 200 ft average push | 4.6 | LCY blade capacity (SAE J1265) | 96.7922 | 120.9903 | 193.5845 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.49x88) + 200/(4.97x88)) x E x factors; cycle = 1.420 min. Typ: 4.6 LCY blade (Cat D5 VPAT 4.6 yd3 (LGP VPAT 5.5; push-arm SU 5.6)) x 60/1.420 x 0.83 x 1.0 x 0.75 = 121.0 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D5 | EW-PUSH-300 | D5 class (~170 hp, ~40k lb) | Dozer push, 300 ft average push | 4.6 | LCY blade capacity (SAE J1265) | 65.2945 | 81.6181 | 130.589 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 300 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 300/(2.49x88) + 300/(4.97x88)) x E x factors; cycle = 2.105 min. Typ: 4.6 LCY blade (Cat D5 VPAT 4.6 yd3 (LGP VPAT 5.5; push-arm SU 5.6)) x 60/2.105 x 0.83 x 1.0 x 0.75 = 81.6 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D5 | EW-SPREAD | D5 class (~170 hp, ~40k lb) | Spread dumped fill / topsoil with dozer (50 ft, loose material) | 4.6 | LCY blade capacity (SAE J1265) | 420.2149 | 525.2686 | 840.4297 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 4.6 LCY blade (Cat D5 VPAT 4.6 yd3 (LGP VPAT 5.5; push-arm SU 5.6)) x 60/0.393 x 0.83 x 1.2 x 0.75 = 525.3 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D5 | EW-RGRADE | D5 class (~170 hp, ~40k lb) | Rough grade with dozer | [5 empty] | SY/hr | n/a |  | No dozer grading rate source | FM5434 | D | Needs production rate
DZ-CRAWL-D6 | EW-CLR-MED | D6 class (~215-240 hp, ~50k lb) | Clear & grub with medium tractor dozer (straight blade) |  |  | 0.1 | 0.2 | 0.4 | acre/hr | Handbook ideal (FM Table 2-1) | Medium tractor, straight blade; low = heavy (>=18 in), typ = medium (12-18 in), high = light (<=12 in) vegetation | acre/hr = 1 / hr per acre: 1/10.0, 1/5.0, 1/2.5. Strip-type +60% time; grubbing +25%. Tractor-size mapping (D4-D7 medium, D8+ heavy) is an inference. | FM5434 | B
DZ-CRAWL-D6 | EW-STRIP | D6 class (~215-240 hp, ~50k lb) | Strip topsoil with dozer (short push, 50 ft) | 7.5 | LCY blade capacity (SAE J1265) | 570.9441 | 713.6801 | 1141.8882 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 7.5 LCY blade (Cat D6 SU 7.5 yd3 (VPAT 5.4; angle 5.5; LGP-36 S 5.0)) x 60/0.393 x 0.83 x 1.0 x 0.75 = 713.7 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D6 | EW-PUSH-100 | D6 class (~215-240 hp, ~50k lb) | Dozer push / bulk doze, 100 ft average push | 7.5 | LCY blade capacity (SAE J1265) | 304.8915 | 381.1144 | 609.783 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Typ: 7.5 LCY blade (Cat D6 SU 7.5 yd3 (VPAT 5.4; angle 5.5; LGP-36 S 5.0)) x 60/0.735 x 0.83 x 1.0 x 0.75 = 381.1 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D6 | EW-PUSH-200 | D6 class (~215-240 hp, ~50k lb) | Dozer push, 200 ft average push | 7.5 | LCY blade capacity (SAE J1265) | 157.8134 | 197.2668 | 315.6269 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.49x88) + 200/(4.97x88)) x E x factors; cycle = 1.420 min. Typ: 7.5 LCY blade (Cat D6 SU 7.5 yd3 (VPAT 5.4; angle 5.5; LGP-36 S 5.0)) x 60/1.420 x 0.83 x 1.0 x 0.75 = 197.3 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D6 | EW-PUSH-300 | D6 class (~215-240 hp, ~50k lb) | Dozer push, 300 ft average push | 7.5 | LCY blade capacity (SAE J1265) | 106.4585 | 133.0731 | 212.9169 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 300 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 300/(2.49x88) + 300/(4.97x88)) x E x factors; cycle = 2.105 min. Typ: 7.5 LCY blade (Cat D6 SU 7.5 yd3 (VPAT 5.4; angle 5.5; LGP-36 S 5.0)) x 60/2.105 x 0.83 x 1.0 x 0.75 = 133.1 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D6 | EW-SPREAD | D6 class (~215-240 hp, ~50k lb) | Spread dumped fill / topsoil with dozer (50 ft, loose material) | 7.5 | LCY blade capacity (SAE J1265) | 685.1329 | 856.4162 | 1370.2659 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 7.5 LCY blade (Cat D6 SU 7.5 yd3 (VPAT 5.4; angle 5.5; LGP-36 S 5.0)) x 60/0.393 x 0.83 x 1.2 x 0.75 = 856.4 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D6 | EW-RGRADE | D6 class (~215-240 hp, ~50k lb) | Rough grade with dozer | [5 empty] | SY/hr | n/a |  | No dozer grading rate source | FM5434 | D | Needs production rate
DZ-CRAWL-D6-XE | EW-STRIP | D6 XE (215 hp) | Strip topsoil with dozer (short push, 50 ft) |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Per 1.0 LCY of blade (typ): 95.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-CRAWL-D6-XE | EW-PUSH-100 | D6 XE (215 hp) | Dozer push / bulk doze, 100 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Per 1.0 LCY of blade (typ): 50.8 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-CRAWL-D6-XE | EW-PUSH-200 | D6 XE (215 hp) | Dozer push, 200 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.49x88) + 200/(4.97x88)) x E x factors; cycle = 1.420 min. Per 1.0 LCY of blade (typ): 26.3 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-CRAWL-D6-XE | EW-PUSH-300 | D6 XE (215 hp) | Dozer push, 300 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 300 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 300/(2.49x88) + 300/(4.97x88)) x E x factors; cycle = 2.105 min. Per 1.0 LCY of blade (typ): 17.7 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-CRAWL-D6-XE | EW-SPREAD | D6 XE (215 hp) | Spread dumped fill / topsoil with dozer (50 ft, loose material) |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Per 1.0 LCY of blade (typ): 114.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-CRAWL-D6-XE | EW-RGRADE | D6 XE (215 hp) | Rough grade with dozer | [5 empty] | SY/hr | n/a |  | No dozer grading rate source | FM5434 | D | Needs production rate
DZ-CRAWL-D6-LGP | EW-STRIP | D6 LGP | Strip topsoil with dozer (short push, 50 ft) | 7.6 | LCY blade capacity (SAE J1265) | 578.5567 | 723.1959 | 1157.1134 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 7.6 LCY blade (Cat D6 LGP SU 7.6 yd3 (LGP VPAT 5.9-6.5)) x 60/0.393 x 0.83 x 1.0 x 0.75 = 723.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D6-LGP | EW-PUSH-100 | D6 LGP | Dozer push / bulk doze, 100 ft average push | 7.6 | LCY blade capacity (SAE J1265) | 308.9567 | 386.1959 | 617.9135 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Typ: 7.6 LCY blade (Cat D6 LGP SU 7.6 yd3 (LGP VPAT 5.9-6.5)) x 60/0.735 x 0.83 x 1.0 x 0.75 = 386.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D6-LGP | EW-SPREAD | D6 LGP | Spread dumped fill / topsoil with dozer (50 ft, loose material) | 7.6 | LCY blade capacity (SAE J1265) | 694.268 | 867.8351 | 1388.5361 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 7.6 LCY blade (Cat D6 LGP SU 7.6 yd3 (LGP VPAT 5.9-6.5)) x 60/0.393 x 0.83 x 1.2 x 0.75 = 867.8 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D6-LGP | EW-RGRADE | D6 LGP | Rough grade with dozer | [5 empty] | SY/hr | n/a |  | No dozer grading rate source | FM5434 | D | Needs production rate
DZ-CRAWL-D7 | EW-CLR-MED | D7 class (~265 hp) | Clear & grub with medium tractor dozer (straight blade) |  |  | 0.1 | 0.2 | 0.4 | acre/hr | Handbook ideal (FM Table 2-1) | Medium tractor, straight blade; low = heavy (>=18 in), typ = medium (12-18 in), high = light (<=12 in) vegetation | acre/hr = 1 / hr per acre: 1/10.0, 1/5.0, 1/2.5. Strip-type +60% time; grubbing +25%. Tractor-size mapping (D4-D7 medium, D8+ heavy) is an inference. | FM5434 | B
DZ-CRAWL-D7 | EW-STRIP | D7 class (~265 hp) | Strip topsoil with dozer (short push, 50 ft) | 9.7 | LCY blade capacity (SAE J1265) | 738.4211 | 923.0263 | 1476.8421 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 9.7 LCY blade (Cat D7 (Tier 3, MX page) SU 9.7 yd3 (S 8.1)) x 60/0.393 x 0.83 x 1.0 x 0.75 = 923.0 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D7 | EW-PUSH-100 | D7 class (~265 hp) | Dozer push / bulk doze, 100 ft average push | 9.7 | LCY blade capacity (SAE J1265) | 394.3264 | 492.908 | 788.6527 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Typ: 9.7 LCY blade (Cat D7 (Tier 3, MX page) SU 9.7 yd3 (S 8.1)) x 60/0.735 x 0.83 x 1.0 x 0.75 = 492.9 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D7 | EW-PUSH-200 | D7 class (~265 hp) | Dozer push, 200 ft average push | 9.7 | LCY blade capacity (SAE J1265) | 204.1054 | 255.1317 | 408.2108 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.49x88) + 200/(4.97x88)) x E x factors; cycle = 1.420 min. Typ: 9.7 LCY blade (Cat D7 (Tier 3, MX page) SU 9.7 yd3 (S 8.1)) x 60/1.420 x 0.83 x 1.0 x 0.75 = 255.1 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D7 | EW-PUSH-300 | D7 class (~265 hp) | Dozer push, 300 ft average push | 9.7 | LCY blade capacity (SAE J1265) | 137.6863 | 172.1078 | 275.3725 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 300 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 300/(2.49x88) + 300/(4.97x88)) x E x factors; cycle = 2.105 min. Typ: 9.7 LCY blade (Cat D7 (Tier 3, MX page) SU 9.7 yd3 (S 8.1)) x 60/2.105 x 0.83 x 1.0 x 0.75 = 172.1 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D7 | EW-SPREAD | D7 class (~265 hp) | Spread dumped fill / topsoil with dozer (50 ft, loose material) | 9.7 | LCY blade capacity (SAE J1265) | 886.1053 | 1107.6316 | 1772.2105 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 9.7 LCY blade (Cat D7 (Tier 3, MX page) SU 9.7 yd3 (S 8.1)) x 60/0.393 x 0.83 x 1.2 x 0.75 = 1,107.6 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D7 | EW-RGRADE | D7 class (~265 hp) | Rough grade with dozer | [5 empty] | SY/hr | n/a |  | No dozer grading rate source | FM5434 | D | Needs production rate
DZ-CRAWL-D8 | EW-CLR-HVY | D8 class (~363 hp) | Clear & grub with heavy tractor dozer (straight blade) |  |  | 0.125 | 0.33333 | 0.66667 | acre/hr | Handbook ideal (FM Table 2-1) | Heavy tractor, straight blade; low = heavy (>=18 in), typ = medium (12-18 in), high = light (<=12 in) vegetation | acre/hr = 1 / hr per acre: 1/8.0, 1/3.0, 1/1.5. Strip-type +60% time; grubbing +25%. Tractor-size mapping (D4-D7 medium, D8+ heavy) is an inference. | FM5434 | B
DZ-CRAWL-D8 | EW-PUSH-100 | D8 class (~363 hp) | Dozer push / bulk doze, 100 ft average push | 13.47 | LCY blade capacity (SAE J1265) | 547.5852 | 684.4815 | 1095.1703 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Typ: 13.47 LCY blade (Cat D8 SU 13.47 yd3 (LGP SU 12.9)) x 60/0.735 x 0.83 x 1.0 x 0.75 = 684.5 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D8 | EW-PUSH-200 | D8 class (~363 hp) | Dozer push, 200 ft average push | 13.47 | LCY blade capacity (SAE J1265) | 283.433 | 354.2912 | 566.8659 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.49x88) + 200/(4.97x88)) x E x factors; cycle = 1.420 min. Typ: 13.47 LCY blade (Cat D8 SU 13.47 yd3 (LGP SU 12.9)) x 60/1.420 x 0.83 x 1.0 x 0.75 = 354.3 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D8 | EW-PUSH-300 | D8 class (~363 hp) | Dozer push, 300 ft average push | 13.47 | LCY blade capacity (SAE J1265) | 191.1994 | 238.9992 | 382.3988 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 300 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 300/(2.49x88) + 300/(4.97x88)) x E x factors; cycle = 2.105 min. Typ: 13.47 LCY blade (Cat D8 SU 13.47 yd3 (LGP SU 12.9)) x 60/2.105 x 0.83 x 1.0 x 0.75 = 239.0 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D8 | EW-SPREAD | D8 class (~363 hp) | Spread dumped fill / topsoil with dozer (50 ft, loose material) | 13.47 | LCY blade capacity (SAE J1265) | 1230.4988 | 1538.1234 | 2460.9975 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Typ: 13.47 LCY blade (Cat D8 SU 13.47 yd3 (LGP SU 12.9)) x 60/0.393 x 0.83 x 1.2 x 0.75 = 1,538.1 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D8 | EW-RIP | D8 class (~363 hp) | Rip rock with single-shank ripper (large dozer) |  |  | 150 | 300 | 500 | BCY/hr | Indicative published (single tractor, model not stated) | Low 8,500 fps / typ 6,500 fps / high 5,000 fps seismic velocity; first gear ~1-1.5 mph | Geometrics indicative curve; applied to all large dozers (not model-specific). Pass-geometry check D11 single shank 1.5 ft x 3 ft x 225 ft at 0.3 mph, 24 s turn -> ~210 BCY/hr | GEOM;FM5434;WYDOT-RIP | C | Not model-specific; Cat rippability charts needed
DZ-CRAWL-D9 | EW-CLR-HVY | D9 class (~452 hp) | Clear & grub with heavy tractor dozer (straight blade) |  |  | 0.125 | 0.33333 | 0.66667 | acre/hr | Handbook ideal (FM Table 2-1) | Heavy tractor, straight blade; low = heavy (>=18 in), typ = medium (12-18 in), high = light (<=12 in) vegetation | acre/hr = 1 / hr per acre: 1/8.0, 1/3.0, 1/1.5. Strip-type +60% time; grubbing +25%. Tractor-size mapping (D4-D7 medium, D8+ heavy) is an inference. | FM5434 | B
DZ-CRAWL-D9 | EW-PUSH-100 | D9 class (~452 hp) | Dozer push / bulk doze, 100 ft average push | 17.8 | LCY blade capacity (SAE J1265) | 662.1225 | 827.6531 | 1324.2449 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; row-specific gear speeds D9 F1 2.2 / R2 4.8 mph [CAT-DOZ-PG]; fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.2x88) + 100/(4.8x88)) x E x factors; cycle = 0.803 min. Typ: 17.8 LCY blade (Cat D9 SU 17.8 yd3 (U 21.7)) x 60/0.803 x 0.83 x 1.0 x 0.75 = 827.7 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D9 | EW-PUSH-200 | D9 class (~452 hp) | Dozer push, 200 ft average push | 17.8 | LCY blade capacity (SAE J1265) | 341.6957 | 427.1197 | 683.3915 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; row-specific gear speeds D9 F1 2.2 / R2 4.8 mph [CAT-DOZ-PG]; fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.2x88) + 200/(4.8x88)) x E x factors; cycle = 1.557 min. Typ: 17.8 LCY blade (Cat D9 SU 17.8 yd3 (U 21.7)) x 60/1.557 x 0.83 x 1.0 x 0.75 = 427.1 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D9 | EW-PUSH-300 | D9 class (~452 hp) | Dozer push, 300 ft average push | 17.8 | LCY blade capacity (SAE J1265) | 230.2627 | 287.8284 | 460.5254 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 300 ft; row-specific gear speeds D9 F1 2.2 / R2 4.8 mph [CAT-DOZ-PG]; fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 300/(2.2x88) + 300/(4.8x88)) x E x factors; cycle = 2.310 min. Typ: 17.8 LCY blade (Cat D9 SU 17.8 yd3 (U 21.7)) x 60/2.310 x 0.83 x 1.0 x 0.75 = 287.8 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D9 | EW-RIP | D9 class (~452 hp) | Rip rock with single-shank ripper (large dozer) |  |  | 150 | 300 | 500 | BCY/hr | Indicative published (single tractor, model not stated) | Low 8,500 fps / typ 6,500 fps / high 5,000 fps seismic velocity; first gear ~1-1.5 mph | Geometrics indicative curve; applied to all large dozers (not model-specific). Pass-geometry check D11 single shank 1.5 ft x 3 ft x 225 ft at 0.3 mph, 24 s turn -> ~210 BCY/hr | GEOM;FM5434;WYDOT-RIP | C | Not model-specific; Cat rippability charts needed
DZ-CRAWL-D10 | EW-PUSH-100 | D10 class (~602 hp) | Dozer push / bulk doze, 100 ft average push | 24.2 | LCY blade capacity (SAE J1265) | 1022.0907 | 1277.6134 | 2044.1814 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; row-specific gear speeds D10 F1.0 2.5 / R2.0 5.6 mph [CAT-DOZ-PG]; fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.5x88) + 100/(5.6x88)) x E x factors; cycle = 0.707 min. Typ: 24.2 LCY blade (Cat D10 10SU 24.2 yd3 (10U 28.7)) x 60/0.707 x 0.83 x 1.0 x 0.75 = 1,277.6 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D10 | EW-PUSH-200 | D10 class (~602 hp) | Dozer push, 200 ft average push | 24.2 | LCY blade capacity (SAE J1265) | 529.7659 | 662.2073 | 1059.5317 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; row-specific gear speeds D10 F1.0 2.5 / R2.0 5.6 mph [CAT-DOZ-PG]; fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.5x88) + 200/(5.6x88)) x E x factors; cycle = 1.365 min. Typ: 24.2 LCY blade (Cat D10 10SU 24.2 yd3 (10U 28.7)) x 60/1.365 x 0.83 x 1.0 x 0.75 = 662.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D10 | EW-PUSH-300 | D10 class (~602 hp) | Dozer push, 300 ft average push | 24.2 | LCY blade capacity (SAE J1265) | 357.5431 | 446.9288 | 715.0861 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 300 ft; row-specific gear speeds D10 F1.0 2.5 / R2.0 5.6 mph [CAT-DOZ-PG]; fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 300/(2.5x88) + 300/(5.6x88)) x E x factors; cycle = 2.022 min. Typ: 24.2 LCY blade (Cat D10 10SU 24.2 yd3 (10U 28.7)) x 60/2.022 x 0.83 x 1.0 x 0.75 = 446.9 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D10 | EW-RIP | D10 class (~602 hp) | Rip rock with single-shank ripper (large dozer) |  |  | 150 | 300 | 500 | BCY/hr | Indicative published (single tractor, model not stated) | Low 8,500 fps / typ 6,500 fps / high 5,000 fps seismic velocity; first gear ~1-1.5 mph | Geometrics indicative curve; applied to all large dozers (not model-specific). Pass-geometry check D11 single shank 1.5 ft x 3 ft x 225 ft at 0.3 mph, 24 s turn -> ~210 BCY/hr | GEOM;FM5434;WYDOT-RIP | C | Not model-specific; Cat rippability charts needed
DZ-CRAWL-D11 | EW-PUSH-100 | D11 class (~850 hp) | Dozer push / bulk doze, 100 ft average push | 35.6 | LCY blade capacity (SAE J1265) | 1479.5501 | 1849.4376 | 2959.1002 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; row-specific gear speeds D11 F1 2.5 / R2 5.3 mph [CAT-DOZ-PG]; fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.5x88) + 100/(5.3x88)) x E x factors; cycle = 0.719 min. Typ: 35.6 LCY blade (Cat D11 SU 35.6 yd3 (U 45; reclamation U 55; carrydozer 57)) x 60/0.719 x 0.83 x 1.0 x 0.75 = 1,849.4 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D11 | EW-PUSH-200 | D11 class (~850 hp) | Dozer push, 200 ft average push | 35.6 | LCY blade capacity (SAE J1265) | 766.4258 | 958.0322 | 1532.8516 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; row-specific gear speeds D11 F1 2.5 / R2 5.3 mph [CAT-DOZ-PG]; fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.5x88) + 200/(5.3x88)) x E x factors; cycle = 1.388 min. Typ: 35.6 LCY blade (Cat D11 SU 35.6 yd3 (U 45; reclamation U 55; carrydozer 57)) x 60/1.388 x 0.83 x 1.0 x 0.75 = 958.0 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D11 | EW-PUSH-300 | D11 class (~850 hp) | Dozer push, 300 ft average push | 35.6 | LCY blade capacity (SAE J1265) | 517.1608 | 646.4511 | 1034.3217 | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 300 ft; row-specific gear speeds D11 F1 2.5 / R2 5.3 mph [CAT-DOZ-PG]; fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 300/(2.5x88) + 300/(5.3x88)) x E x factors; cycle = 2.057 min. Typ: 35.6 LCY blade (Cat D11 SU 35.6 yd3 (U 45; reclamation U 55; carrydozer 57)) x 60/2.057 x 0.83 x 1.0 x 0.75 = 646.5 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434;CAT-DOZ-PG | C
DZ-CRAWL-D11 | EW-RIP | D11 class (~850 hp) | Rip rock with single-shank ripper (large dozer) |  |  | 150 | 300 | 500 | BCY/hr | Indicative published (single tractor, model not stated) | Low 8,500 fps / typ 6,500 fps / high 5,000 fps seismic velocity; first gear ~1-1.5 mph | Geometrics indicative curve; applied to all large dozers (not model-specific). Pass-geometry check D11 single shank 1.5 ft x 3 ft x 225 ft at 0.3 mph, 24 s turn -> ~210 BCY/hr | GEOM;FM5434;WYDOT-RIP | C | Not model-specific; Cat rippability charts needed
DZ-WHEEL-814 | EW-PUSH-100 | Cat 814 class (~249 hp) | Dozer push / bulk doze, 100 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Per 1.0 LCY of blade (typ): 50.8 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-814 | EW-PUSH-200 | Cat 814 class (~249 hp) | Dozer push, 200 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.49x88) + 200/(4.97x88)) x E x factors; cycle = 1.420 min. Per 1.0 LCY of blade (typ): 26.3 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-814 | EW-SPREAD | Cat 814 class (~249 hp) | Spread dumped fill / topsoil with dozer (50 ft, loose material) |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Per 1.0 LCY of blade (typ): 114.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-824 | EW-PUSH-100 | Cat 824 class (~405 hp) | Dozer push / bulk doze, 100 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Per 1.0 LCY of blade (typ): 50.8 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-824 | EW-PUSH-200 | Cat 824 class (~405 hp) | Dozer push, 200 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.49x88) + 200/(4.97x88)) x E x factors; cycle = 1.420 min. Per 1.0 LCY of blade (typ): 26.3 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-824 | EW-SPREAD | Cat 824 class (~405 hp) | Spread dumped fill / topsoil with dozer (50 ft, loose material) |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Per 1.0 LCY of blade (typ): 114.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-834 | EW-PUSH-100 | Cat 834 class (~496 hp) | Dozer push / bulk doze, 100 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Per 1.0 LCY of blade (typ): 50.8 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-834 | EW-PUSH-200 | Cat 834 class (~496 hp) | Dozer push, 200 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.49x88) + 200/(4.97x88)) x E x factors; cycle = 1.420 min. Per 1.0 LCY of blade (typ): 26.3 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-834 | EW-SPREAD | Cat 834 class (~496 hp) | Spread dumped fill / topsoil with dozer (50 ft, loose material) |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Per 1.0 LCY of blade (typ): 114.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-844 | EW-PUSH-100 | Cat 844 class (~732 hp) | Dozer push / bulk doze, 100 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Per 1.0 LCY of blade (typ): 50.8 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-844 | EW-PUSH-200 | Cat 844 class (~732 hp) | Dozer push, 200 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.49x88) + 200/(4.97x88)) x E x factors; cycle = 1.420 min. Per 1.0 LCY of blade (typ): 26.3 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-844 | EW-SPREAD | Cat 844 class (~732 hp) | Spread dumped fill / topsoil with dozer (50 ft, loose material) |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Per 1.0 LCY of blade (typ): 114.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-854 | EW-PUSH-100 | Cat 854 class (~814 hp) | Dozer push / bulk doze, 100 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 100 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 100/(2.49x88) + 100/(4.97x88)) x E x factors; cycle = 0.735 min. Per 1.0 LCY of blade (typ): 50.8 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-854 | EW-PUSH-200 | Cat 854 class (~814 hp) | Dozer push, 200 ft average push |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 200 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.0; typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 200/(2.49x88) + 200/(4.97x88)) x E x factors; cycle = 1.420 min. Per 1.0 LCY of blade (typ): 26.3 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
DZ-WHEEL-854 | EW-SPREAD | Cat 854 class (~814 hp) | Spread dumped fill / topsoil with dozer (50 ft, loose material) |  | LCY blade capacity (SAE J1265) |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Push distance 50 ft; doze 2.49 / reverse 4.97 mph (Settings B28-B29, KSU example); fixed 0.05 min; material factor 1.2 (loose stockpile); typ = average operator 0.75; low = x0.80 hard-to-drift; high = excellent operator 1.00 x slot dozing 1.20 | LCY/hr = Blade_LCY x 60 / (0.05 + 50/(2.49x88) + 50/(4.97x88)) x E x factors; cycle = 0.393 min. Per 1.0 LCY of blade (typ): 114.2 LCY/hr. Cat push curves NOT obtained - first-principles blade/cycle method; SAE J1265 rated blade capacity used as blade load. | KSU-4;FM5434 | D | Needs blade capacity LCY
EX-MINI-1T | EW-TRENCH-5 | 1-2 t (<=5,000 lb) | Trench excavation, up to ~5 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-MINI-1T | EW-STRUCT | 1-2 t (<=5,000 lb) | Structural excavation (footings, pits; confined swing) |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Per 1.0 CY bucket at 15 s, typ fill 1.0: 151.4 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-MINI-1T | EW-BACKFILL | 1-2 t (<=5,000 lb) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose backfill material; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.85/0.95/1.0 (low/typ/high) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83). Per 1.0 CY bucket at 15 s, typ fill 0.95: 189.2 LCY/hr. | FM5434-8;KSU-3;FM5434;CAT-FILL | D | Needs bucket CY (enter in Input_capacity)
EX-MINI-3T | EW-TRENCH-5 | 3-4 t (5,000-10,000 lb) | Trench excavation, up to ~5 ft deep | 0.15 | CY heaped bucket | 20.0794 | 25.0992 | 27.6091 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/14 x 0.15 x 1.0 x 0.83 x 0.80 x 0.98 = 25.1 BCY/hr. Input bucket = Deere 35G spec-basis bucket 0.11 m3 (0.15 yd3); single value, not a range. | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-35G | C
EX-MINI-3T | EW-STRUCT | 3-4 t (5,000-10,000 lb) | Structural excavation (footings, pits; confined swing) | 0.15 | CY heaped bucket | 19.4647 | 24.3309 | 26.7639 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Typ: 3600/14 x 0.15 x 1.0 x 0.83 x 0.80 x 0.95 = 24.3 BCY/hr. Input bucket = Deere 35G spec-basis bucket 0.11 m3 (0.15 yd3); single value, not a range. | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-35G | C
EX-MINI-3T | EW-BACKFILL | 3-4 t (5,000-10,000 lb) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 0.15 | CY heaped bucket | 27.2121 | 30.4136 | 32.0143 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose backfill material; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.85/0.95/1.0 (low/typ/high) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83). Typ: 3600/14 x 0.15 x 0.95 x 0.83 = 30.4 LCY/hr. Input bucket = Deere 35G spec-basis bucket 0.11 m3 (0.15 yd3); single value, not a range. | FM5434-8;KSU-3;FM5434;CAT-FILL;DEERE-35G | C
EX-MINI-3T | UT-PIPE-WATER | 3-4 t (5,000-10,000 lb) | Lay water main |  |  | 100 | 300 | 800 | LF/day | DOT field daily (crew) | Water main | WSDOT 100-800, normal 300. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT | B
EX-MINI-5T | EW-TRENCH-5 | 5-6 t (10,000-14,000 lb) | Trench excavation, up to ~5 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-MINI-5T | EW-TRENCH-10 | 5-6 t (10,000-14,000 lb) | Trench excavation, 6-10 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-MINI-5T | EW-STRUCT | 5-6 t (10,000-14,000 lb) | Structural excavation (footings, pits; confined swing) |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Per 1.0 CY bucket at 15 s, typ fill 1.0: 151.4 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-MINI-5T | EW-BACKFILL | 5-6 t (10,000-14,000 lb) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose backfill material; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.85/0.95/1.0 (low/typ/high) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83). Per 1.0 CY bucket at 15 s, typ fill 0.95: 189.2 LCY/hr. | FM5434-8;KSU-3;FM5434;CAT-FILL | D | Needs bucket CY (enter in Input_capacity)
EX-MINI-5T | UT-PIPE-WATER | 5-6 t (10,000-14,000 lb) | Lay water main |  |  | 100 | 300 | 800 | LF/day | DOT field daily (crew) | Water main | WSDOT 100-800, normal 300. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT | B
EX-MIDI-8T | EW-CUTLOAD | 7-8 t nominal (~15,400-19,800 lb) | Bulk cut and load trucks (hydraulic excavator) | 0.26 | CY heaped bucket | 35.5145 | 44.3931 | 48.8325 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/14 x 0.26 x 1.0 x 0.83 x 0.80 = 44.4 BCY/hr. Input bucket = Komatsu PC88MR-11 single listed bucket 0.26 yd3 (aggregator). | FM5434-8;KSU-3;FM5434;ALLMACH-PC88 | C
EX-MIDI-8T | EW-MASS | 7-8 t nominal (~15,400-19,800 lb) | Mass excavation, cast to spoil/stockpile (hydraulic excavator) | 0.26 | CY heaped bucket | 35.5145 | 44.3931 | 48.8325 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/14 x 0.26 x 1.0 x 0.83 x 0.80 = 44.4 BCY/hr. Input bucket = Komatsu PC88MR-11 single listed bucket 0.26 yd3 (aggregator). | FM5434-8;KSU-3;FM5434;ALLMACH-PC88 | C
EX-MIDI-8T | EW-TRENCH-5 | 7-8 t nominal (~15,400-19,800 lb) | Trench excavation, up to ~5 ft deep | 0.26 | CY heaped bucket | 34.8042 | 43.5053 | 47.8558 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/14 x 0.26 x 1.0 x 0.83 x 0.80 x 0.98 = 43.5 BCY/hr. Input bucket = Komatsu PC88MR-11 single listed bucket 0.26 yd3 (aggregator). | FM5434-8;KSU-3;FM5434;KSU-T3;ALLMACH-PC88 | C
EX-MIDI-8T | EW-TRENCH-10 | 7-8 t nominal (~15,400-19,800 lb) | Trench excavation, 6-10 ft deep | 0.26 | CY heaped bucket | 34.8042 | 43.5053 | 47.8558 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/14 x 0.26 x 1.0 x 0.83 x 0.80 x 0.98 = 43.5 BCY/hr. Input bucket = Komatsu PC88MR-11 single listed bucket 0.26 yd3 (aggregator). | FM5434-8;KSU-3;FM5434;KSU-T3;ALLMACH-PC88 | C
EX-MIDI-8T | EW-STRUCT | 7-8 t nominal (~15,400-19,800 lb) | Structural excavation (footings, pits; confined swing) | 0.26 | CY heaped bucket | 33.7388 | 42.1735 | 46.3908 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Typ: 3600/14 x 0.26 x 1.0 x 0.83 x 0.80 x 0.95 = 42.2 BCY/hr. Input bucket = Komatsu PC88MR-11 single listed bucket 0.26 yd3 (aggregator). | FM5434-8;KSU-3;FM5434;KSU-T3;ALLMACH-PC88 | C
EX-MIDI-8T | EW-BACKFILL | 7-8 t nominal (~15,400-19,800 lb) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 0.26 | CY heaped bucket | 47.1677 | 52.7169 | 55.4914 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose backfill material; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.85/0.95/1.0 (low/typ/high) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83). Typ: 3600/14 x 0.26 x 0.95 x 0.83 = 52.7 LCY/hr. Input bucket = Komatsu PC88MR-11 single listed bucket 0.26 yd3 (aggregator). | FM5434-8;KSU-3;FM5434;CAT-FILL;ALLMACH-PC88 | C
EX-MIDI-8T | UT-PIPE-STORM | 7-8 t nominal (~15,400-19,800 lb) | Lay storm sewer 12-36 in (excavator-led crew) |  |  | 300 | 800 | 1500 | LF/day | DOT field daily, 8-hr day (crew) | Storm sewer 12-36 in, WSDOT West | WSDOT range 300-1,500, normal 800 (East normal 1,500). Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT | B
EX-MIDI-8T | DM-PAVE-CONC | 7-8 t nominal (~15,400-19,800 lb) | Remove concrete pavement |  |  | 410 | 1000 | 4000 | SY/day | DOT field daily median (crew) | Remove concrete pavement | Typ = median of WisDOT 1,000, TxDOT 1,974, WSDOT 600; low 410; high 4,000. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;WSDOT | A
EX-MIDI-10T | EW-CUTLOAD | 9-10 t (~19,800-23,000 lb) | Bulk cut and load trucks (hydraulic excavator) |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Per 1.0 CY bucket at 15 s, typ fill 1.0: 159.4 BCY/hr. | FM5434-8;KSU-3;FM5434 | D | Needs bucket CY (enter in Input_capacity)
EX-MIDI-10T | EW-MASS | 9-10 t (~19,800-23,000 lb) | Mass excavation, cast to spoil/stockpile (hydraulic excavator) |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Per 1.0 CY bucket at 15 s, typ fill 1.0: 159.4 BCY/hr. | FM5434-8;KSU-3;FM5434 | D | Needs bucket CY (enter in Input_capacity)
EX-MIDI-10T | EW-TRENCH-5 | 9-10 t (~19,800-23,000 lb) | Trench excavation, up to ~5 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-MIDI-10T | EW-TRENCH-10 | 9-10 t (~19,800-23,000 lb) | Trench excavation, 6-10 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-MIDI-10T | EW-STRUCT | 9-10 t (~19,800-23,000 lb) | Structural excavation (footings, pits; confined swing) |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Per 1.0 CY bucket at 15 s, typ fill 1.0: 151.4 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-MIDI-10T | EW-BACKFILL | 9-10 t (~19,800-23,000 lb) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose backfill material; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.85/0.95/1.0 (low/typ/high) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83). Per 1.0 CY bucket at 15 s, typ fill 0.95: 189.2 LCY/hr. | FM5434-8;KSU-3;FM5434;CAT-FILL | D | Needs bucket CY (enter in Input_capacity)
EX-MIDI-10T | UT-PIPE-STORM | 9-10 t (~19,800-23,000 lb) | Lay storm sewer 12-36 in (excavator-led crew) |  |  | 300 | 800 | 1500 | LF/day | DOT field daily, 8-hr day (crew) | Storm sewer 12-36 in, WSDOT West | WSDOT range 300-1,500, normal 800 (East normal 1,500). Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT | B
EX-CRAWL-13T | EW-CUTLOAD | 13-15 t (~30,000-34,000 lb) | Bulk cut and load trucks (hydraulic excavator) | 0.75 | CY heaped bucket | 102.4457 | 128.0571 | 140.8629 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/14 x 0.75 x 1.0 x 0.83 x 0.80 = 128.1 BCY/hr. Input bucket = midpoint of typical GP 0.5-1.0 yd3 (Deere 135 P HD 0.47-0.99). | FM5434-8;KSU-3;FM5434;DEERE-135P | C
EX-CRAWL-13T | EW-MASS | 13-15 t (~30,000-34,000 lb) | Mass excavation, cast to spoil/stockpile (hydraulic excavator) | 0.75 | CY heaped bucket | 102.4457 | 128.0571 | 140.8629 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/14 x 0.75 x 1.0 x 0.83 x 0.80 = 128.1 BCY/hr. Input bucket = midpoint of typical GP 0.5-1.0 yd3 (Deere 135 P HD 0.47-0.99). | FM5434-8;KSU-3;FM5434;DEERE-135P | C
EX-CRAWL-13T | EW-TRENCH-5 | 13-15 t (~30,000-34,000 lb) | Trench excavation, up to ~5 ft deep | 0.75 | CY heaped bucket | 100.3968 | 125.496 | 138.0456 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/14 x 0.75 x 1.0 x 0.83 x 0.80 x 0.98 = 125.5 BCY/hr. Input bucket = midpoint of typical GP 0.5-1.0 yd3 (Deere 135 P HD 0.47-0.99). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-135P | C
EX-CRAWL-13T | EW-TRENCH-10 | 13-15 t (~30,000-34,000 lb) | Trench excavation, 6-10 ft deep | 0.75 | CY heaped bucket | 100.3968 | 125.496 | 138.0456 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/14 x 0.75 x 1.0 x 0.83 x 0.80 x 0.98 = 125.5 BCY/hr. Input bucket = midpoint of typical GP 0.5-1.0 yd3 (Deere 135 P HD 0.47-0.99). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-135P | C
EX-CRAWL-13T | EW-STRUCT | 13-15 t (~30,000-34,000 lb) | Structural excavation (footings, pits; confined swing) | 0.75 | CY heaped bucket | 97.3234 | 121.6543 | 133.8197 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Typ: 3600/14 x 0.75 x 1.0 x 0.83 x 0.80 x 0.95 = 121.7 BCY/hr. Input bucket = midpoint of typical GP 0.5-1.0 yd3 (Deere 135 P HD 0.47-0.99). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-135P | C
EX-CRAWL-13T | EW-BACKFILL | 13-15 t (~30,000-34,000 lb) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 0.75 | CY heaped bucket | 136.0607 | 152.0679 | 160.0714 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose backfill material; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.85/0.95/1.0 (low/typ/high) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83). Typ: 3600/14 x 0.75 x 0.95 x 0.83 = 152.1 LCY/hr. Input bucket = midpoint of typical GP 0.5-1.0 yd3 (Deere 135 P HD 0.47-0.99). | FM5434-8;KSU-3;FM5434;CAT-FILL;DEERE-135P | C
EX-CRAWL-13T | UT-PIPE-STORM | 13-15 t (~30,000-34,000 lb) | Lay storm sewer 12-36 in (excavator-led crew) |  |  | 300 | 800 | 1500 | LF/day | DOT field daily, 8-hr day (crew) | Storm sewer 12-36 in, WSDOT West | WSDOT range 300-1,500, normal 800 (East normal 1,500). Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT | B
EX-CRAWL-13T | DM-PAVE-CONC | 13-15 t (~30,000-34,000 lb) | Remove concrete pavement |  |  | 410 | 1000 | 4000 | SY/day | DOT field daily median (crew) | Remove concrete pavement | Typ = median of WisDOT 1,000, TxDOT 1,974, WSDOT 600; low 410; high 4,000. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;WSDOT | A
EX-CRAWL-17T | EW-CUTLOAD | 16-18 t (~38,000-40,000 lb) | Bulk cut and load trucks (hydraulic excavator) | 0.899 | CY heaped bucket | 122.7983 | 153.4978 | 168.8476 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/14 x 0.899 x 1.0 x 0.83 x 0.80 = 153.5 BCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-13T (30,400 lb, 0.75) and EX-CRAWL-20T (48,500 lb, 1.025). | FM5434-8;KSU-3;FM5434;DEERE-135P;DEERE-210P | C
EX-CRAWL-17T | EW-MASS | 16-18 t (~38,000-40,000 lb) | Mass excavation, cast to spoil/stockpile (hydraulic excavator) | 0.899 | CY heaped bucket | 122.7983 | 153.4978 | 168.8476 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/14 x 0.899 x 1.0 x 0.83 x 0.80 = 153.5 BCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-13T (30,400 lb, 0.75) and EX-CRAWL-20T (48,500 lb, 1.025). | FM5434-8;KSU-3;FM5434;DEERE-135P;DEERE-210P | C
EX-CRAWL-17T | EW-TRENCH-5 | 16-18 t (~38,000-40,000 lb) | Trench excavation, up to ~5 ft deep | 0.899 | CY heaped bucket | 120.3423 | 150.4279 | 165.4707 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/14 x 0.899 x 1.0 x 0.83 x 0.80 x 0.98 = 150.4 BCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-13T (30,400 lb, 0.75) and EX-CRAWL-20T (48,500 lb, 1.025). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-135P;DEERE-210P | C
EX-CRAWL-17T | EW-TRENCH-10 | 16-18 t (~38,000-40,000 lb) | Trench excavation, 6-10 ft deep | 0.899 | CY heaped bucket | 120.3423 | 150.4279 | 165.4707 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/14 x 0.899 x 1.0 x 0.83 x 0.80 x 0.98 = 150.4 BCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-13T (30,400 lb, 0.75) and EX-CRAWL-20T (48,500 lb, 1.025). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-135P;DEERE-210P | C
EX-CRAWL-17T | EW-STRUCT | 16-18 t (~38,000-40,000 lb) | Structural excavation (footings, pits; confined swing) | 0.899 | CY heaped bucket | 116.6583 | 145.8229 | 160.4052 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Typ: 3600/14 x 0.899 x 1.0 x 0.83 x 0.80 x 0.95 = 145.8 BCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-13T (30,400 lb, 0.75) and EX-CRAWL-20T (48,500 lb, 1.025). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-135P;DEERE-210P | C
EX-CRAWL-17T | EW-BACKFILL | 16-18 t (~38,000-40,000 lb) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 0.899 | CY heaped bucket | 163.0914 | 182.2787 | 191.8723 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose backfill material; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.85/0.95/1.0 (low/typ/high) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83). Typ: 3600/14 x 0.899 x 0.95 x 0.83 = 182.3 LCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-13T (30,400 lb, 0.75) and EX-CRAWL-20T (48,500 lb, 1.025). | FM5434-8;KSU-3;FM5434;CAT-FILL;DEERE-135P;DEERE-210P | C
EX-CRAWL-17T | UT-PIPE-STORM | 16-18 t (~38,000-40,000 lb) | Lay storm sewer 12-36 in (excavator-led crew) |  |  | 300 | 800 | 1500 | LF/day | DOT field daily, 8-hr day (crew) | Storm sewer 12-36 in, WSDOT West | WSDOT range 300-1,500, normal 800 (East normal 1,500). Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT | B
EX-CRAWL-17T | DM-PAVE-CONC | 16-18 t (~38,000-40,000 lb) | Remove concrete pavement |  |  | 410 | 1000 | 4000 | SY/day | DOT field daily median (crew) | Remove concrete pavement | Typ = median of WisDOT 1,000, TxDOT 1,974, WSDOT 600; low 410; high 4,000. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;WSDOT | A
EX-CRAWL-20T | EW-CUTLOAD | 20-25 t (~48,500-62,800 lb) | Bulk cut and load trucks (hydraulic excavator) | 1.025 | CY heaped bucket | 130.6752 | 163.344 | 179.6784 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/15 x 1.025 x 1.0 x 0.83 x 0.80 = 163.3 BCY/hr. Input bucket = midpoint of typical GP 0.75-1.3 yd3 (Deere 210 P 0.56-1.29). | FM5434-8;KSU-3;FM5434;DEERE-210P | C
EX-CRAWL-20T | EW-MASS | 20-25 t (~48,500-62,800 lb) | Mass excavation, cast to spoil/stockpile (hydraulic excavator) | 1.025 | CY heaped bucket | 130.6752 | 163.344 | 179.6784 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/15 x 1.025 x 1.0 x 0.83 x 0.80 = 163.3 BCY/hr. Input bucket = midpoint of typical GP 0.75-1.3 yd3 (Deere 210 P 0.56-1.29). | FM5434-8;KSU-3;FM5434;DEERE-210P | C
EX-CRAWL-20T | EW-TRENCH-5 | 20-25 t (~48,500-62,800 lb) | Trench excavation, up to ~5 ft deep | 1.025 | CY heaped bucket | 128.0617 | 160.0771 | 176.0848 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/15 x 1.025 x 1.0 x 0.83 x 0.80 x 0.98 = 160.1 BCY/hr. Input bucket = midpoint of typical GP 0.75-1.3 yd3 (Deere 210 P 0.56-1.29). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-210P | C
EX-CRAWL-20T | EW-TRENCH-10 | 20-25 t (~48,500-62,800 lb) | Trench excavation, 6-10 ft deep | 1.025 | CY heaped bucket | 128.0617 | 160.0771 | 176.0848 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/15 x 1.025 x 1.0 x 0.83 x 0.80 x 0.98 = 160.1 BCY/hr. Input bucket = midpoint of typical GP 0.75-1.3 yd3 (Deere 210 P 0.56-1.29). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-210P | C
EX-CRAWL-20T | EW-STRUCT | 20-25 t (~48,500-62,800 lb) | Structural excavation (footings, pits; confined swing) | 1.025 | CY heaped bucket | 124.1414 | 155.1768 | 170.6945 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Typ: 3600/15 x 1.025 x 1.0 x 0.83 x 0.80 x 0.95 = 155.2 BCY/hr. Input bucket = midpoint of typical GP 0.75-1.3 yd3 (Deere 210 P 0.56-1.29). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-210P | C
EX-CRAWL-20T | EW-BACKFILL | 20-25 t (~48,500-62,800 lb) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 1.025 | CY heaped bucket | 173.553 | 193.971 | 204.18 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose backfill material; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.85/0.95/1.0 (low/typ/high) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83). Typ: 3600/15 x 1.025 x 0.95 x 0.83 = 194.0 LCY/hr. Input bucket = midpoint of typical GP 0.75-1.3 yd3 (Deere 210 P 0.56-1.29). | FM5434-8;KSU-3;FM5434;CAT-FILL;DEERE-210P | C
EX-CRAWL-20T | UT-PIPE-STORM | 20-25 t (~48,500-62,800 lb) | Lay storm sewer 12-36 in (excavator-led crew) |  |  | 300 | 800 | 1500 | LF/day | DOT field daily, 8-hr day (crew) | Storm sewer 12-36 in, WSDOT West | WSDOT range 300-1,500, normal 800 (East normal 1,500). Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT | B
EX-CRAWL-20T | DM-PAVE-CONC | 20-25 t (~48,500-62,800 lb) | Remove concrete pavement |  |  | 410 | 1000 | 4000 | SY/day | DOT field daily median (crew) | Remove concrete pavement | Typ = median of WisDOT 1,000, TxDOT 1,974, WSDOT 600; low 410; high 4,000. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;WSDOT | A
EX-CRAWL-20T | UT-PIPE-SAN | 20-25 t (~48,500-62,800 lb) | Lay sanitary sewer 6-48 in |  |  | 200 | 300 | 400 | LF/day | DOT field daily (crew) | Sanitary sewer 6-48 in | WSDOT 200-400; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT | B
EX-CRAWL-20T | EW-TRENCH-15 | 20-25 t (~48,500-62,800 lb) | Trench excavation, 11-15 ft deep (shored/boxed) | 1.025 | CY heaped bucket | 128.0617 | 160.0771 | 176.0848 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/15 x 1.025 x 1.0 x 0.83 x 0.80 x 0.98 = 160.1 BCY/hr. Input bucket = midpoint of typical GP 0.75-1.3 yd3 (Deere 210 P 0.56-1.29). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-210P | C
EX-CRAWL-30T | EW-CUTLOAD | 30-36 t (~68,000-81,000 lb) | Bulk cut and load trucks (hydraulic excavator) | 1.95 | CY heaped bucket | 248.6016 | 310.752 | 341.8272 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/15 x 1.95 x 1.0 x 0.83 x 0.80 = 310.8 BCY/hr. Input bucket = midpoint of typical GP 1.4-2.5 yd3 (Deere 345/350 P, Komatsu PC360LC-11). | FM5434-8;KSU-3;FM5434;DEERE-345P;DEERE-350P;KOM-PC360 | C
EX-CRAWL-30T | EW-MASS | 30-36 t (~68,000-81,000 lb) | Mass excavation, cast to spoil/stockpile (hydraulic excavator) | 1.95 | CY heaped bucket | 248.6016 | 310.752 | 341.8272 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/15 x 1.95 x 1.0 x 0.83 x 0.80 = 310.8 BCY/hr. Input bucket = midpoint of typical GP 1.4-2.5 yd3 (Deere 345/350 P, Komatsu PC360LC-11). | FM5434-8;KSU-3;FM5434;DEERE-345P;DEERE-350P;KOM-PC360 | C
EX-CRAWL-30T | EW-TRENCH-5 | 30-36 t (~68,000-81,000 lb) | Trench excavation, up to ~5 ft deep | 1.95 | CY heaped bucket | 243.6296 | 304.537 | 334.9907 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/15 x 1.95 x 1.0 x 0.83 x 0.80 x 0.98 = 304.5 BCY/hr. Input bucket = midpoint of typical GP 1.4-2.5 yd3 (Deere 345/350 P, Komatsu PC360LC-11). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-345P;DEERE-350P;KOM-PC360 | C
EX-CRAWL-30T | EW-TRENCH-10 | 30-36 t (~68,000-81,000 lb) | Trench excavation, 6-10 ft deep | 1.95 | CY heaped bucket | 243.6296 | 304.537 | 334.9907 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/15 x 1.95 x 1.0 x 0.83 x 0.80 x 0.98 = 304.5 BCY/hr. Input bucket = midpoint of typical GP 1.4-2.5 yd3 (Deere 345/350 P, Komatsu PC360LC-11). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-345P;DEERE-350P;KOM-PC360 | C
EX-CRAWL-30T | EW-STRUCT | 30-36 t (~68,000-81,000 lb) | Structural excavation (footings, pits; confined swing) | 1.95 | CY heaped bucket | 236.1715 | 295.2144 | 324.7358 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Typ: 3600/15 x 1.95 x 1.0 x 0.83 x 0.80 x 0.95 = 295.2 BCY/hr. Input bucket = midpoint of typical GP 1.4-2.5 yd3 (Deere 345/350 P, Komatsu PC360LC-11). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-345P;DEERE-350P;KOM-PC360 | C
EX-CRAWL-30T | EW-BACKFILL | 30-36 t (~68,000-81,000 lb) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 1.95 | CY heaped bucket | 330.174 | 369.018 | 388.44 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose backfill material; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.85/0.95/1.0 (low/typ/high) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83). Typ: 3600/15 x 1.95 x 0.95 x 0.83 = 369.0 LCY/hr. Input bucket = midpoint of typical GP 1.4-2.5 yd3 (Deere 345/350 P, Komatsu PC360LC-11). | FM5434-8;KSU-3;FM5434;CAT-FILL;DEERE-345P;DEERE-350P;KOM-PC360 | C
EX-CRAWL-30T | UT-PIPE-STORM | 30-36 t (~68,000-81,000 lb) | Lay storm sewer 12-36 in (excavator-led crew) |  |  | 300 | 800 | 1500 | LF/day | DOT field daily, 8-hr day (crew) | Storm sewer 12-36 in, WSDOT West | WSDOT range 300-1,500, normal 800 (East normal 1,500). Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT | B
EX-CRAWL-30T | DM-PAVE-CONC | 30-36 t (~68,000-81,000 lb) | Remove concrete pavement |  |  | 410 | 1000 | 4000 | SY/day | DOT field daily median (crew) | Remove concrete pavement | Typ = median of WisDOT 1,000, TxDOT 1,974, WSDOT 600; low 410; high 4,000. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;WSDOT | A
EX-CRAWL-30T | UT-PIPE-SAN | 30-36 t (~68,000-81,000 lb) | Lay sanitary sewer 6-48 in |  |  | 200 | 300 | 400 | LF/day | DOT field daily (crew) | Sanitary sewer 6-48 in | WSDOT 200-400; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT | B
EX-CRAWL-30T | UT-PIPE-STORM-L | 30-36 t (~68,000-81,000 lb) | Lay storm sewer 42-72 in |  |  | 50 | 125 | 200 | LF/day | DOT field daily (crew) | Storm sewer 42-72 in | WSDOT 50-200; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT | B
EX-CRAWL-30T | EW-TRENCH-15 | 30-36 t (~68,000-81,000 lb) | Trench excavation, 11-15 ft deep (shored/boxed) | 1.95 | CY heaped bucket | 243.6296 | 304.537 | 334.9907 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/15 x 1.95 x 1.0 x 0.83 x 0.80 x 0.98 = 304.5 BCY/hr. Input bucket = midpoint of typical GP 1.4-2.5 yd3 (Deere 345/350 P, Komatsu PC360LC-11). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-345P;DEERE-350P;KOM-PC360 | C
EX-CRAWL-40T | EW-CUTLOAD | ~40 t (83,000 lb) | Bulk cut and load trucks (hydraulic excavator) | 2.402 | CY heaped bucket | 306.2262 | 382.7827 | 421.061 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/15 x 2.402 x 1.0 x 0.83 x 0.80 = 382.8 BCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-30T (69,200 lb, 1.95) and EX-CRAWL-70T (162,900 lb, 5.0). | FM5434-8;KSU-3;FM5434;DEERE-350P;CAT-EXC-PG | C
EX-CRAWL-40T | EW-MASS | ~40 t (83,000 lb) | Mass excavation, cast to spoil/stockpile (hydraulic excavator) | 2.402 | CY heaped bucket | 306.2262 | 382.7827 | 421.061 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/15 x 2.402 x 1.0 x 0.83 x 0.80 = 382.8 BCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-30T (69,200 lb, 1.95) and EX-CRAWL-70T (162,900 lb, 5.0). | FM5434-8;KSU-3;FM5434;DEERE-350P;CAT-EXC-PG | C
EX-CRAWL-40T | EW-TRENCH-10 | ~40 t (83,000 lb) | Trench excavation, 6-10 ft deep | 2.402 | CY heaped bucket | 300.1017 | 375.1271 | 412.6398 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/15 x 2.402 x 1.0 x 0.83 x 0.80 x 0.98 = 375.1 BCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-30T (69,200 lb, 1.95) and EX-CRAWL-70T (162,900 lb, 5.0). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-350P;CAT-EXC-PG | C
EX-CRAWL-40T | EW-STRUCT | ~40 t (83,000 lb) | Structural excavation (footings, pits; confined swing) | 2.402 | CY heaped bucket | 290.9149 | 363.6436 | 400.0079 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Typ: 3600/15 x 2.402 x 1.0 x 0.83 x 0.80 x 0.95 = 363.6 BCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-30T (69,200 lb, 1.95) and EX-CRAWL-70T (162,900 lb, 5.0). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-350P;CAT-EXC-PG | C
EX-CRAWL-40T | UT-PIPE-STORM-L | ~40 t (83,000 lb) | Lay storm sewer 42-72 in |  |  | 50 | 125 | 200 | LF/day | DOT field daily (crew) | Storm sewer 42-72 in | WSDOT 50-200; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT | B
EX-CRAWL-40T | EW-TRENCH-15 | ~40 t (83,000 lb) | Trench excavation, 11-15 ft deep (shored/boxed) | 2.402 | CY heaped bucket | 300.1017 | 375.1271 | 412.6398 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/15 x 2.402 x 1.0 x 0.83 x 0.80 x 0.98 = 375.1 BCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-30T (69,200 lb, 1.95) and EX-CRAWL-70T (162,900 lb, 5.0). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-350P;CAT-EXC-PG | C
EX-CRAWL-50T | EW-CUTLOAD | 45-55 t (~105,000-108,000 lb) | Bulk cut and load trucks (hydraulic excavator) | 3.206 | CY heaped bucket | 408.7265 | 510.9082 | 561.999 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/15 x 3.206 x 1.0 x 0.83 x 0.80 = 510.9 BCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-30T (69,200 lb, 1.95) and EX-CRAWL-70T (162,900 lb, 5.0). Bucket >2.5 CY: FM cycle not sourced for this size; 15 s retained (likely optimistic). | FM5434-8;KSU-3;FM5434;DEERE-350P;CAT-EXC-PG | C
EX-CRAWL-50T | EW-MASS | 45-55 t (~105,000-108,000 lb) | Mass excavation, cast to spoil/stockpile (hydraulic excavator) | 3.206 | CY heaped bucket | 408.7265 | 510.9082 | 561.999 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/15 x 3.206 x 1.0 x 0.83 x 0.80 = 510.9 BCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-30T (69,200 lb, 1.95) and EX-CRAWL-70T (162,900 lb, 5.0). Bucket >2.5 CY: FM cycle not sourced for this size; 15 s retained (likely optimistic). | FM5434-8;KSU-3;FM5434;DEERE-350P;CAT-EXC-PG | C
EX-CRAWL-50T | EW-STRUCT | 45-55 t (~105,000-108,000 lb) | Structural excavation (footings, pits; confined swing) | 3.206 | CY heaped bucket | 388.2902 | 485.3628 | 533.899 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Typ: 3600/15 x 3.206 x 1.0 x 0.83 x 0.80 x 0.95 = 485.4 BCY/hr. Input bucket = interpolated by operating weight between EX-CRAWL-30T (69,200 lb, 1.95) and EX-CRAWL-70T (162,900 lb, 5.0). Bucket >2.5 CY: FM cycle not sourced for this size; 15 s retained (likely optimistic). | FM5434-8;KSU-3;FM5434;KSU-T3;DEERE-350P;CAT-EXC-PG | C
EX-CRAWL-70T | EW-CUTLOAD | 65-75 t (~145,000-163,000 lb) | Bulk cut and load trucks (hydraulic excavator) | 5 | CY heaped bucket | 637.44 | 796.8 | 876.48 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/15 x 5 x 1.0 x 0.83 x 0.80 = 796.8 BCY/hr. Input bucket = midpoint of typical production bucket 4-6 yd3 (Cat 374 SD 4.32; Deere 870 P 4.56 spec bucket). Bucket >2.5 CY: FM cycle not sourced for this size; 15 s retained (likely optimistic). | FM5434-8;KSU-3;FM5434;CAT-EXC-PG | C
EX-CRAWL-70T | EW-MASS | 65-75 t (~145,000-163,000 lb) | Mass excavation, cast to spoil/stockpile (hydraulic excavator) | 5 | CY heaped bucket | 637.44 | 796.8 | 876.48 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/15 x 5 x 1.0 x 0.83 x 0.80 = 796.8 BCY/hr. Input bucket = midpoint of typical production bucket 4-6 yd3 (Cat 374 SD 4.32; Deere 870 P 4.56 spec bucket). Bucket >2.5 CY: FM cycle not sourced for this size; 15 s retained (likely optimistic). | FM5434-8;KSU-3;FM5434;CAT-EXC-PG | C
EX-CRAWL-90T | EW-CUTLOAD | 90-95 t (~205,000-207,000 lb) | Bulk cut and load trucks (hydraulic excavator) | 6 | CY heaped bucket | 764.928 | 956.16 | 1051.776 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/15 x 6 x 1.0 x 0.83 x 0.80 = 956.2 BCY/hr. Input bucket = midpoint of typical 5-7 yd3 (Cat 395 SD 6.8). Bucket >2.5 CY: FM cycle not sourced for this size; 15 s retained (likely optimistic). | FM5434-8;KSU-3;FM5434;CAT-EXC-PG | C
EX-CRAWL-90T | EW-MASS | 90-95 t (~205,000-207,000 lb) | Mass excavation, cast to spoil/stockpile (hydraulic excavator) | 6 | CY heaped bucket | 764.928 | 956.16 | 1051.776 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/15 x 6 x 1.0 x 0.83 x 0.80 = 956.2 BCY/hr. Input bucket = midpoint of typical 5-7 yd3 (Cat 395 SD 6.8). Bucket >2.5 CY: FM cycle not sourced for this size; 15 s retained (likely optimistic). | FM5434-8;KSU-3;FM5434;CAT-EXC-PG | C
EX-WHEEL-11T | EW-TRENCH-5 | Wheeled ~25,000 lb | Trench excavation, up to ~5 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-WHEEL-11T | EW-STRUCT | Wheeled ~25,000 lb | Structural excavation (footings, pits; confined swing) |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Per 1.0 CY bucket at 15 s, typ fill 1.0: 151.4 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-WHEEL-11T | EW-BACKFILL | Wheeled ~25,000 lb | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose backfill material; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.85/0.95/1.0 (low/typ/high) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83). Per 1.0 CY bucket at 15 s, typ fill 0.95: 189.2 LCY/hr. | FM5434-8;KSU-3;FM5434;CAT-FILL | D | Needs bucket CY (enter in Input_capacity)
EX-WHEEL-20T | EW-TRENCH-5 | Wheeled 40,000-55,000 lb | Trench excavation, up to ~5 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-WHEEL-20T | EW-TRENCH-10 | Wheeled 40,000-55,000 lb | Trench excavation, 6-10 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-WHEEL-20T | EW-STRUCT | Wheeled 40,000-55,000 lb | Structural excavation (footings, pits; confined swing) |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Per 1.0 CY bucket at 15 s, typ fill 1.0: 151.4 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-WHEEL-20T | EW-BACKFILL | Wheeled 40,000-55,000 lb | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose backfill material; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.85/0.95/1.0 (low/typ/high) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83). Per 1.0 CY bucket at 15 s, typ fill 0.95: 189.2 LCY/hr. | FM5434-8;KSU-3;FM5434;CAT-FILL | D | Needs bucket CY (enter in Input_capacity)
EX-WHEEL-20T | EW-TRENCH-15 | Wheeled 40,000-55,000 lb | Trench excavation, 11-15 ft deep (shored/boxed) |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
EX-LR-40T | EW-MASS | Long-reach ~43 t (42.8 ft dig) | Mass excavation, cast to spoil/stockpile (hydraulic excavator) |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Per 1.0 CY bucket at 15 s, typ fill 1.0: 159.4 BCY/hr. | FM5434-8;KSU-3;FM5434 | D | Needs bucket CY (enter in Input_capacity)
EX-LR-55T | EW-MASS | Long-reach ~58 t (42.8 ft dig) | Mass excavation, cast to spoil/stockpile (hydraulic excavator) |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Per 1.0 CY bucket at 15 s, typ fill 1.0: 159.4 BCY/hr. | FM5434-8;KSU-3;FM5434 | D | Needs bucket CY (enter in Input_capacity)
EX-SHOVEL-95T | EW-CUTLOAD | Front shovel ~96 t | Bulk cut and load trucks (hydraulic excavator) |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Per 1.0 CY bucket at 15 s, typ fill 1.0: 159.4 BCY/hr. | FM5434-8;KSU-3;FM5434 | D | Needs bucket CY (enter in Input_capacity)
EX-GRADALL-XL3100 | EW-CUTLOAD | Gradall XL3100 III (0.57 CY) | Bulk cut and load trucks (hydraulic excavator) | 0.57 | CY heaped bucket | 77.8587 | 97.3234 | 107.0558 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/14 x 0.57 x 1.0 x 0.83 x 0.80 = 97.3 BCY/hr. Input bucket = Gradall XL3100 0.57 CY (FEMA/taxonomy). | FM5434-8;KSU-3;FM5434;FEMA25 | C
EX-GRADALL-XL3100 | EW-TRENCH-5 | Gradall XL3100 III (0.57 CY) | Trench excavation, up to ~5 ft deep | 0.57 | CY heaped bucket | 76.3016 | 95.377 | 104.9147 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/14 x 0.57 x 1.0 x 0.83 x 0.80 x 0.98 = 95.4 BCY/hr. Input bucket = Gradall XL3100 0.57 CY (FEMA/taxonomy). | FM5434-8;KSU-3;FM5434;KSU-T3;FEMA25 | C
EX-GRADALL-XL3100 | EW-STRUCT | Gradall XL3100 III (0.57 CY) | Structural excavation (footings, pits; confined swing) | 0.57 | CY heaped bucket | 73.9658 | 92.4573 | 101.703 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Typ: 3600/14 x 0.57 x 1.0 x 0.83 x 0.80 x 0.95 = 92.5 BCY/hr. Input bucket = Gradall XL3100 0.57 CY (FEMA/taxonomy). | FM5434-8;KSU-3;FM5434;KSU-T3;FEMA25 | C
EX-GRADALL-XL4100 | EW-CUTLOAD | Gradall XL4100 III (0.62 CY) | Bulk cut and load trucks (hydraulic excavator) | 0.62 | CY heaped bucket | 84.6885 | 105.8606 | 116.4466 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/14 x 0.62 x 1.0 x 0.83 x 0.80 = 105.9 BCY/hr. Input bucket = Gradall XL4100 0.62 CY. | FM5434-8;KSU-3;FM5434;FEMA25 | C
EX-GRADALL-XL4100 | EW-TRENCH-5 | Gradall XL4100 III (0.62 CY) | Trench excavation, up to ~5 ft deep | 0.62 | CY heaped bucket | 82.9947 | 103.7434 | 114.1177 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/14 x 0.62 x 1.0 x 0.83 x 0.80 x 0.98 = 103.7 BCY/hr. Input bucket = Gradall XL4100 0.62 CY. | FM5434-8;KSU-3;FM5434;KSU-T3;FEMA25 | C
EX-GRADALL-XL4100 | EW-STRUCT | Gradall XL4100 III (0.62 CY) | Structural excavation (footings, pits; confined swing) | 0.62 | CY heaped bucket | 80.454 | 100.5675 | 110.6243 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Typ: 3600/14 x 0.62 x 1.0 x 0.83 x 0.80 x 0.95 = 100.6 BCY/hr. Input bucket = Gradall XL4100 0.62 CY. | FM5434-8;KSU-3;FM5434;KSU-T3;FEMA25 | C
EX-GRADALL-XL5100 | EW-CUTLOAD | Gradall XL5100 (1.25 CY) | Bulk cut and load trucks (hydraulic excavator) | 1.25 | CY heaped bucket | 159.36 | 199.2 | 219.12 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80. Typ: 3600/15 x 1.25 x 1.0 x 0.83 x 0.80 = 199.2 BCY/hr. Input bucket = Gradall XL5100 1.25 CY. | FM5434-8;KSU-3;FM5434;FEMA25 | C
EX-GRADALL-XL5100 | EW-TRENCH-5 | Gradall XL5100 (1.25 CY) | Trench excavation, up to ~5 ft deep | 1.25 | CY heaped bucket | 156.1728 | 195.216 | 214.7376 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Typ: 3600/15 x 1.25 x 1.0 x 0.83 x 0.80 x 0.98 = 195.2 BCY/hr. Input bucket = Gradall XL5100 1.25 CY. | FM5434-8;KSU-3;FM5434;KSU-T3;FEMA25 | C
EX-GRADALL-XL5100 | EW-STRUCT | Gradall XL5100 (1.25 CY) | Structural excavation (footings, pits; confined swing) | 1.25 | CY heaped bucket | 151.392 | 189.24 | 208.164 | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Typ: 3600/15 x 1.25 x 1.0 x 0.83 x 0.80 x 0.95 = 189.2 BCY/hr. Input bucket = Gradall XL5100 1.25 CY. | FM5434-8;KSU-3;FM5434;KSU-T3;FEMA25 | C
BH-415 | EW-TRENCH-5 | Cat 415 class (69 hp) | Trench excavation, up to ~5 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
BH-415 | EW-BACKFILL | Cat 415 class (69 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
BH-415 | EW-LOAD-TRK | Cat 415 class (69 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
BH-STD-14FT | EW-TRENCH-5 | Standard 14-15 ft dig (90-103 hp) | Trench excavation, up to ~5 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
BH-STD-14FT | EW-STRUCT | Standard 14-15 ft dig (90-103 hp) | Structural excavation (footings, pits; confined swing) |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.95 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.95. Per 1.0 CY bucket at 15 s, typ fill 1.0: 151.4 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
BH-STD-14FT | EW-BACKFILL | Standard 14-15 ft dig (90-103 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 1.25 | CY heaped bucket | 96.2045 | 118.275 | 138.3333 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; Cat 420 loader MP bucket 1.25 yd3 | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 1.25 x 0.95 x 3600/30 x 0.83 = 118.3 | CAT-WL;CAT-FILL;KSU-EQ;CAT-420 | C
BH-STD-14FT | EW-LOAD-TRK | Standard 14-15 ft dig (90-103 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 1.25 | CY heaped bucket | 96.2045 | 118.275 | 138.3333 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; Cat 420 loader MP bucket 1.25 yd3 | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 1.25 x 0.95 x 3600/30 x 0.83 = 118.3 | CAT-WL;CAT-FILL;KSU-EQ;CAT-420 | C
BH-STD-14FT | UT-PIPE-WATER | Standard 14-15 ft dig (90-103 hp) | Lay water main |  |  | 100 | 300 | 800 | LF/day | DOT field daily (crew) | Water main | WSDOT 100-800, normal 300. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT | B
BH-CASE580-80HP | EW-TRENCH-5 | Case 580 Super L (80 hp, 0.87 CY) | Trench excavation, up to ~5 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
BH-CASE580-80HP | EW-BACKFILL | Case 580 Super L (80 hp, 0.87 CY) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 0.87 | CY heaped bucket | 66.9584 | 82.3194 | 96.28 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; Case 580 Super L 0.87 CY (FEMA 8401) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 0.87 x 0.95 x 3600/30 x 0.83 = 82.3 | CAT-WL;CAT-FILL;KSU-EQ;FEMA25 | C
BH-430 | EW-TRENCH-5 | Cat 430 class (107 hp, 15.1 ft dig) | Trench excavation, up to ~5 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
BH-430 | EW-BACKFILL | Cat 430 class (107 hp, 15.1 ft dig) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
BH-430 | EW-LOAD-TRK | Cat 430 class (107 hp, 15.1 ft dig) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
BH-440 | EW-TRENCH-5 | Cat 440 class (104 hp, 29,321 lb) | Trench excavation, up to ~5 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
BH-440 | EW-TRENCH-10 | Cat 440 class (104 hp, 29,321 lb) | Trench excavation, 6-10 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
BH-440 | EW-BACKFILL | Cat 440 class (104 hp, 29,321 lb) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
BH-440 | EW-LOAD-TRK | Cat 440 class (104 hp, 29,321 lb) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
BH-450 | EW-TRENCH-5 | Cat 450 class (131 hp, 17 ft dig) | Trench excavation, up to ~5 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
BH-450 | EW-TRENCH-10 | Cat 450 class (131 hp, 17 ft dig) | Trench excavation, 6-10 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98; depth effect on cycle NOT applied (Peurifoy swing-depth table not retrieved) | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
BH-450 | EW-BACKFILL | Cat 450 class (131 hp, 17 ft dig) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
BH-450 | EW-LOAD-TRK | Cat 450 class (131 hp, 17 ft dig) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
BH-SIDESHIFT | EW-TRENCH-5 | Side-shift 70-92 hp | Trench excavation, up to ~5 ft deep |  | CY heaped bucket |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | Common earth/loam; cycle 14 s (<1 CY) / 15 s (>=1 CY) at 40-60% of max depth & 30-60 deg swing; fill 0.8/1.0/1.1 (low/typ/high); L->B 0.80 (loam); trench/confined factor 0.98 | Prod = 3600/cycle_s x Bucket_CY x Fill x E(0.83) x 0.80 x 0.98. Per 1.0 CY bucket at 15 s, typ fill 1.0: 156.2 BCY/hr. | FM5434-8;KSU-3;FM5434;KSU-T3 | D | Needs bucket CY (enter in Input_capacity)
BH-SIDESHIFT | EW-BACKFILL | Side-shift 70-92 hp | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
WL-MINI-07Y | EW-LOAD-TRK | 0.5-0.7 CY (~38 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 0.6 | CY heaped bucket | 46.1782 | 56.772 | 66.4 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 0.5-0.7 CY (Gehl 280, taxonomy) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 0.6 x 0.95 x 3600/30 x 0.83 = 56.8 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-MINI-07Y | EW-STOCKPILE | 0.5-0.7 CY (~38 hp) | Stockpile / rehandle with loader (minimum travel) | 0.6 | CY heaped bucket | 46.1782 | 56.772 | 66.4 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 0.5-0.7 CY (Gehl 280, taxonomy) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 0.6 x 0.95 x 3600/30 x 0.83 = 56.8 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-MINI-07Y | EW-BACKFILL | 0.5-0.7 CY (~38 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 0.6 | CY heaped bucket | 46.1782 | 56.772 | 66.4 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 0.5-0.7 CY (Gehl 280, taxonomy) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 0.6 x 0.95 x 3600/30 x 0.83 = 56.8 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-COMPACT-1Y | EW-LOAD-TRK | ~1-1.25 yd (~68-75 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 1.125 | CY heaped bucket | 86.5841 | 106.4475 | 124.5 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 1.0-1.25 yd rental class (Cat 906 GP 1.0-1.7; Deere 244 P 1.0-1.4) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 1.125 x 0.95 x 3600/30 x 0.83 = 106.4 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-COMPACT-1Y | EW-STOCKPILE | ~1-1.25 yd (~68-75 hp) | Stockpile / rehandle with loader (minimum travel) | 1.125 | CY heaped bucket | 86.5841 | 106.4475 | 124.5 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 1.0-1.25 yd rental class (Cat 906 GP 1.0-1.7; Deere 244 P 1.0-1.4) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 1.125 x 0.95 x 3600/30 x 0.83 = 106.4 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-COMPACT-1Y | EW-BACKFILL | ~1-1.25 yd (~68-75 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 1.125 | CY heaped bucket | 86.5841 | 106.4475 | 124.5 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 1.0-1.25 yd rental class (Cat 906 GP 1.0-1.7; Deere 244 P 1.0-1.4) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 1.125 x 0.95 x 3600/30 x 0.83 = 106.4 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-COMPACT-2Y | EW-LOAD-TRK | 2-2.5 yd (~110 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 2.25 | CY heaped bucket | 173.1682 | 212.895 | 249 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 2.0-2.5 yd rental class (Deere 344 P 2.0-2.6) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 2.25 x 0.95 x 3600/30 x 0.83 = 212.9 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-COMPACT-2Y | EW-STOCKPILE | 2-2.5 yd (~110 hp) | Stockpile / rehandle with loader (minimum travel) | 2.25 | CY heaped bucket | 173.1682 | 212.895 | 249 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 2.0-2.5 yd rental class (Deere 344 P 2.0-2.6) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 2.25 x 0.95 x 3600/30 x 0.83 = 212.9 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-COMPACT-2Y | EW-BACKFILL | 2-2.5 yd (~110 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 2.25 | CY heaped bucket | 173.1682 | 212.895 | 249 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 2.0-2.5 yd rental class (Deere 344 P 2.0-2.6) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 2.25 x 0.95 x 3600/30 x 0.83 = 212.9 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-SMALL-3Y | EW-LOAD-TRK | 3-3.2 yd (~170 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 3.1 | CY heaped bucket | 238.5873 | 293.322 | 343.0667 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 3.0-3.2 yd rental class | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 3.1 x 0.95 x 3600/30 x 0.83 = 293.3 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-SMALL-3Y | EW-STOCKPILE | 3-3.2 yd (~170 hp) | Stockpile / rehandle with loader (minimum travel) | 3.1 | CY heaped bucket | 238.5873 | 293.322 | 343.0667 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 3.0-3.2 yd rental class | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 3.1 x 0.95 x 3600/30 x 0.83 = 293.3 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-SMALL-3Y | EW-BACKFILL | 3-3.2 yd (~170 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 3.1 | CY heaped bucket | 238.5873 | 293.322 | 343.0667 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 3.0-3.2 yd rental class | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 3.1 x 0.95 x 3600/30 x 0.83 = 293.3 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-SMALL-4Y | EW-LOAD-TRK | 3.5-4.25 yd (~190-232 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 3.875 | CY heaped bucket | 298.2341 | 366.6525 | 428.8333 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 3.5-4.25 yd rental class | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 3.875 x 0.95 x 3600/30 x 0.83 = 366.7 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-SMALL-4Y | EW-STOCKPILE | 3.5-4.25 yd (~190-232 hp) | Stockpile / rehandle with loader (minimum travel) | 3.875 | CY heaped bucket | 298.2341 | 366.6525 | 428.8333 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 3.5-4.25 yd rental class | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 3.875 x 0.95 x 3600/30 x 0.83 = 366.7 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-SMALL-4Y | EW-BACKFILL | 3.5-4.25 yd (~190-232 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 3.875 | CY heaped bucket | 298.2341 | 366.6525 | 428.8333 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of 3.5-4.25 yd rental class | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 3.875 x 0.95 x 3600/30 x 0.83 = 366.7 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-MED-45Y | EW-LOAD-TRK | 4.5 yd (~225-250 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 4.5 | CY heaped bucket | 346.3364 | 425.79 | 498 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 4.5 yd (Wheeler Cat 950 rental line; cat.com 950 rated 4.1) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 4.5 x 0.95 x 3600/30 x 0.83 = 425.8 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-MED-45Y | EW-STOCKPILE | 4.5 yd (~225-250 hp) | Stockpile / rehandle with loader (minimum travel) | 4.5 | CY heaped bucket | 346.3364 | 425.79 | 498 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 4.5 yd (Wheeler Cat 950 rental line; cat.com 950 rated 4.1) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 4.5 x 0.95 x 3600/30 x 0.83 = 425.8 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-MED-45Y | EW-BACKFILL | 4.5 yd (~225-250 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 4.5 | CY heaped bucket | 346.3364 | 425.79 | 498 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 4.5 yd (Wheeler Cat 950 rental line; cat.com 950 rated 4.1) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 4.5 x 0.95 x 3600/30 x 0.83 = 425.8 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-MED-5Y | EW-LOAD-TRK | 5-5.25 yd (~255-321 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 5.25 | CY heaped bucket | 404.0591 | 496.755 | 581 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 5.25 yd (Cat 966 rental line) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 5.25 x 0.95 x 3600/30 x 0.83 = 496.8 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-MED-5Y | EW-STOCKPILE | 5-5.25 yd (~255-321 hp) | Stockpile / rehandle with loader (minimum travel) | 5.25 | CY heaped bucket | 404.0591 | 496.755 | 581 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 5.25 yd (Cat 966 rental line) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 5.25 x 0.95 x 3600/30 x 0.83 = 496.8 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-MED-5Y | EW-BACKFILL | 5-5.25 yd (~255-321 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 5.25 | CY heaped bucket | 404.0591 | 496.755 | 581 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 5.25 yd (Cat 966 rental line) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 5.25 x 0.95 x 3600/30 x 0.83 = 496.8 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-MED-972 | EW-LOAD-TRK | Cat 972 class (~339 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
WL-MED-972 | EW-STOCKPILE | Cat 972 class (~339 hp) | Stockpile / rehandle with loader (minimum travel) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
WL-MED-972 | EW-BACKFILL | Cat 972 class (~339 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
WL-MED-980 | EW-LOAD-TRK | Cat 980 class (~420 hp, 5.75-7.5 yd) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 6.625 | CY heaped bucket | 509.8841 | 626.8575 | 733.1667 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of Cat 980 GC 5.75-7.5 yd3 | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 6.625 x 0.95 x 3600/30 x 0.83 = 626.9 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-MED-980 | EW-STOCKPILE | Cat 980 class (~420 hp, 5.75-7.5 yd) | Stockpile / rehandle with loader (minimum travel) | 6.625 | CY heaped bucket | 509.8841 | 626.8575 | 733.1667 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of Cat 980 GC 5.75-7.5 yd3 | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 6.625 x 0.95 x 3600/30 x 0.83 = 626.9 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-MED-980 | EW-BACKFILL | Cat 980 class (~420 hp, 5.75-7.5 yd) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 6.625 | CY heaped bucket | 509.8841 | 626.8575 | 733.1667 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of Cat 980 GC 5.75-7.5 yd3 | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 6.625 x 0.95 x 3600/30 x 0.83 = 626.9 | CAT-WL;CAT-FILL;KSU-EQ;CAT-WL-PG;DEERE-FLEET | C
WL-MED-982 | EW-LOAD-TRK | Cat 982 class (~432 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
WL-MED-982 | EW-STOCKPILE | Cat 982 class (~432 hp) | Stockpile / rehandle with loader (minimum travel) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
WL-LARGE-986 | EW-LOAD-TRK | Cat 986 class (~449 hp, 6.5-13.5 yd) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
WL-LARGE-986 | EW-STOCKPILE | Cat 986 class (~449 hp, 6.5-13.5 yd) | Stockpile / rehandle with loader (minimum travel) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
WL-LARGE-988 | EW-LOAD-TRK | Cat 988 class (~580 hp, 6.2-17 yd) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
WL-LARGE-988 | EW-STOCKPILE | Cat 988 class (~580 hp, 6.2-17 yd) | Stockpile / rehandle with loader (minimum travel) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
WL-LARGE-990 | EW-LOAD-TRK | Cat 990 class (~786 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
WL-LARGE-992 | EW-LOAD-TRK | Cat 992 class (~814 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical) | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
TL-CRAWL-963 | EW-LOAD-TRK | 3-3.2 CY (~178 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 3.1 | CY heaped bucket | 238.5873 | 293.322 | 343.0667 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of Cat 963 3-3.2 CY | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 3.1 x 0.95 x 3600/30 x 0.83 = 293.3 | CAT-WL;CAT-FILL;KSU-EQ;ZIEGLER | C
TL-CRAWL-963 | EW-BACKFILL | 3-3.2 CY (~178 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 3.1 | CY heaped bucket | 238.5873 | 293.322 | 343.0667 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of Cat 963 3-3.2 CY | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 3.1 x 0.95 x 3600/30 x 0.83 = 293.3 | CAT-WL;CAT-FILL;KSU-EQ;ZIEGLER | C
TL-CRAWL-973 | EW-LOAD-TRK | 4-4.19 CY (~238 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 4.095 | CY heaped bucket | 315.1661 | 387.4689 | 453.18 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of Cat 973 4-4.19 CY | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 4.095 x 0.95 x 3600/30 x 0.83 = 387.5 | CAT-WL;CAT-FILL;KSU-EQ;ZIEGLER | C
TL-CRAWL-973 | EW-BACKFILL | 4-4.19 CY (~238 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 4.095 | CY heaped bucket | 315.1661 | 387.4689 | 453.18 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; midpoint of Cat 973 4-4.19 CY | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 4.095 x 0.95 x 3600/30 x 0.83 = 387.5 | CAT-WL;CAT-FILL;KSU-EQ;ZIEGLER | C
SS-WHEEL-MICRO | EW-LOAD-TRK | ROC 700-1,099 lb (~24 hp) | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
SS-WHEEL-MICRO | EW-BACKFILL | ROC 700-1,099 lb (~24 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
SS-WHEEL-MICRO | EW-SPREAD-SSL | ROC 700-1,099 lb (~24 hp) | Spread/backfill with skid steer or CTL | [5 empty] | LCY/hr | n/a |  | No skid steer bucket/production source |  | D | Needs production rate
SS-WHEEL-SMALL | EW-LOAD-TRK | ROC <1,750 lb | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
SS-WHEEL-SMALL | EW-BACKFILL | ROC <1,750 lb | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
SS-WHEEL-SMALL | EW-SPREAD-SSL | ROC <1,750 lb | Spread/backfill with skid steer or CTL | [5 empty] | LCY/hr | n/a |  | No skid steer bucket/production source |  | D | Needs production rate
SS-WHEEL-MED | EW-LOAD-TRK | ROC 1,750-2,500 lb | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 0.6 | CY heaped bucket | 46.1782 | 56.772 | 66.4 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 62-68 in bucket 0.57-0.63 yd3 mapped to 1,750-2,200 lb ROC (notes mapping; midpoint); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 0.6 x 0.95 x 3600/30 x 0.83 = 56.8 | CAT-WL;CAT-FILL;KSU-EQ;CARLETON-BKT;DEERE-FLEET | C
SS-WHEEL-MED | EW-BACKFILL | ROC 1,750-2,500 lb | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 0.6 | CY heaped bucket | 46.1782 | 56.772 | 66.4 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 62-68 in bucket 0.57-0.63 yd3 mapped to 1,750-2,200 lb ROC (notes mapping; midpoint); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 0.6 x 0.95 x 3600/30 x 0.83 = 56.8 | CAT-WL;CAT-FILL;KSU-EQ;CARLETON-BKT;DEERE-FLEET | C
SS-WHEEL-MED | EW-SPREAD-SSL | ROC 1,750-2,500 lb | Spread/backfill with skid steer or CTL | [5 empty] | LCY/hr | n/a |  | No skid steer bucket/production source |  | D | Needs production rate
SS-WHEEL-LARGE | EW-LOAD-TRK | ROC 2,500-3,500 lb | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 0.69 | CY heaped bucket | 53.1049 | 65.2878 | 76.36 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 74 in bucket 0.69 yd3 mapped to 2,500-3,200 lb ROC (notes mapping); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 0.69 x 0.95 x 3600/30 x 0.83 = 65.3 | CAT-WL;CAT-FILL;KSU-EQ;CARLETON-BKT;DEERE-FLEET | C
SS-WHEEL-LARGE | EW-BACKFILL | ROC 2,500-3,500 lb | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 0.69 | CY heaped bucket | 53.1049 | 65.2878 | 76.36 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 74 in bucket 0.69 yd3 mapped to 2,500-3,200 lb ROC (notes mapping); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 0.69 x 0.95 x 3600/30 x 0.83 = 65.3 | CAT-WL;CAT-FILL;KSU-EQ;CARLETON-BKT;DEERE-FLEET | C
SS-WHEEL-LARGE | EW-SPREAD-SSL | ROC 2,500-3,500 lb | Spread/backfill with skid steer or CTL | [5 empty] | LCY/hr | n/a |  | No skid steer bucket/production source |  | D | Needs production rate
SS-WHEEL-XL | EW-LOAD-TRK | ROC 3,000-4,500 lb | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
SS-WHEEL-XL | EW-BACKFILL | ROC 3,000-4,500 lb | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
SS-WHEEL-XL | EW-SPREAD-SSL | ROC 3,000-4,500 lb | Spread/backfill with skid steer or CTL | [5 empty] | LCY/hr | n/a |  | No skid steer bucket/production source |  | D | Needs production rate
SS-MTL | EW-BACKFILL | Mini track loader (~25 hp) | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
SS-MTL | EW-SPREAD-SSL | Mini track loader (~25 hp) | Spread/backfill with skid steer or CTL | [5 empty] | LCY/hr | n/a |  | No skid steer bucket/production source |  | D | Needs production rate
CTL-SMALL | EW-LOAD-TRK | ROC <2,000 lb | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
CTL-SMALL | EW-BACKFILL | ROC <2,000 lb | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) |  | CY heaped bucket |  |  |  | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; bucket not in notes/specs (or range too wide for a typical); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: Bucket x 0.95 x 3600/30 x 0.83 = 94.6 per 1 CY | CAT-WL;CAT-FILL;KSU-EQ | D | Needs bucket CY
CTL-SMALL | EW-SPREAD-SSL | ROC <2,000 lb | Spread/backfill with skid steer or CTL | [5 empty] | LCY/hr | n/a |  | No skid steer bucket/production source |  | D | Needs production rate
CTL-MED | EW-LOAD-TRK | ROC 2,000-3,000 lb | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 0.69 | CY heaped bucket | 53.1049 | 65.2878 | 76.36 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 74 in bucket 0.69 yd3 mapped to 2,500-3,200 lb ROC (notes mapping); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 0.69 x 0.95 x 3600/30 x 0.83 = 65.3 | CAT-WL;CAT-FILL;KSU-EQ;CARLETON-BKT;DEERE-FLEET | C
CTL-MED | EW-BACKFILL | ROC 2,000-3,000 lb | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 0.69 | CY heaped bucket | 53.1049 | 65.2878 | 76.36 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 74 in bucket 0.69 yd3 mapped to 2,500-3,200 lb ROC (notes mapping); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 0.69 x 0.95 x 3600/30 x 0.83 = 65.3 | CAT-WL;CAT-FILL;KSU-EQ;CARLETON-BKT;DEERE-FLEET | C
CTL-MED | EW-SPREAD-SSL | ROC 2,000-3,000 lb | Spread/backfill with skid steer or CTL | [5 empty] | LCY/hr | n/a |  | No skid steer bucket/production source |  | D | Needs production rate
CTL-LARGE | EW-LOAD-TRK | ROC >3,000 lb | Load trucks from stockpile/loose (wheel/track loader, backhoe loader) | 0.74 | CY heaped bucket | 56.9531 | 70.0188 | 81.8933 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 80 in bucket 0.74 yd3 mapped to 3,500 lb+ ROC (notes mapping); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 0.74 x 0.95 x 3600/30 x 0.83 = 70.0 | CAT-WL;CAT-FILL;KSU-EQ;CARLETON-BKT;DEERE-FLEET | C
CTL-LARGE | EW-BACKFILL | ROC >3,000 lb | Backfill with excavator/backhoe/loader (place loose material, excl. compaction) | 0.74 | CY heaped bucket | 56.9531 | 70.0188 | 81.8933 | LCY/hr | Calculated: job-adjusted (E from Settings) | Loose material, hard smooth floor; Cat basic loader cycle 33/30/27 s (low/typ/high) applied to every loader-end bucket (wheel/track loaders, backhoe loader end, skid steers/CTLs). Fill 0.85/0.95/1.00; 80 in bucket 0.74 yd3 mapped to 3,500 lb+ ROC (notes mapping); Cat cycle is for wheel loaders - applied to skid steers/CTLs as an inference | LCY/hr = Bucket x Fill x 3600/cycle_s x E. Typ: 0.74 x 0.95 x 3600/30 x 0.83 = 70.0 | CAT-WL;CAT-FILL;KSU-EQ;CARLETON-BKT;DEERE-FLEET | C
CTL-LARGE | EW-SPREAD-SSL | ROC >3,000 lb | Spread/backfill with skid steer or CTL | [5 empty] | LCY/hr | n/a |  | No skid steer bucket/production source |  | D | Needs production rate
SC-621-24 | EW-SCR-1000 | 24 yd3 bowl | Scraper load-haul-dump, 1,000 ft one-way | 24 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 1,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 20.0 LCY | Payload LCY = MIN(24 x 0.833 (FM 621B: 20 LCY from 24 yd3), 57610 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 1000/(v_haul x 88) + 1000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-621-24 | EW-SCR-2000 | 24 yd3 bowl | Scraper load-haul-dump, 2,000 ft one-way | 24 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 2,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 20.0 LCY | Payload LCY = MIN(24 x 0.833 (FM 621B: 20 LCY from 24 yd3), 57610 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 2000/(v_haul x 88) + 2000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-621-24 | EW-SCR-3000 | 24 yd3 bowl | Scraper load-haul-dump, 3,000 ft one-way | 24 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 3,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 20.0 LCY | Payload LCY = MIN(24 x 0.833 (FM 621B: 20 LCY from 24 yd3), 57610 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 3000/(v_haul x 88) + 3000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-623-23 | EW-SCR-1000 | 23 yd3 bowl | Scraper load-haul-dump, 1,000 ft one-way | 23 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 1,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 19.2 LCY | Payload LCY = MIN(23 x 0.833 (FM 621B: 20 LCY from 24 yd3), 55200 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 1000/(v_haul x 88) + 1000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-623-23 | EW-SCR-2000 | 23 yd3 bowl | Scraper load-haul-dump, 2,000 ft one-way | 23 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 2,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 19.2 LCY | Payload LCY = MIN(23 x 0.833 (FM 621B: 20 LCY from 24 yd3), 55200 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 2000/(v_haul x 88) + 2000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-623-23 | EW-SCR-3000 | 23 yd3 bowl | Scraper load-haul-dump, 3,000 ft one-way | 23 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 3,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 19.2 LCY | Payload LCY = MIN(23 x 0.833 (FM 621B: 20 LCY from 24 yd3), 55200 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 3000/(v_haul x 88) + 3000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-627-24 | EW-SCR-1000 | 24 yd3 bowl | Scraper load-haul-dump, 1,000 ft one-way | 24 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 1,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 20.0 LCY | Payload LCY = MIN(24 x 0.833 (FM 621B: 20 LCY from 24 yd3), n/a lb / 2,300) (rated load not in specs; heaped x 0.833 only); trips/hr = 60 x E / (load + 0.81 + 1000/(v_haul x 88) + 1000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-627-24 | EW-SCR-2000 | 24 yd3 bowl | Scraper load-haul-dump, 2,000 ft one-way | 24 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 2,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 20.0 LCY | Payload LCY = MIN(24 x 0.833 (FM 621B: 20 LCY from 24 yd3), n/a lb / 2,300) (rated load not in specs; heaped x 0.833 only); trips/hr = 60 x E / (load + 0.81 + 2000/(v_haul x 88) + 2000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-627-24 | EW-SCR-3000 | 24 yd3 bowl | Scraper load-haul-dump, 3,000 ft one-way | 24 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 3,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 20.0 LCY | Payload LCY = MIN(24 x 0.833 (FM 621B: 20 LCY from 24 yd3), n/a lb / 2,300) (rated load not in specs; heaped x 0.833 only); trips/hr = 60 x E / (load + 0.81 + 3000/(v_haul x 88) + 3000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-631-34 | EW-SCR-1000 | 34 yd3 bowl | Scraper load-haul-dump, 1,000 ft one-way | 34 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 1,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 28.3 LCY | Payload LCY = MIN(34 x 0.833 (FM 621B: 20 LCY from 24 yd3), 82200 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 1000/(v_haul x 88) + 1000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-631-34 | EW-SCR-2000 | 34 yd3 bowl | Scraper load-haul-dump, 2,000 ft one-way | 34 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 2,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 28.3 LCY | Payload LCY = MIN(34 x 0.833 (FM 621B: 20 LCY from 24 yd3), 82200 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 2000/(v_haul x 88) + 2000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-631-34 | EW-SCR-3000 | 34 yd3 bowl | Scraper load-haul-dump, 3,000 ft one-way | 34 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 3,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 28.3 LCY | Payload LCY = MIN(34 x 0.833 (FM 621B: 20 LCY from 24 yd3), 82200 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 3000/(v_haul x 88) + 3000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-637-34 | EW-SCR-1000 | 34 yd3 bowl | Scraper load-haul-dump, 1,000 ft one-way | 34 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 1,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 28.3 LCY | Payload LCY = MIN(34 x 0.833 (FM 621B: 20 LCY from 24 yd3), 82200 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 1000/(v_haul x 88) + 1000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-637-34 | EW-SCR-2000 | 34 yd3 bowl | Scraper load-haul-dump, 2,000 ft one-way | 34 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 2,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 28.3 LCY | Payload LCY = MIN(34 x 0.833 (FM 621B: 20 LCY from 24 yd3), 82200 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 2000/(v_haul x 88) + 2000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-637-34 | EW-SCR-3000 | 34 yd3 bowl | Scraper load-haul-dump, 3,000 ft one-way | 34 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 3,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 28.3 LCY | Payload LCY = MIN(34 x 0.833 (FM 621B: 20 LCY from 24 yd3), 82200 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 3000/(v_haul x 88) + 3000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-651-44 | EW-SCR-1000 | 44 yd3 bowl | Scraper load-haul-dump, 1,000 ft one-way | 44 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 1,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 36.7 LCY | Payload LCY = MIN(44 x 0.833 (FM 621B: 20 LCY from 24 yd3), n/a lb / 2,300) (rated load not in specs; heaped x 0.833 only); trips/hr = 60 x E / (load + 0.81 + 1000/(v_haul x 88) + 1000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-651-44 | EW-SCR-2000 | 44 yd3 bowl | Scraper load-haul-dump, 2,000 ft one-way | 44 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 2,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 36.7 LCY | Payload LCY = MIN(44 x 0.833 (FM 621B: 20 LCY from 24 yd3), n/a lb / 2,300) (rated load not in specs; heaped x 0.833 only); trips/hr = 60 x E / (load + 0.81 + 2000/(v_haul x 88) + 2000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-651-44 | EW-SCR-3000 | 44 yd3 bowl | Scraper load-haul-dump, 3,000 ft one-way | 44 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 3,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 36.7 LCY | Payload LCY = MIN(44 x 0.833 (FM 621B: 20 LCY from 24 yd3), n/a lb / 2,300) (rated load not in specs; heaped x 0.833 only); trips/hr = 60 x E / (load + 0.81 + 3000/(v_haul x 88) + 3000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-657-44 | EW-SCR-1000 | 44 yd3 bowl | Scraper load-haul-dump, 1,000 ft one-way | 44 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 1,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 36.7 LCY | Payload LCY = MIN(44 x 0.833 (FM 621B: 20 LCY from 24 yd3), 104000 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 1000/(v_haul x 88) + 1000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-657-44 | EW-SCR-2000 | 44 yd3 bowl | Scraper load-haul-dump, 2,000 ft one-way | 44 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 2,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 36.7 LCY | Payload LCY = MIN(44 x 0.833 (FM 621B: 20 LCY from 24 yd3), 104000 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 2000/(v_haul x 88) + 2000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
SC-657-44 | EW-SCR-3000 | 44 yd3 bowl | Scraper load-haul-dump, 3,000 ft one-way | 44 | yd3 heaped bowl |  |  |  | BCY/hr | Calculated: job-adjusted (E from Settings) | One-way 3,000 ft; push-loaded: load 0.85 min (D8 pusher) / 1.0 min (D7, low); turn/dump 0.81 min; loam L->B 0.80. Payload = MIN(heaped x 0.833, rated load lb / 2,300 lb/LCY) = 36.7 LCY | Payload LCY = MIN(44 x 0.833 (FM 621B: 20 LCY from 24 yd3), 104000 lb / 2,300); trips/hr = 60 x E / (load + 0.81 + 3000/(v_haul x 88) + 3000/(v_return x 88)); BCY/hr = trips x payload x 0.80. Loaded top speed is a maximum, not an average haul speed, so Settings speeds are left blank. | FM5434;USMC-PE;KSU-T6;CAT-SCR-PG | D | Needs scraper haul/return speeds (Settings B26-B27; not sourced)
GR-COMPACT | EW-FGRADE | Compact grader | Fine grade subgrade/base with motor grader | [5 empty] | SY/hr | n/a | Moldboard length not in notes | No moldboard | CAT-MG | D | Needs moldboard length
GR-12FT-120 | EW-FGRADE | 12 ft (Cat 120) | Fine grade subgrade/base with motor grader | 12 | ft moldboard | 1532.4349 | 2724.3286 | 3405.4108 | SY/hr | Calculated: job-adjusted (E from Settings) | Finish grading 1.5/2.0/2.5 mph (within Cat 0-2.5 mph band); blade at 30 deg; 2 ft overlap; passes 4/3/3 (output is completed area) | SY/hr = mph x (L x cos30 - 2) x 5,280 x E / 9 / passes. Typ: 2.0 x 8.4 x 5,280 x 0.83 / 9 / 3 = 2,724 | CAT-MG;KSU-T7;CAT-GR-PG | C
GR-12FT-120 | EW-RGRADE-GR | 12 ft (Cat 120) | Rough grade / heavy blading with motor grader (PER PASS) | 12 | ft moldboard | 6315.7994 | 9473.699 | 12631.5987 | SY/hr per pass | Calculated: job-adjusted (E from Settings) | Heavy blading 2/3/4 mph (within Cat 0-6 mph band); blade at 45 deg; 2 ft overlap. PER PASS: hours = area / rate x number of passes | SY per hour per pass = mph x (L x cos45 - 2) x 5,280 x E / 9. Typ: 3 x 6.5 x 5,280 x 0.83 / 9 = 9,474 | CAT-MG;CAT-GR-PG | C
GR-12FT-120 | EW-SPREAD-BASE | 12 ft (Cat 120) | Spread and shape aggregate base (grader-led spread) |  |  | 500 | 750 | 1250 | CY/day | DOT field daily (crew) | Flex base, one crew | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
GR-12FT-140 | EW-FGRADE | 12 ft (Cat 140) | Fine grade subgrade/base with motor grader | 12 | ft moldboard | 1532.4349 | 2724.3286 | 3405.4108 | SY/hr | Calculated: job-adjusted (E from Settings) | Finish grading 1.5/2.0/2.5 mph (within Cat 0-2.5 mph band); blade at 30 deg; 2 ft overlap; passes 4/3/3 (output is completed area) | SY/hr = mph x (L x cos30 - 2) x 5,280 x E / 9 / passes. Typ: 2.0 x 8.4 x 5,280 x 0.83 / 9 / 3 = 2,724 | CAT-MG;KSU-T7;CAT-GR-PG | C
GR-12FT-140 | EW-RGRADE-GR | 12 ft (Cat 140) | Rough grade / heavy blading with motor grader (PER PASS) | 12 | ft moldboard | 6315.7994 | 9473.699 | 12631.5987 | SY/hr per pass | Calculated: job-adjusted (E from Settings) | Heavy blading 2/3/4 mph (within Cat 0-6 mph band); blade at 45 deg; 2 ft overlap. PER PASS: hours = area / rate x number of passes | SY per hour per pass = mph x (L x cos45 - 2) x 5,280 x E / 9. Typ: 3 x 6.5 x 5,280 x 0.83 / 9 = 9,474 | CAT-MG;CAT-GR-PG | C
GR-12FT-140 | EW-SPREAD-BASE | 12 ft (Cat 140) | Spread and shape aggregate base (grader-led spread) |  |  | 500 | 750 | 1250 | CY/day | DOT field daily (crew) | Flex base, one crew | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
GR-12FT-120GC | EW-FGRADE | 12 ft (Cat 120 GC) | Fine grade subgrade/base with motor grader | 12 | ft moldboard | 1532.4349 | 2724.3286 | 3405.4108 | SY/hr | Calculated: job-adjusted (E from Settings) | Finish grading 1.5/2.0/2.5 mph (within Cat 0-2.5 mph band); blade at 30 deg; 2 ft overlap; passes 4/3/3 (output is completed area) | SY/hr = mph x (L x cos30 - 2) x 5,280 x E / 9 / passes. Typ: 2.0 x 8.4 x 5,280 x 0.83 / 9 / 3 = 2,724 | CAT-MG;KSU-T7;CAT-GR-PG | C
GR-12FT-120GC | EW-RGRADE-GR | 12 ft (Cat 120 GC) | Rough grade / heavy blading with motor grader (PER PASS) | 12 | ft moldboard | 6315.7994 | 9473.699 | 12631.5987 | SY/hr per pass | Calculated: job-adjusted (E from Settings) | Heavy blading 2/3/4 mph (within Cat 0-6 mph band); blade at 45 deg; 2 ft overlap. PER PASS: hours = area / rate x number of passes | SY per hour per pass = mph x (L x cos45 - 2) x 5,280 x E / 9. Typ: 3 x 6.5 x 5,280 x 0.83 / 9 = 9,474 | CAT-MG;CAT-GR-PG | C
GR-12FT-120GC | EW-SPREAD-BASE | 12 ft (Cat 120 GC) | Spread and shape aggregate base (grader-led spread) |  |  | 500 | 750 | 1250 | CY/day | DOT field daily (crew) | Flex base, one crew | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
GR-12FT-140GC | EW-FGRADE | 12 ft (Cat 140 GC) | Fine grade subgrade/base with motor grader | 12 | ft moldboard | 1532.4349 | 2724.3286 | 3405.4108 | SY/hr | Calculated: job-adjusted (E from Settings) | Finish grading 1.5/2.0/2.5 mph (within Cat 0-2.5 mph band); blade at 30 deg; 2 ft overlap; passes 4/3/3 (output is completed area) | SY/hr = mph x (L x cos30 - 2) x 5,280 x E / 9 / passes. Typ: 2.0 x 8.4 x 5,280 x 0.83 / 9 / 3 = 2,724 | CAT-MG;KSU-T7;CAT-GR-PG | C
GR-12FT-140GC | EW-RGRADE-GR | 12 ft (Cat 140 GC) | Rough grade / heavy blading with motor grader (PER PASS) | 12 | ft moldboard | 6315.7994 | 9473.699 | 12631.5987 | SY/hr per pass | Calculated: job-adjusted (E from Settings) | Heavy blading 2/3/4 mph (within Cat 0-6 mph band); blade at 45 deg; 2 ft overlap. PER PASS: hours = area / rate x number of passes | SY per hour per pass = mph x (L x cos45 - 2) x 5,280 x E / 9. Typ: 3 x 6.5 x 5,280 x 0.83 / 9 = 9,474 | CAT-MG;CAT-GR-PG | C
GR-12FT-140GC | EW-SPREAD-BASE | 12 ft (Cat 140 GC) | Spread and shape aggregate base (grader-led spread) |  |  | 500 | 750 | 1250 | CY/day | DOT field daily (crew) | Flex base, one crew | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
GR-12FT-150 | EW-FGRADE | 12 ft (Cat 150) | Fine grade subgrade/base with motor grader | 12 | ft moldboard | 1532.4349 | 2724.3286 | 3405.4108 | SY/hr | Calculated: job-adjusted (E from Settings) | Finish grading 1.5/2.0/2.5 mph (within Cat 0-2.5 mph band); blade at 30 deg; 2 ft overlap; passes 4/3/3 (output is completed area) | SY/hr = mph x (L x cos30 - 2) x 5,280 x E / 9 / passes. Typ: 2.0 x 8.4 x 5,280 x 0.83 / 9 / 3 = 2,724 | CAT-MG;KSU-T7;CAT-GR-PG | C
GR-12FT-150 | EW-RGRADE-GR | 12 ft (Cat 150) | Rough grade / heavy blading with motor grader (PER PASS) | 12 | ft moldboard | 6315.7994 | 9473.699 | 12631.5987 | SY/hr per pass | Calculated: job-adjusted (E from Settings) | Heavy blading 2/3/4 mph (within Cat 0-6 mph band); blade at 45 deg; 2 ft overlap. PER PASS: hours = area / rate x number of passes | SY per hour per pass = mph x (L x cos45 - 2) x 5,280 x E / 9. Typ: 3 x 6.5 x 5,280 x 0.83 / 9 = 9,474 | CAT-MG;CAT-GR-PG | C
GR-12FT-150 | EW-SPREAD-BASE | 12 ft (Cat 150) | Spread and shape aggregate base (grader-led spread) |  |  | 500 | 750 | 1250 | CY/day | DOT field daily (crew) | Flex base, one crew | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
GR-14FT-160 | EW-FGRADE | 14 ft (Cat 160) | Fine grade subgrade/base with motor grader | 14 | ft moldboard | 1848.7073 | 3286.5908 | 4108.2385 | SY/hr | Calculated: job-adjusted (E from Settings) | Finish grading 1.5/2.0/2.5 mph (within Cat 0-2.5 mph band); blade at 30 deg; 2 ft overlap; passes 4/3/3 (output is completed area) | SY/hr = mph x (L x cos30 - 2) x 5,280 x E / 9 / passes. Typ: 2.0 x 10.1 x 5,280 x 0.83 / 9 / 3 = 3,287 | CAT-MG;KSU-T7;CAT-GR-PG | C
GR-14FT-160 | EW-RGRADE-GR | 14 ft (Cat 160) | Rough grade / heavy blading with motor grader (PER PASS) | 14 | ft moldboard | 7693.0548 | 11539.5822 | 15386.1096 | SY/hr per pass | Calculated: job-adjusted (E from Settings) | Heavy blading 2/3/4 mph (within Cat 0-6 mph band); blade at 45 deg; 2 ft overlap. PER PASS: hours = area / rate x number of passes | SY per hour per pass = mph x (L x cos45 - 2) x 5,280 x E / 9. Typ: 3 x 7.9 x 5,280 x 0.83 / 9 = 11,540 | CAT-MG;CAT-GR-PG | C
GR-14FT-160 | EW-SPREAD-BASE | 14 ft (Cat 160) | Spread and shape aggregate base (grader-led spread) |  |  | 500 | 750 | 1250 | CY/day | DOT field daily (crew) | Flex base, one crew | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
GR-14FT-14 | EW-FGRADE | 14 ft (Cat 14) | Fine grade subgrade/base with motor grader | 14 | ft moldboard | 1848.7073 | 3286.5908 | 4108.2385 | SY/hr | Calculated: job-adjusted (E from Settings) | Finish grading 1.5/2.0/2.5 mph (within Cat 0-2.5 mph band); blade at 30 deg; 2 ft overlap; passes 4/3/3 (output is completed area) | SY/hr = mph x (L x cos30 - 2) x 5,280 x E / 9 / passes. Typ: 2.0 x 10.1 x 5,280 x 0.83 / 9 / 3 = 3,287 | CAT-MG;KSU-T7;CAT-GR-PG | C
GR-14FT-14 | EW-RGRADE-GR | 14 ft (Cat 14) | Rough grade / heavy blading with motor grader (PER PASS) | 14 | ft moldboard | 7693.0548 | 11539.5822 | 15386.1096 | SY/hr per pass | Calculated: job-adjusted (E from Settings) | Heavy blading 2/3/4 mph (within Cat 0-6 mph band); blade at 45 deg; 2 ft overlap. PER PASS: hours = area / rate x number of passes | SY per hour per pass = mph x (L x cos45 - 2) x 5,280 x E / 9. Typ: 3 x 7.9 x 5,280 x 0.83 / 9 = 11,540 | CAT-MG;CAT-GR-PG | C
GR-14FT-14 | EW-SPREAD-BASE | 14 ft (Cat 14) | Spread and shape aggregate base (grader-led spread) |  |  | 500 | 750 | 1250 | CY/day | DOT field daily (crew) | Flex base, one crew | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
GR-16FT-16 | EW-FGRADE | 16 ft (Cat 16) | Fine grade subgrade/base with motor grader | 16 | ft moldboard | 2164.9798 | 3848.853 | 4811.0663 | SY/hr | Calculated: job-adjusted (E from Settings) | Finish grading 1.5/2.0/2.5 mph (within Cat 0-2.5 mph band); blade at 30 deg; 2 ft overlap; passes 4/3/3 (output is completed area) | SY/hr = mph x (L x cos30 - 2) x 5,280 x E / 9 / passes. Typ: 2.0 x 11.9 x 5,280 x 0.83 / 9 / 3 = 3,849 | CAT-MG;KSU-T7;CAT-GR-PG | C
GR-16FT-16 | EW-RGRADE-GR | 16 ft (Cat 16) | Rough grade / heavy blading with motor grader (PER PASS) | 16 | ft moldboard | 9070.3103 | 13605.4654 | 18140.6205 | SY/hr per pass | Calculated: job-adjusted (E from Settings) | Heavy blading 2/3/4 mph (within Cat 0-6 mph band); blade at 45 deg; 2 ft overlap. PER PASS: hours = area / rate x number of passes | SY per hour per pass = mph x (L x cos45 - 2) x 5,280 x E / 9. Typ: 3 x 9.3 x 5,280 x 0.83 / 9 = 13,605 | CAT-MG;CAT-GR-PG | C
GR-16FT-16 | EW-SPREAD-BASE | 16 ft (Cat 16) | Spread and shape aggregate base (grader-led spread) |  |  | 500 | 750 | 1250 | CY/day | DOT field daily (crew) | Flex base, one crew | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
GR-18FT-18 | EW-FGRADE | 18 ft (Cat 18) | Fine grade subgrade/base with motor grader | 18 | ft moldboard | 2481.2523 | 4411.1152 | 5513.894 | SY/hr | Calculated: job-adjusted (E from Settings) | Finish grading 1.5/2.0/2.5 mph (within Cat 0-2.5 mph band); blade at 30 deg; 2 ft overlap; passes 4/3/3 (output is completed area) | SY/hr = mph x (L x cos30 - 2) x 5,280 x E / 9 / passes. Typ: 2.0 x 13.6 x 5,280 x 0.83 / 9 / 3 = 4,411 | CAT-MG;KSU-T7;CAT-GR-PG | C
GR-18FT-18 | EW-RGRADE-GR | 18 ft (Cat 18) | Rough grade / heavy blading with motor grader (PER PASS) | 18 | ft moldboard | 10447.5657 | 15671.3485 | 20895.1314 | SY/hr per pass | Calculated: job-adjusted (E from Settings) | Heavy blading 2/3/4 mph (within Cat 0-6 mph band); blade at 45 deg; 2 ft overlap. PER PASS: hours = area / rate x number of passes | SY per hour per pass = mph x (L x cos45 - 2) x 5,280 x E / 9. Typ: 3 x 10.7 x 5,280 x 0.83 / 9 = 15,671 | CAT-MG;CAT-GR-PG | C
GR-18FT-18 | EW-SPREAD-BASE | 18 ft (Cat 18) | Spread and shape aggregate base (grader-led spread) |  |  | 500 | 750 | 1250 | CY/day | DOT field daily (crew) | Flex base, one crew | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
GR-24FT-24 | EW-FGRADE | 24 ft (Cat 24) | Fine grade subgrade/base with motor grader | 24 | ft moldboard | 3430.0697 | 6097.9017 | 7622.3772 | SY/hr | Calculated: job-adjusted (E from Settings) | Finish grading 1.5/2.0/2.5 mph (within Cat 0-2.5 mph band); blade at 30 deg; 2 ft overlap; passes 4/3/3 (output is completed area) | SY/hr = mph x (L x cos30 - 2) x 5,280 x E / 9 / passes. Typ: 2.0 x 18.8 x 5,280 x 0.83 / 9 / 3 = 6,098 | CAT-MG;KSU-T7;CAT-GR-PG | C
GR-24FT-24 | EW-RGRADE-GR | 24 ft (Cat 24) | Rough grade / heavy blading with motor grader (PER PASS) | 24 | ft moldboard | 14579.332 | 21868.9981 | 29158.6641 | SY/hr per pass | Calculated: job-adjusted (E from Settings) | Heavy blading 2/3/4 mph (within Cat 0-6 mph band); blade at 45 deg; 2 ft overlap. PER PASS: hours = area / rate x number of passes | SY per hour per pass = mph x (L x cos45 - 2) x 5,280 x E / 9. Typ: 3 x 15.0 x 5,280 x 0.83 / 9 = 21,869 | CAT-MG;CAT-GR-PG | C
GR-24FT-24 | EW-SPREAD-BASE | 24 ft (Cat 24) | Spread and shape aggregate base (grader-led spread) |  |  | 500 | 750 | 1250 | CY/day | DOT field daily (crew) | Flex base, one crew | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
ADT-25T | EW-HAUL-ADT-05 | 26.5 t payload | Haul with ADT, 0.5 mi one-way | 19.6 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 19.6 yd3, payload 26.5 t x 2,000 / 2,300 lb/LCY = 23.0) = 19.6 LCY (Cat 725 26.5 t / 19.6 yd3 heaped). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-25T | EW-HAUL-ADT-10 | 26.5 t payload | Haul with ADT, 1 mi one-way | 19.6 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 19.6 yd3, payload 26.5 t x 2,000 / 2,300 lb/LCY = 23.0) = 19.6 LCY (Cat 725 26.5 t / 19.6 yd3 heaped). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-25T | EW-HAUL-ADT-20 | 26.5 t payload | Haul with ADT, 2 mi one-way | 19.6 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 2.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 2.0x60/v_loaded + 2.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 19.6 yd3, payload 26.5 t x 2,000 / 2,300 lb/LCY = 23.0) = 19.6 LCY (Cat 725 26.5 t / 19.6 yd3 heaped). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-30T | EW-HAUL-ADT-05 | 30 t payload | Haul with ADT, 0.5 mi one-way | 23.3 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 23.3 yd3, payload 32 t x 2,000 / 2,300 lb/LCY = 27.8) = 23.3 LCY (Volvo A30 32 st / 23.3 yd3 (class proxy; Cat 730 heaped not in specs)). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-30T | EW-HAUL-ADT-10 | 30 t payload | Haul with ADT, 1 mi one-way | 23.3 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 23.3 yd3, payload 32 t x 2,000 / 2,300 lb/LCY = 27.8) = 23.3 LCY (Volvo A30 32 st / 23.3 yd3 (class proxy; Cat 730 heaped not in specs)). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-30T | EW-HAUL-ADT-20 | 30 t payload | Haul with ADT, 2 mi one-way | 23.3 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 2.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 2.0x60/v_loaded + 2.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 23.3 yd3, payload 32 t x 2,000 / 2,300 lb/LCY = 27.8) = 23.3 LCY (Volvo A30 32 st / 23.3 yd3 (class proxy; Cat 730 heaped not in specs)). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-35T | EW-HAUL-ADT-05 | 35.3 t payload | Haul with ADT, 0.5 mi one-way | 28.4 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 28.4 yd3, payload 38 t x 2,000 / 2,300 lb/LCY = 33.0) = 28.4 LCY (Volvo A35 38 st / 28.4 yd3 (class proxy)). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-35T | EW-HAUL-ADT-10 | 35.3 t payload | Haul with ADT, 1 mi one-way | 28.4 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 28.4 yd3, payload 38 t x 2,000 / 2,300 lb/LCY = 33.0) = 28.4 LCY (Volvo A35 38 st / 28.4 yd3 (class proxy)). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-35T | EW-HAUL-ADT-20 | 35.3 t payload | Haul with ADT, 2 mi one-way | 28.4 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 2.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 2.0x60/v_loaded + 2.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 28.4 yd3, payload 38 t x 2,000 / 2,300 lb/LCY = 33.0) = 28.4 LCY (Volvo A35 38 st / 28.4 yd3 (class proxy)). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-40T | EW-HAUL-ADT-05 | 40 t payload | Haul with ADT, 0.5 mi one-way | 31.4 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 31.4 yd3, payload 43 t x 2,000 / 2,300 lb/LCY = 37.4) = 31.4 LCY (Volvo A40G 43 st / 31.4 yd3 (class proxy)). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-40T | EW-HAUL-ADT-10 | 40 t payload | Haul with ADT, 1 mi one-way | 31.4 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 31.4 yd3, payload 43 t x 2,000 / 2,300 lb/LCY = 37.4) = 31.4 LCY (Volvo A40G 43 st / 31.4 yd3 (class proxy)). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-40T | EW-HAUL-ADT-20 | 40 t payload | Haul with ADT, 2 mi one-way | 31.4 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 2.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 2.0x60/v_loaded + 2.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 31.4 yd3, payload 43 t x 2,000 / 2,300 lb/LCY = 37.4) = 31.4 LCY (Volvo A40G 43 st / 31.4 yd3 (class proxy)). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-45T | EW-HAUL-ADT-05 | 45.2 t payload | Haul with ADT, 0.5 mi one-way | 33.4 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 33.4 yd3, payload 45.2 t x 2,000 / 2,300 lb/LCY = 39.3) = 33.4 LCY (Cat 745 45.2 t / 33.4 yd3). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-45T | EW-HAUL-ADT-10 | 45.2 t payload | Haul with ADT, 1 mi one-way | 33.4 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 33.4 yd3, payload 45.2 t x 2,000 / 2,300 lb/LCY = 39.3) = 33.4 LCY (Cat 745 45.2 t / 33.4 yd3). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-45T | EW-HAUL-ADT-20 | 45.2 t payload | Haul with ADT, 2 mi one-way | 33.4 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 2.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 2.0x60/v_loaded + 2.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 33.4 yd3, payload 45.2 t x 2,000 / 2,300 lb/LCY = 39.3) = 33.4 LCY (Cat 745 45.2 t / 33.4 yd3). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-EJ-30T | EW-HAUL-ADT-05 | 30 t payload (ejector) | Haul with ADT, 0.5 mi one-way | 26.1 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 30 t x 2,000 / 2,300 lb/LCY = 26.1 LCY (heaped not in specs; weight-limited). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434 | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-EJ-30T | EW-HAUL-ADT-10 | 30 t payload (ejector) | Haul with ADT, 1 mi one-way | 26.1 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 30 t x 2,000 / 2,300 lb/LCY = 26.1 LCY (heaped not in specs; weight-limited). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434 | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-EJ-42T | EW-HAUL-ADT-05 | 42 t payload (ejector) | Haul with ADT, 0.5 mi one-way | 36.5 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 42 t x 2,000 / 2,300 lb/LCY = 36.5 LCY (heaped not in specs; weight-limited). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434 | D | Needs haul speeds (Settings B22-B25; not sourced)
ADT-EJ-42T | EW-HAUL-ADT-10 | 42 t payload (ejector) | Haul with ADT, 1 mi one-way | 36.5 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 42 t x 2,000 / 2,300 lb/LCY = 36.5 LCY (heaped not in specs; weight-limited). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434 | D | Needs haul speeds (Settings B22-B25; not sourced)
RDT-770 | EW-HAUL-RDT-10 | 42.1 t payload | Haul with rigid off-highway truck, 1 mi one-way | 36.6 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 42.1 t x 2,000 / 2,300 lb/LCY = 36.6 LCY (heaped not in specs; weight-limited). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434 | D | Needs haul speeds (Settings B22-B25; not sourced)
RDT-772 | EW-HAUL-RDT-10 | 51.6 t payload | Haul with rigid off-highway truck, 1 mi one-way | 40.8 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 40.8 yd3, payload 51.6 t x 2,000 / 2,300 lb/LCY = 44.9) = 40.8 LCY (Cat 772 51.6 t / 40.8 yd3). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
RDT-773 | EW-HAUL-RDT-10 | 61.7 t payload | Haul with rigid off-highway truck, 1 mi one-way | 46.8 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 46.75 yd3, payload 61.7 t x 2,000 / 2,300 lb/LCY = 53.7) = 46.8 LCY (Cat 773 61.7 t / 46.75 yd3). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
RDT-775 | EW-HAUL-RDT-10 | 70.5 t payload | Haul with rigid off-highway truck, 1 mi one-way | 61.3 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 70.5 t x 2,000 / 2,300 lb/LCY = 61.3 LCY (heaped not in specs; weight-limited). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434 | D | Needs haul speeds (Settings B22-B25; not sourced)
RDT-777 | EW-HAUL-RDT-10 | 101.1 t payload | Haul with rigid off-highway truck, 1 mi one-way | 83.1 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (ADT/rigid) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity MIN(heaped 83.1 yd3, payload 101.1 t x 2,000 / 2,300 lb/LCY = 87.9) = 83.1 LCY (Cat 777 101.1 t / 83.1 yd3). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FM5434;CAT-TRK-PG;VOLVO-ADT | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-7CY | EW-HAUL-TRK-05 | 7 CY struck | Haul with on-road dump truck, 0.5 mi one-way | 7 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 7 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-7CY | EW-HAUL-TRK-10 | 7 CY struck | Haul with on-road dump truck, 1 mi one-way | 7 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 7 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-7CY | EW-HAUL-TRK-20 | 7 CY struck | Haul with on-road dump truck, 2 mi one-way | 7 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 2.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 2.0x60/v_loaded + 2.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 7 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-9CY | EW-HAUL-TRK-05 | 9 CY struck | Haul with on-road dump truck, 0.5 mi one-way | 9 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 9 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-9CY | EW-HAUL-TRK-10 | 9 CY struck | Haul with on-road dump truck, 1 mi one-way | 9 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 9 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-9CY | EW-HAUL-TRK-20 | 9 CY struck | Haul with on-road dump truck, 2 mi one-way | 9 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 2.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 2.0x60/v_loaded + 2.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 9 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-12CY | EW-HAUL-TRK-05 | 12 CY struck | Haul with on-road dump truck, 0.5 mi one-way | 12 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 12 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-12CY | EW-HAUL-TRK-10 | 12 CY struck | Haul with on-road dump truck, 1 mi one-way | 12 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 12 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-12CY | EW-HAUL-TRK-20 | 12 CY struck | Haul with on-road dump truck, 2 mi one-way | 12 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 2.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 2.0x60/v_loaded + 2.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 12 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-14CY | EW-HAUL-TRK-05 | 14 CY struck | Haul with on-road dump truck, 0.5 mi one-way | 14 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 14 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-14CY | EW-HAUL-TRK-10 | 14 CY struck | Haul with on-road dump truck, 1 mi one-way | 14 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 14 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-14CY | EW-HAUL-TRK-20 | 14 CY struck | Haul with on-road dump truck, 2 mi one-way | 14 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 2.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 2.0x60/v_loaded + 2.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 14 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-18CY | EW-HAUL-TRK-05 | 18 CY struck | Haul with on-road dump truck, 0.5 mi one-way | 18 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 18 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-18CY | EW-HAUL-TRK-10 | 18 CY struck | Haul with on-road dump truck, 1 mi one-way | 18 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 18 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-ROAD-18CY | EW-HAUL-TRK-20 | 18 CY struck | Haul with on-road dump truck, 2 mi one-way | 18 | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 2.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 2.0x60/v_loaded + 2.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity 18 CY struck used as LCY (heaped not sourced; tandem dumps 10-16 yd3 per CTOS). Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6;FEMA25 | D | Needs haul speeds (Settings B22-B25; not sourced)
DT-OP-3AXLE | EW-HAUL-TRK-05 | 3-axle (tri-axle), operated | Haul with on-road dump truck, 0.5 mi one-way |  | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity not in notes/specs. Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6 | D | Needs haul speeds (Settings B22-B25; not sourced); Needs truck capacity
DT-OP-3AXLE | EW-HAUL-TRK-10 | 3-axle (tri-axle), operated | Haul with on-road dump truck, 1 mi one-way |  | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity not in notes/specs. Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6 | D | Needs haul speeds (Settings B22-B25; not sourced); Needs truck capacity
DT-OP-3AXLE | EW-HAUL-TRK-20 | 3-axle (tri-axle), operated | Haul with on-road dump truck, 2 mi one-way |  | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 2.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 2.0x60/v_loaded + 2.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity not in notes/specs. Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6 | D | Needs haul speeds (Settings B22-B25; not sourced); Needs truck capacity
DT-OP-4AXLE | EW-HAUL-TRK-05 | 4+ axle, operated | Haul with on-road dump truck, 0.5 mi one-way |  | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 0.5 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 0.5x60/v_loaded + 0.5x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity not in notes/specs. Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6 | D | Needs haul speeds (Settings B22-B25; not sourced); Needs truck capacity
DT-OP-4AXLE | EW-HAUL-TRK-10 | 4+ axle, operated | Haul with on-road dump truck, 1 mi one-way |  | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity not in notes/specs. Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6 | D | Needs haul speeds (Settings B22-B25; not sourced); Needs truck capacity
DT-OP-4AXLE | EW-HAUL-TRK-20 | 4+ axle, operated | Haul with on-road dump truck, 2 mi one-way |  | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 2.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 2.0x60/v_loaded + 2.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity not in notes/specs. Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6 | D | Needs haul speeds (Settings B22-B25; not sourced); Needs truck capacity
DT-OP-SEMI | EW-HAUL-TRK-10 | Tractor-trailer (semi end dump), operated | Haul with on-road dump truck, 1 mi one-way |  | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity not in notes/specs. Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6 | D | Needs haul speeds (Settings B22-B25; not sourced); Needs truck capacity
DT-OP-SEMI | EW-HAUL-TRK-20 | Tractor-trailer (semi end dump), operated | Haul with on-road dump truck, 2 mi one-way |  | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 2.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 2.0x60/v_loaded + 2.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity not in notes/specs. Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6 | D | Needs haul speeds (Settings B22-B25; not sourced); Needs truck capacity
CP-PLATE-FWD | EW-COMP-PLATE | ~150-200 lb forward plate | Compact with vibratory plate (structural/trench backfill) |  |  | 12.4884 | 19.9815 | 31.2211 | CCY/hr | Calculated from single-pass spec (E from Settings) | Wacker Neuson WP1550AW 19.5 in, 194 lb: 9,750 ft2/hr single pass (100 ft/min); lift 3/4/5 in, passes 6/5/4 | CCY/hr = ft2/hr / passes x E x lift(in)/12 / 27. Typ: 9,750/5 x 0.83 x 4/12/27 = 20.0 | WN-WP1550;MST-GE441;EDUREV | C
CP-PLATE-REV | EW-COMP-PLATE | ~800-1,100 lb reversible plate | Compact with vibratory plate (structural/trench backfill) |  |  | 10.9514 | 17.5222 | 27.3785 | CCY/hr | Calculated from single-pass spec (E from Settings) | ATE TP-1830H 18x18 in, 465 lb: 8,550 ft2/hr single pass - LIGHTER proxy than this 800-1,100 lb class (output likely understated); lift 3/4/5 in, passes 6/5/4 | CCY/hr = ft2/hr / passes x E x lift(in)/12 / 27. Typ: 8,550/5 x 0.83 x 4/12/27 = 17.5 | ATE-PLATE;MST-GE441;EDUREV | C | Proxy plate spec (lighter than class) - verify
CP-PLATE-REV | EW-COMP-TRENCH | ~800-1,100 lb reversible plate | Compact trench backfill (trench roller / reversible plate), 4-5 in lifts |  |  | 10.9514 | 17.5222 | 27.3785 | CCY/hr | Calculated from single-pass spec (E from Settings) | ATE TP-1830H 18x18 in, 465 lb: 8,550 ft2/hr single pass - LIGHTER proxy than this 800-1,100 lb class (output likely understated); lift 3/4/5 in, passes 6/5/4 | CCY/hr = ft2/hr / passes x E x lift(in)/12 / 27. Typ: 8,550/5 x 0.83 x 4/12/27 = 17.5 | ATE-PLATE;MST-GE441;EDUREV | C | Proxy plate spec (lighter than class) - verify
CP-RAMMER | EW-COMP-RAMMER | Rammer 100-140 lb | Compact with rammer (2-3 in lifts) |  |  | 1.3577 | 2.0366 | 3.0549 | CCY/hr | Calculated from single-pass spec (E from Settings) | Wacker Neuson BS60-4As 11 in shoe: ~1,590 ft2/hr (148 m2/hr), 28.9 ft/min; lift 2/2.5/3 in, passes 6/5/4 | CCY/hr = ft2/hr / passes x E x lift(in)/12 / 27. Typ: 1,590/5 x 0.83 x 2.5/12/27 = 2.0 | WN-BS60;MST-GE441;EDUREV | C
CP-TRENCH-ROLLER | EW-COMP-TRENCH | ~32-33 in, ~3,200 lb | Compact trench backfill (trench roller / reversible plate), 4-5 in lifts | 33 | in drum width | 28.2756 | 52.0866 | 88.1753 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 4 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical); trench compactors take lifts <=4-5 in | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 33/12 x 1.75 x 4 x 0.83 / 5 = 52 | KSU-T7;STORMW;EDUREV | C | Trench roller speed not sourced; vibratory 1 impact/inch rule applied
CP-SSL-VIBROLL | EW-COMP-SOIL-SM | 72-84 in SSL vibratory roller | Compact soil with small roller/attachment, 6 in lifts | 84 | in drum width | 107.9614 | 198.8763 | 336.6692 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 6 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 84/12 x 1.75 x 6 x 0.83 / 5 = 199 | KSU-T7;STORMW;EDUREV | C
CP-SD-48-SM | EW-COMP-SOIL-6 | 48-54 in smooth (~10,000 lb) | Compact soil, 6 in compacted lifts (ride-on roller) | 50 | in drum width | 64.2627 | 118.3787 | 200.3983 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 6 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 50/12 x 1.75 x 6 x 0.83 / 5 = 118 | KSU-T7;STORMW;EDUREV | C
CP-SD-48-SM | EW-COMP-SOIL-8 | 48-54 in smooth (~10,000 lb) | Compact soil, 8 in compacted lifts | 50 | in drum width | 85.6837 | 157.8383 | 267.1977 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 8 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 50/12 x 1.75 x 8 x 0.83 / 5 = 158 | KSU-T7;STORMW;EDUREV | C
CP-SD-66-SM | EW-COMP-SOIL-6 | 66-67 in smooth | Compact soil, 6 in compacted lifts (ride-on roller) | 66 | in drum width | 84.8268 | 156.26 | 264.5258 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 6 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 66/12 x 1.75 x 6 x 0.83 / 5 = 156 | KSU-T7;STORMW;EDUREV | C
CP-SD-66-SM | EW-COMP-SOIL-8 | 66-67 in smooth | Compact soil, 8 in compacted lifts | 66 | in drum width | 113.1024 | 208.3466 | 352.701 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 8 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 66/12 x 1.75 x 8 x 0.83 / 5 = 208 | KSU-T7;STORMW;EDUREV | C
CP-SD-66-PAD | EW-COMP-SOIL-6 | 66 in padfoot | Compact soil, 6 in compacted lifts (ride-on roller) | 66 | in drum width | 84.8268 | 156.26 | 264.5258 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 6 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 66/12 x 1.75 x 6 x 0.83 / 5 = 156 | KSU-T7;STORMW;EDUREV | C
CP-SD-66-PAD | EW-COMP-SOIL-8 | 66 in padfoot | Compact soil, 8 in compacted lifts | 66 | in drum width | 113.1024 | 208.3466 | 352.701 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 8 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 66/12 x 1.75 x 8 x 0.83 / 5 = 208 | KSU-T7;STORMW;EDUREV | C
CP-SD-84-SM | EW-COMP-SOIL-6 | 84 in smooth | Compact soil, 6 in compacted lifts (ride-on roller) | 84 | in drum width | 107.9614 | 198.8763 | 336.6692 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 6 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 84/12 x 1.75 x 6 x 0.83 / 5 = 199 | KSU-T7;STORMW;EDUREV | C
CP-SD-84-SM | EW-COMP-SOIL-8 | 84 in smooth | Compact soil, 8 in compacted lifts | 84 | in drum width | 143.9486 | 265.1684 | 448.8922 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 8 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 84/12 x 1.75 x 8 x 0.83 / 5 = 265 | KSU-T7;STORMW;EDUREV | C
CP-SD-84-SM | EW-COMP-SOIL-12 | 84 in smooth | Compact soil, 12 in compacted lifts (granular, heavy rollers) | 84 | in drum width | 215.9228 | 397.7526 | 673.3383 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 12 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 84/12 x 1.75 x 12 x 0.83 / 5 = 398 | KSU-T7;STORMW;EDUREV | C
CP-SD-84-PAD | EW-COMP-SOIL-6 | 84 in padfoot | Compact soil, 6 in compacted lifts (ride-on roller) | 84 | in drum width | 107.9614 | 198.8763 | 336.6692 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 6 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 84/12 x 1.75 x 6 x 0.83 / 5 = 199 | KSU-T7;STORMW;EDUREV | C
CP-SD-84-PAD | EW-COMP-SOIL-8 | 84 in padfoot | Compact soil, 8 in compacted lifts | 84 | in drum width | 143.9486 | 265.1684 | 448.8922 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 8 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 84/12 x 1.75 x 8 x 0.83 / 5 = 265 | KSU-T7;STORMW;EDUREV | C
CP-SD-84-PAD | EW-COMP-SOIL-12 | 84 in padfoot | Compact soil, 12 in compacted lifts (granular, heavy rollers) | 84 | in drum width | 215.9228 | 397.7526 | 673.3383 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 12 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 84/12 x 1.75 x 12 x 0.83 / 5 = 398 | KSU-T7;STORMW;EDUREV | C
CP-SD-84-HVY | EW-COMP-SOIL-6 | 84 in heavy (CS74/CS19 class, to ~41,600 lb) | Compact soil, 6 in compacted lifts (ride-on roller) | 84 | in drum width | 107.9614 | 198.8763 | 336.6692 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 6 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 84/12 x 1.75 x 6 x 0.83 / 5 = 199 | KSU-T7;STORMW;EDUREV | C
CP-SD-84-HVY | EW-COMP-SOIL-8 | 84 in heavy (CS74/CS19 class, to ~41,600 lb) | Compact soil, 8 in compacted lifts | 84 | in drum width | 143.9486 | 265.1684 | 448.8922 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 8 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 84/12 x 1.75 x 8 x 0.83 / 5 = 265 | KSU-T7;STORMW;EDUREV | C
CP-SD-84-HVY | EW-COMP-SOIL-12 | 84 in heavy (CS74/CS19 class, to ~41,600 lb) | Compact soil, 12 in compacted lifts (granular, heavy rollers) | 84 | in drum width | 215.9228 | 397.7526 | 673.3383 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 12 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 84/12 x 1.75 x 12 x 0.83 / 5 = 398 | KSU-T7;STORMW;EDUREV | C
CP-SD-48PAD | EW-COMP-SOIL-6 | ~48 in padfoot (FEMA 2-ton class) | Compact soil, 6 in compacted lifts (ride-on roller) |  | in drum width |  |  |  | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 6 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W x S x L x E / P (drum width needed) | KSU-T7;STORMW;EDUREV | D | Needs drum width
CP-SD-51PAD-CP563 | EW-COMP-SOIL-6 | Cat CP-563D 51 in (to 145 hp) | Compact soil, 6 in compacted lifts (ride-on roller) | 51 | in drum width | 65.548 | 120.7463 | 204.4063 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 6 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 51/12 x 1.75 x 6 x 0.83 / 5 = 121 | KSU-T7;STORMW;EDUREV | C
CP-SD-51PAD-CP563 | EW-COMP-SOIL-8 | Cat CP-563D 51 in (to 145 hp) | Compact soil, 8 in compacted lifts | 51 | in drum width | 87.3973 | 160.9951 | 272.5417 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 8 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 51/12 x 1.75 x 8 x 0.83 / 5 = 161 | KSU-T7;STORMW;EDUREV | C
CP-TAMP-815 | EW-COMP-SOIL-8 | Cat 815 (~249 hp) | Compact soil, 8 in compacted lifts |  | in drum width |  |  |  | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 8 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W x S x L x E / P (drum width needed) | KSU-T7;STORMW;EDUREV | D | Needs drum width
CP-TAMP-815 | EW-COMP-SOIL-12 | Cat 815 (~249 hp) | Compact soil, 12 in compacted lifts (granular, heavy rollers) |  | in drum width |  |  |  | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 12 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W x S x L x E / P (drum width needed) | KSU-T7;STORMW;EDUREV | D | Needs drum width
CP-TAMP-825 | EW-COMP-SOIL-8 | Cat 825 (~405 hp) | Compact soil, 8 in compacted lifts |  | in drum width |  |  |  | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 8 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W x S x L x E / P (drum width needed) | KSU-T7;STORMW;EDUREV | D | Needs drum width
CP-TAMP-825 | EW-COMP-SOIL-12 | Cat 825 (~405 hp) | Compact soil, 12 in compacted lifts (granular, heavy rollers) |  | in drum width |  |  |  | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 12 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W x S x L x E / P (drum width needed) | KSU-T7;STORMW;EDUREV | D | Needs drum width
CP-TANDEM-SMALL | PV-ROLL-HMA | 36-54 in double drum | Compact HMA mat (breakdown/intermediate/finish roller) | 47 | in drum/rolling width | 681.127 | 817.3524 | 1089.8032 | SY/hr | Calculated: job-adjusted (E from Settings) | Speed 2.5 / 3.0 / 4.0 mph (Roads & Bridges: static/vib <=2,400 vpm ~2.5 mph; vib to 3,600 vpm and pneumatic up to 4 mph; Asphalt Institute/Penn State 3 mph); 7 passes total (Penn State example) | SY/hr = mph x 5,280 x W(ft) / 9 x E / passes. Typ: 3 x 5,280 x 47/12 / 9 x 0.83 / 7 = 817 | AI-ROLL;PSU-SP;RB-HMA | C
CP-TANDEM-SMALL | EW-COMP-SOIL-SM | 36-54 in double drum | Compact soil with small roller/attachment, 6 in lifts | 47 | in drum width | 60.407 | 111.276 | 188.3744 | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 6 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P. Typ: 16.3 x 47/12 x 1.75 x 6 x 0.83 / 5 = 111 | KSU-T7;STORMW;EDUREV | C
CP-TANDEM-47 | PV-ROLL-HMA | 47 in double drum (to 75 hp) | Compact HMA mat (breakdown/intermediate/finish roller) | 47.2 | in drum/rolling width | 684.0254 | 820.8305 | 1094.4406 | SY/hr | Calculated: job-adjusted (E from Settings) | Speed 2.5 / 3.0 / 4.0 mph (Roads & Bridges: static/vib <=2,400 vpm ~2.5 mph; vib to 3,600 vpm and pneumatic up to 4 mph; Asphalt Institute/Penn State 3 mph); 7 passes total (Penn State example) | SY/hr = mph x 5,280 x W(ft) / 9 x E / passes. Typ: 3 x 5,280 x 47.2/12 / 9 x 0.83 / 7 = 821 | AI-ROLL;PSU-SP;RB-HMA | C
CP-TANDEM-54 | PV-ROLL-HMA | 54 in double drum | Compact HMA mat (breakdown/intermediate/finish roller) | 54 | in drum/rolling width | 782.5714 | 939.0857 | 1252.1143 | SY/hr | Calculated: job-adjusted (E from Settings) | Speed 2.5 / 3.0 / 4.0 mph (Roads & Bridges: static/vib <=2,400 vpm ~2.5 mph; vib to 3,600 vpm and pneumatic up to 4 mph; Asphalt Institute/Penn State 3 mph); 7 passes total (Penn State example) | SY/hr = mph x 5,280 x W(ft) / 9 x E / passes. Typ: 3 x 5,280 x 54/12 / 9 x 0.83 / 7 = 939 | AI-ROLL;PSU-SP;RB-HMA | C
CP-TANDEM-67 | PV-ROLL-HMA | 66-67 in double drum | Compact HMA mat (breakdown/intermediate/finish roller) | 67 | in drum/rolling width | 970.9683 | 1165.1619 | 1553.5492 | SY/hr | Calculated: job-adjusted (E from Settings) | Speed 2.5 / 3.0 / 4.0 mph (Roads & Bridges: static/vib <=2,400 vpm ~2.5 mph; vib to 3,600 vpm and pneumatic up to 4 mph; Asphalt Institute/Penn State 3 mph); 7 passes total (Penn State example) | SY/hr = mph x 5,280 x W(ft) / 9 x E / passes. Typ: 3 x 5,280 x 67/12 / 9 x 0.83 / 7 = 1,165 | AI-ROLL;PSU-SP;RB-HMA | C
CP-TANDEM-79 | PV-ROLL-HMA | 79 in double drum | Compact HMA mat (breakdown/intermediate/finish roller) | 79 | in drum/rolling width | 1144.873 | 1373.8476 | 1831.7968 | SY/hr | Calculated: job-adjusted (E from Settings) | Speed 2.5 / 3.0 / 4.0 mph (Roads & Bridges: static/vib <=2,400 vpm ~2.5 mph; vib to 3,600 vpm and pneumatic up to 4 mph; Asphalt Institute/Penn State 3 mph); 7 passes total (Penn State example) | SY/hr = mph x 5,280 x W(ft) / 9 x E / passes. Typ: 3 x 5,280 x 79/12 / 9 x 0.83 / 7 = 1,374 | AI-ROLL;PSU-SP;RB-HMA | C
CP-TANDEM-84 | PV-ROLL-HMA | 84 in double drum (~29,000-32,000 lb) | Compact HMA mat (breakdown/intermediate/finish roller) | 84 | in drum/rolling width | 1217.3333 | 1460.8 | 1947.7333 | SY/hr | Calculated: job-adjusted (E from Settings) | Speed 2.5 / 3.0 / 4.0 mph (Roads & Bridges: static/vib <=2,400 vpm ~2.5 mph; vib to 3,600 vpm and pneumatic up to 4 mph; Asphalt Institute/Penn State 3 mph); 7 passes total (Penn State example) | SY/hr = mph x 5,280 x W(ft) / 9 x E / passes. Typ: 3 x 5,280 x 84/12 / 9 x 0.83 / 7 = 1,461 | AI-ROLL;PSU-SP;RB-HMA | C
CP-COMBO | PV-ROLL-HMA | Combination 2.7-4.0 t | Compact HMA mat (breakdown/intermediate/finish roller) |  | in drum/rolling width |  |  |  | SY/hr | Calculated: job-adjusted (E from Settings) | Speed 2.5 / 3.0 / 4.0 mph (Roads & Bridges: static/vib <=2,400 vpm ~2.5 mph; vib to 3,600 vpm and pneumatic up to 4 mph; Asphalt Institute/Penn State 3 mph); 7 passes total (Penn State example) | SY/hr = mph x 5,280 x W(ft) / 9 x E / passes | AI-ROLL;PSU-SP;RB-HMA | D | Needs drum width
CP-PNEU-SMALL | PV-ROLL-HMA | 9-wheel ~5,000 lb | Compact HMA mat (breakdown/intermediate/finish roller) |  | in drum/rolling width |  |  |  | SY/hr | Calculated: job-adjusted (E from Settings) | Speed 2.5 / 3.0 / 4.0 mph (Roads & Bridges: static/vib <=2,400 vpm ~2.5 mph; vib to 3,600 vpm and pneumatic up to 4 mph; Asphalt Institute/Penn State 3 mph); 7 passes total (Penn State example) | SY/hr = mph x 5,280 x W(ft) / 9 x E / passes | AI-ROLL;PSU-SP;RB-HMA | D | Needs drum width
CP-PNEU-68 | PV-ROLL-HMA | ~33,000 lb ballasted (CW16 class) | Compact HMA mat (breakdown/intermediate/finish roller) | 68 | in drum/rolling width | 985.4603 | 1182.5524 | 1576.7365 | SY/hr | Calculated: job-adjusted (E from Settings) | Speed 2.5 / 3.0 / 4.0 mph (Roads & Bridges: static/vib <=2,400 vpm ~2.5 mph; vib to 3,600 vpm and pneumatic up to 4 mph; Asphalt Institute/Penn State 3 mph); 7 passes total (Penn State example) | SY/hr = mph x 5,280 x W(ft) / 9 x E / passes. Typ: 3 x 5,280 x 68/12 / 9 x 0.83 / 7 = 1,183 | AI-ROLL;PSU-SP;RB-HMA | C
CP-PNEU-68 | EW-COMP-SOIL-8 | ~33,000 lb ballasted (CW16 class) | Compact soil, 8 in compacted lifts |  | in drum width |  |  |  | CCY/hr | Calculated: job-adjusted (E from Settings) | Lift 8 in compacted; speed 1.14/1.75/2.37 mph (= 1 impact per inch at 1,200/1,850/2,500 vpm); passes 6/5/4 (low/typ/high; 4-6 typical) | CCY/hr = 16.3 x W x S x L x E / P (drum width needed) | KSU-T7;STORMW;EDUREV | D | Static pneumatic: vibratory speed rule does not apply; needs soil working speed
CP-PNEU-82 | PV-ROLL-HMA | 82 in, to ~59,500 lb ballasted (CW34 class) | Compact HMA mat (breakdown/intermediate/finish roller) | 82 | in drum/rolling width | 1188.3492 | 1426.019 | 1901.3587 | SY/hr | Calculated: job-adjusted (E from Settings) | Speed 2.5 / 3.0 / 4.0 mph (Roads & Bridges: static/vib <=2,400 vpm ~2.5 mph; vib to 3,600 vpm and pneumatic up to 4 mph; Asphalt Institute/Penn State 3 mph); 7 passes total (Penn State example) | SY/hr = mph x 5,280 x W(ft) / 9 x E / passes. Typ: 3 x 5,280 x 82/12 / 9 x 0.83 / 7 = 1,426 | AI-ROLL;PSU-SP;RB-HMA | C
CP-PNEU-82 | EW-PROOFROLL | 82 in, to ~59,500 lb ballasted (CW34 class) | Proof roll | [5 empty] | SY/hr | n/a |  | No proof-rolling rate source |  | D | Needs production rate
CP-PAVEROLLER-2T | PV-ROLL-HMA | 2-ton pavement roller | Compact HMA mat (breakdown/intermediate/finish roller) |  | in drum/rolling width |  |  |  | SY/hr | Calculated: job-adjusted (E from Settings) | Speed 2.5 / 3.0 / 4.0 mph (Roads & Bridges: static/vib <=2,400 vpm ~2.5 mph; vib to 3,600 vpm and pneumatic up to 4 mph; Asphalt Institute/Penn State 3 mph); 7 passes total (Penn State example) | SY/hr = mph x 5,280 x W(ft) / 9 x E / passes | AI-ROLL;PSU-SP;RB-HMA | D | Needs drum width
PV-PAVER-TOWED | PV-HMA-LOT | Towed paver 8 ft | Place HMA, small urban / lots / thin overlay |  |  | 200 | 425 | 750 | TON/day | DOT field daily (crew) | Small urban / thin overlay | Typ = median of NCDOT small urban mid 350 and TxDOT thin overlay med 500; low 200; high 750. Crew/spread rate: equipment hours = crew days x hours/day. | NCDOT;TXDOT | A
PV-PAVER-P195 | PV-HMA-LOT | 3'10"-7' (P195 class) | Place HMA, small urban / lots / thin overlay |  |  | 200 | 425 | 750 | TON/day | DOT field daily (crew) | Small urban / thin overlay | Typ = median of NCDOT small urban mid 350 and TxDOT thin overlay med 500; low 200; high 750. Crew/spread rate: equipment hours = crew days x hours/day. | NCDOT;TXDOT | A
PV-PAVER-COMM | PV-HMA-LOT | 8-15'8" (P265-P395B class) | Place HMA, small urban / lots / thin overlay |  |  | 200 | 425 | 750 | TON/day | DOT field daily (crew) | Small urban / thin overlay | Typ = median of NCDOT small urban mid 350 and TxDOT thin overlay med 500; low 200; high 750. Crew/spread rate: equipment hours = crew days x hours/day. | NCDOT;TXDOT | A
PV-PAVER-COMM | PV-HMA-ROAD | 8-15'8" (P265-P395B class) | Place HMA, highway/road paving spread |  |  | 505 | 1400 | 2200 | TON/day | DOT field daily median (crew) | Mainline HMA, supply-governed spread | Typ = median of one typical per agency: TxDOT 989 (mean of ACP 978 / Superpave 1,000), WisDOT 1,300, NCDOT mainline mid 1,400 (800-2,000), FHWA CFL mid 1,650, WSDOT West mid 1,700 (1,200-2,200) -> 1,400; low TxDOT ACP 505; high WSDOT West 2,200 (WSDOT East up to 3,000 not used). Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;FHWA-CFL;NCDOT;WSDOT | A
PV-PAVER-AP355 | PV-HMA-LOT | Cat AP355 | Place HMA, small urban / lots / thin overlay |  |  | 200 | 425 | 750 | TON/day | DOT field daily (crew) | Small urban / thin overlay | Typ = median of NCDOT small urban mid 350 and TxDOT thin overlay med 500; low 200; high 750. Crew/spread rate: equipment hours = crew days x hours/day. | NCDOT;TXDOT | A
PV-PAVER-AP400 | PV-HMA-ROAD | Cat AP400 (8'-19'6") | Place HMA, highway/road paving spread |  |  | 505 | 1400 | 2200 | TON/day | DOT field daily median (crew) | Mainline HMA, supply-governed spread | Typ = median of one typical per agency: TxDOT 989 (mean of ACP 978 / Superpave 1,000), WisDOT 1,300, NCDOT mainline mid 1,400 (800-2,000), FHWA CFL mid 1,650, WSDOT West mid 1,700 (1,200-2,200) -> 1,400; low TxDOT ACP 505; high WSDOT West 2,200 (WSDOT East up to 3,000 not used). Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;FHWA-CFL;NCDOT;WSDOT | A
PV-PAVER-AP400 | PV-HMA-LOT | Cat AP400 (8'-19'6") | Place HMA, small urban / lots / thin overlay |  |  | 200 | 425 | 750 | TON/day | DOT field daily (crew) | Small urban / thin overlay | Typ = median of NCDOT small urban mid 350 and TxDOT thin overlay med 500; low 200; high 750. Crew/spread rate: equipment hours = crew days x hours/day. | NCDOT;TXDOT | A
PV-PAVER-AP455 | PV-HMA-ROAD | Cat AP455 (8'-19'6") | Place HMA, highway/road paving spread |  |  | 505 | 1400 | 2200 | TON/day | DOT field daily median (crew) | Mainline HMA, supply-governed spread | Typ = median of one typical per agency: TxDOT 989 (mean of ACP 978 / Superpave 1,000), WisDOT 1,300, NCDOT mainline mid 1,400 (800-2,000), FHWA CFL mid 1,650, WSDOT West mid 1,700 (1,200-2,200) -> 1,400; low TxDOT ACP 505; high WSDOT West 2,200 (WSDOT East up to 3,000 not used). Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;FHWA-CFL;NCDOT;WSDOT | A
PV-PAVER-AP455 | PV-HMA-LOT | Cat AP455 (8'-19'6") | Place HMA, small urban / lots / thin overlay |  |  | 200 | 425 | 750 | TON/day | DOT field daily (crew) | Small urban / thin overlay | Typ = median of NCDOT small urban mid 350 and TxDOT thin overlay med 500; low 200; high 750. Crew/spread rate: equipment hours = crew days x hours/day. | NCDOT;TXDOT | A
PV-PAVER-AP500 | PV-HMA-ROAD | Cat AP500 (8'-19'6") | Place HMA, highway/road paving spread |  |  | 505 | 1400 | 2200 | TON/day | DOT field daily median (crew) | Mainline HMA, supply-governed spread | Typ = median of one typical per agency: TxDOT 989 (mean of ACP 978 / Superpave 1,000), WisDOT 1,300, NCDOT mainline mid 1,400 (800-2,000), FHWA CFL mid 1,650, WSDOT West mid 1,700 (1,200-2,200) -> 1,400; low TxDOT ACP 505; high WSDOT West 2,200 (WSDOT East up to 3,000 not used). Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;FHWA-CFL;NCDOT;WSDOT | A
PV-PAVER-AP500 | PV-HMA-LOT | Cat AP500 (8'-19'6") | Place HMA, small urban / lots / thin overlay |  |  | 200 | 425 | 750 | TON/day | DOT field daily (crew) | Small urban / thin overlay | Typ = median of NCDOT small urban mid 350 and TxDOT thin overlay med 500; low 200; high 750. Crew/spread rate: equipment hours = crew days x hours/day. | NCDOT;TXDOT | A
PV-PAVER-AP555 | PV-HMA-ROAD | Cat AP555 (8'-20') | Place HMA, highway/road paving spread |  |  | 505 | 1400 | 2200 | TON/day | DOT field daily median (crew) | Mainline HMA, supply-governed spread | Typ = median of one typical per agency: TxDOT 989 (mean of ACP 978 / Superpave 1,000), WisDOT 1,300, NCDOT mainline mid 1,400 (800-2,000), FHWA CFL mid 1,650, WSDOT West mid 1,700 (1,200-2,200) -> 1,400; low TxDOT ACP 505; high WSDOT West 2,200 (WSDOT East up to 3,000 not used). Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;FHWA-CFL;NCDOT;WSDOT | A
PV-PAVER-AP555 | PV-HMA-LOT | Cat AP555 (8'-20') | Place HMA, small urban / lots / thin overlay |  |  | 200 | 425 | 750 | TON/day | DOT field daily (crew) | Small urban / thin overlay | Typ = median of NCDOT small urban mid 350 and TxDOT thin overlay med 500; low 200; high 750. Crew/spread rate: equipment hours = crew days x hours/day. | NCDOT;TXDOT | A
PV-PAVER-AP600 | PV-HMA-ROAD | Cat AP600 (8'-20'6") | Place HMA, highway/road paving spread |  |  | 505 | 1400 | 2200 | TON/day | DOT field daily median (crew) | Mainline HMA, supply-governed spread | Typ = median of one typical per agency: TxDOT 989 (mean of ACP 978 / Superpave 1,000), WisDOT 1,300, NCDOT mainline mid 1,400 (800-2,000), FHWA CFL mid 1,650, WSDOT West mid 1,700 (1,200-2,200) -> 1,400; low TxDOT ACP 505; high WSDOT West 2,200 (WSDOT East up to 3,000 not used). Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;FHWA-CFL;NCDOT;WSDOT | A
PV-PAVER-AP600 | PV-HMA-LOT | Cat AP600 (8'-20'6") | Place HMA, small urban / lots / thin overlay |  |  | 200 | 425 | 750 | TON/day | DOT field daily (crew) | Small urban / thin overlay | Typ = median of NCDOT small urban mid 350 and TxDOT thin overlay med 500; low 200; high 750. Crew/spread rate: equipment hours = crew days x hours/day. | NCDOT;TXDOT | A
PV-PAVER-AP655 | PV-HMA-ROAD | Cat AP655 (8'-20'6") | Place HMA, highway/road paving spread |  |  | 505 | 1400 | 2200 | TON/day | DOT field daily median (crew) | Mainline HMA, supply-governed spread | Typ = median of one typical per agency: TxDOT 989 (mean of ACP 978 / Superpave 1,000), WisDOT 1,300, NCDOT mainline mid 1,400 (800-2,000), FHWA CFL mid 1,650, WSDOT West mid 1,700 (1,200-2,200) -> 1,400; low TxDOT ACP 505; high WSDOT West 2,200 (WSDOT East up to 3,000 not used). Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;FHWA-CFL;NCDOT;WSDOT | A
PV-PAVER-AP655 | PV-HMA-LOT | Cat AP655 (8'-20'6") | Place HMA, small urban / lots / thin overlay |  |  | 200 | 425 | 750 | TON/day | DOT field daily (crew) | Small urban / thin overlay | Typ = median of NCDOT small urban mid 350 and TxDOT thin overlay med 500; low 200; high 750. Crew/spread rate: equipment hours = crew days x hours/day. | NCDOT;TXDOT | A
PV-PAVER-AP1000 | PV-HMA-ROAD | Cat AP1000 (10'-25'6") | Place HMA, highway/road paving spread |  |  | 505 | 1400 | 2200 | TON/day | DOT field daily median (crew) | Mainline HMA, supply-governed spread | Typ = median of one typical per agency: TxDOT 989 (mean of ACP 978 / Superpave 1,000), WisDOT 1,300, NCDOT mainline mid 1,400 (800-2,000), FHWA CFL mid 1,650, WSDOT West mid 1,700 (1,200-2,200) -> 1,400; low TxDOT ACP 505; high WSDOT West 2,200 (WSDOT East up to 3,000 not used). Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;FHWA-CFL;NCDOT;WSDOT | A
PV-PAVER-AP1000 | PV-HMA-LOT | Cat AP1000 (10'-25'6") | Place HMA, small urban / lots / thin overlay |  |  | 200 | 425 | 750 | TON/day | DOT field daily (crew) | Small urban / thin overlay | Typ = median of NCDOT small urban mid 350 and TxDOT thin overlay med 500; low 200; high 750. Crew/spread rate: equipment hours = crew days x hours/day. | NCDOT;TXDOT | A
PV-PAVER-AP1055 | PV-HMA-ROAD | Cat AP1055 (9'10"-25') | Place HMA, highway/road paving spread |  |  | 505 | 1400 | 2200 | TON/day | DOT field daily median (crew) | Mainline HMA, supply-governed spread | Typ = median of one typical per agency: TxDOT 989 (mean of ACP 978 / Superpave 1,000), WisDOT 1,300, NCDOT mainline mid 1,400 (800-2,000), FHWA CFL mid 1,650, WSDOT West mid 1,700 (1,200-2,200) -> 1,400; low TxDOT ACP 505; high WSDOT West 2,200 (WSDOT East up to 3,000 not used). Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;FHWA-CFL;NCDOT;WSDOT | A
PV-PAVER-AP1055 | PV-HMA-LOT | Cat AP1055 (9'10"-25') | Place HMA, small urban / lots / thin overlay |  |  | 200 | 425 | 750 | TON/day | DOT field daily (crew) | Small urban / thin overlay | Typ = median of NCDOT small urban mid 350 and TxDOT thin overlay med 500; low 200; high 750. Crew/spread rate: equipment hours = crew days x hours/day. | NCDOT;TXDOT | A
PV-MTV-8436 | PV-HMA-ROAD | Pickup machine / MTV (FEMA 8436) | Place HMA, highway/road paving spread |  |  | 505 | 1400 | 2200 | TON/day | DOT field daily median (crew) | Mainline HMA, supply-governed spread | Typ = median of one typical per agency: TxDOT 989 (mean of ACP 978 / Superpave 1,000), WisDOT 1,300, NCDOT mainline mid 1,400 (800-2,000), FHWA CFL mid 1,650, WSDOT West mid 1,700 (1,200-2,200) -> 1,400; low TxDOT ACP 505; high WSDOT West 2,200 (WSDOT East up to 3,000 not used). Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;FHWA-CFL;NCDOT;WSDOT | A
PV-MTV-8437 | PV-HMA-ROAD | Pickup machine / MTV (FEMA 8437) | Place HMA, highway/road paving spread |  |  | 505 | 1400 | 2200 | TON/day | DOT field daily median (crew) | Mainline HMA, supply-governed spread | Typ = median of one typical per agency: TxDOT 989 (mean of ACP 978 / Superpave 1,000), WisDOT 1,300, NCDOT mainline mid 1,400 (800-2,000), FHWA CFL mid 1,650, WSDOT West mid 1,700 (1,200-2,200) -> 1,400; low TxDOT ACP 505; high WSDOT West 2,200 (WSDOT East up to 3,000 not used). Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;FHWA-CFL;NCDOT;WSDOT | A
PV-MTV-8438 | PV-HMA-ROAD | Pickup machine / MTV (FEMA 8438) | Place HMA, highway/road paving spread |  |  | 505 | 1400 | 2200 | TON/day | DOT field daily median (crew) | Mainline HMA, supply-governed spread | Typ = median of one typical per agency: TxDOT 989 (mean of ACP 978 / Superpave 1,000), WisDOT 1,300, NCDOT mainline mid 1,400 (800-2,000), FHWA CFL mid 1,650, WSDOT West mid 1,700 (1,200-2,200) -> 1,400; low TxDOT ACP 505; high WSDOT West 2,200 (WSDOT East up to 3,000 not used). Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;FHWA-CFL;NCDOT;WSDOT | A
PV-MTV-8439 | PV-HMA-ROAD | Roadtec MTV-1000C (FEMA 8439) | Place HMA, highway/road paving spread |  |  | 505 | 1400 | 2200 | TON/day | DOT field daily median (crew) | Mainline HMA, supply-governed spread | Typ = median of one typical per agency: TxDOT 989 (mean of ACP 978 / Superpave 1,000), WisDOT 1,300, NCDOT mainline mid 1,400 (800-2,000), FHWA CFL mid 1,650, WSDOT West mid 1,700 (1,200-2,200) -> 1,400; low TxDOT ACP 505; high WSDOT West 2,200 (WSDOT East up to 3,000 not used). Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;FHWA-CFL;NCDOT;WSDOT | A
PV-MILL-SSL | PV-MILL-SMALL | SSL planer attachment | Cold plane (mill), small/compact machine |  | in drum width |  |  |  | SY/hr | Calculated (geometric) | Cutting speed 30 fpm, 50% efficiency (notes worked example); truck loading often governs deep cuts | SY/hr = drum width(ft) x fpm x 60 x 0.50 / 9 | CAT-PM310;WSDOT | D | Efficiency 0.50 from example, not Settings E; Needs drum width
PV-MILL-SMALL | PV-MILL-SMALL | 1-3 ft drum (60-250 hp) | Cold plane (mill), small/compact machine | 24 | in drum width |  | 200 |  | SY/hr | Calculated (geometric) | Cutting speed 30 fpm, 50% efficiency (notes worked example); truck loading often governs deep cuts | SY/hr = drum width(ft) x fpm x 60 x 0.50 / 9 = 24/12 x 30 x 60 x 0.5 / 9 = 200 | CAT-PM310;WSDOT | C | Efficiency 0.50 from example, not Settings E
PV-MILL-PM310 | PV-MILL-MID | 39.4 in drum (Cat PM310) | Cold plane, compact/mid (3-5 ft drum) | 39.4 | in drum width |  | 328.3333 |  | SY/hr | Calculated (geometric) | Cutting speed 30 fpm, 50% efficiency (notes worked example); truck loading often governs deep cuts | SY/hr = drum width(ft) x fpm x 60 x 0.50 / 9 = 39.4/12 x 30 x 60 x 0.5 / 9 = 328 | CAT-PM310;WSDOT | C | Efficiency 0.50 from example, not Settings E
PV-MILL-PM312 | PV-MILL-MID | 4 ft 1 in drum (Cat PM312) | Cold plane, compact/mid (3-5 ft drum) | 49 | in drum width |  | 408.3333 |  | SY/hr | Calculated (geometric) | Cutting speed 30 fpm, 50% efficiency (notes worked example); truck loading often governs deep cuts | SY/hr = drum width(ft) x fpm x 60 x 0.50 / 9 = 49/12 x 30 x 60 x 0.5 / 9 = 408 | CAT-PM310;WSDOT | C | Efficiency 0.50 from example, not Settings E
PV-MILL-PM622 | PV-MILL-LARGE | ~6.6 ft drum (Cat PM622) | Cold plane, half/full-lane machine |  |  | 2450 | 11500 | 25000 | SY/day | DOT field daily median (crew) | Half/full-lane machine, 8-hr day | Typ = median of WSDOT normal 9,000, WisDOT thin 17,000 / thick 14,000, TxDOT med 7,430; low TxDOT 2,450; high WisDOT 25,000. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT;WISDOT;TXDOT | A
PV-MILL-PM822 | PV-MILL-LARGE | Full-lane (Cat PM822) | Cold plane, half/full-lane machine |  |  | 2450 | 11500 | 25000 | SY/day | DOT field daily median (crew) | Half/full-lane machine, 8-hr day | Typ = median of WSDOT normal 9,000, WisDOT thin 17,000 / thick 14,000, TxDOT med 7,430; low TxDOT 2,450; high WisDOT 25,000. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT;WISDOT;TXDOT | A
PV-DIST-550 | PV-PRIME | 550 gal | Prime coat (distributor) |  |  | 1000 | 4500 | 8000 | GAL/day | DOT field daily (crew) | Prime coat | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
PV-DIST-1000 | PV-PRIME | 1,000 gal | Prime coat (distributor) |  |  | 1000 | 4500 | 8000 | GAL/day | DOT field daily (crew) | Prime coat | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
PV-DIST-2000 | PV-PRIME | 2,000 gal | Prime coat (distributor) |  |  | 1000 | 4500 | 8000 | GAL/day | DOT field daily (crew) | Prime coat | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
PV-DIST-4000 | PV-PRIME | 4,000 gal | Prime coat (distributor) |  |  | 1000 | 4500 | 8000 | GAL/day | DOT field daily (crew) | Prime coat | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
PV-CHIP-8423 | PV-CHIPSEAL | 2.8 CY | Seal coat / chip seal (spreader) |  |  | 2000 | 21750 | 140000 | SY/day | DOT field daily (crew) | Seal coat / BST | Typ = median of TxDOT med 36,000 and NCDOT major mid 7,500; low NCDOT small urban 2,000; high TxDOT 140,000. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT;NCDOT | A
PV-CHIP-8424 | PV-CHIPSEAL | 3.5-3.8 CY | Seal coat / chip seal (spreader) |  |  | 2000 | 21750 | 140000 | SY/day | DOT field daily (crew) | Seal coat / BST | Typ = median of TxDOT med 36,000 and NCDOT major mid 7,500; low NCDOT small urban 2,000; high TxDOT 140,000. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT;NCDOT | A
PV-CHIP-8425 | PV-CHIPSEAL | Mounted 8 ft | Seal coat / chip seal (spreader) |  |  | 2000 | 21750 | 140000 | SY/day | DOT field daily (crew) | Seal coat / BST | Typ = median of TxDOT med 36,000 and NCDOT major mid 7,500; low NCDOT small urban 2,000; high TxDOT 140,000. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT;NCDOT | A
PV-CHIP-8584 | PV-CHIPSEAL | 13 ft | Seal coat / chip seal (spreader) |  |  | 2000 | 21750 | 140000 | SY/day | DOT field daily (crew) | Seal coat / BST | Typ = median of TxDOT med 36,000 and NCDOT major mid 7,500; low NCDOT small urban 2,000; high TxDOT 140,000. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT;NCDOT | A
PV-BROOM-SP-8 | PV-SWEEP | 8 ft 3-wheel open | Sweep pavement | [5 empty] | lane-mi/hr | n/a |  | No sweeper production source |  | D | Needs production rate
PV-BROOM-SP-8CAB | PV-SWEEP | 8 ft 4-wheel cab | Sweep pavement | [5 empty] | lane-mi/hr | n/a |  | No sweeper production source |  | D | Needs production rate
PV-BROOM-SSL | PV-SWEEP | SSL pickup sweeper | Sweep pavement | [5 empty] | lane-mi/hr | n/a |  | No sweeper production source |  | D | Needs production rate
PV-SWEEPER-TRUCK | PV-SWEEP | 120 in, 4.5 CY hopper | Sweep pavement | [5 empty] | lane-mi/hr | n/a |  | No sweeper production source |  | D | Needs production rate
PV-BROOM-SP-8153 | PV-SWEEP | Self-propelled broom 96 in | Sweep pavement | [5 empty] | lane-mi/hr | n/a |  | No sweeper production source |  | D | Needs production rate
PV-BROOM-SP-8155 | PV-SWEEP | Self-propelled broom 84 in | Sweep pavement | [5 empty] | lane-mi/hr | n/a |  | No sweeper production source |  | D | Needs production rate
PV-BROOM-PULL | PV-SWEEP | Pull broom (towed) | Sweep pavement | [5 empty] | lane-mi/hr | n/a |  | No sweeper production source |  | D | Needs production rate
PV-SWEEPER-8158 | PV-SWEEP | Street sweeper (FEMA 8158) | Sweep pavement | [5 empty] | lane-mi/hr | n/a |  | No sweeper production source |  | D | Needs production rate
PV-STRIPE-8440 | PV-STRIPE-SMALL | Walk-behind striper, single gun | Striping, walk/ride-behind or push cart | [5 empty] | LF/day | n/a |  | No walk-behind paint striping rate (only thermoplastic push cart 400 LF/day) | WSDOT | D | Needs production rate
PV-STRIPE-8441 | PV-STRIPE-SMALL | Ride-on striper | Striping, walk/ride-behind or push cart | [5 empty] | LF/day | n/a |  | No walk-behind paint striping rate (only thermoplastic push cart 400 LF/day) | WSDOT | D | Needs production rate
PV-STRIPE-8442 | PV-STRIPE-SMALL | Ride-on striper, 2x25 gal | Striping, walk/ride-behind or push cart | [5 empty] | LF/day | n/a |  | No walk-behind paint striping rate (only thermoplastic push cart 400 LF/day) | WSDOT | D | Needs production rate
PV-STRIPE-TRUCK | PV-STRIPE-TRUCK | Truck-mounted RoadLazer | Paint striping, truck |  |  | 12500 | 50000 | 100000 | LF/day | DOT field daily (crew) | Paint line, truck | TxDOT Low/Med/High; WSDOT 14,000-100,000 West cross-check. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT;WSDOT | A
PV-STABILIZER-WR2400 | PV-STABILIZE | Wirtgen WR 2400 class | Subgrade lime/cement treatment (stabilizer) |  |  | 688 | 2495 | 4108 | SY/day | DOT field daily (crew) | Lime treatment (cement: 1,585/2,529/3,325) | TxDOT Low/Med/High (lime). Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
CN-MIXER-5CF | CN-MIX-SMALL | 5 cu ft | Mix mortar/concrete on site | [5 empty] | cu ft/hr | n/a |  | No source |  | D | Needs production rate
CN-MIXER-12CF | CN-MIX-SMALL | 12 cu ft | Mix mortar/concrete on site | [5 empty] | cu ft/hr | n/a |  | No source |  | D | Needs production rate
CN-MIXER-16CF | CN-MIX-SMALL | 16 cu ft | Mix mortar/concrete on site | [5 empty] | cu ft/hr | n/a |  | No source |  | D | Needs production rate
CN-PUMP-BOOM-38M | CN-PUMP-BOOM | Boom pump 38 m | Place concrete by boom pump (direct from boom) |  |  | 60 | 80 | 100 | CY/hr | Practitioner field range | Direct from boom; delivery & finishing govern | Range 60-100 CY/hr; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | FCP-CONC;ACI-S21 | B
CN-PUMP-BOOM-46M | CN-PUMP-BOOM | Boom pump 46 m | Place concrete by boom pump (direct from boom) |  |  | 60 | 80 | 100 | CY/hr | Practitioner field range | Direct from boom; delivery & finishing govern | Range 60-100 CY/hr; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | FCP-CONC;ACI-S21 | B
CN-PUMP-LINE | CN-PUMP-LINE | Line pump (trailer) | Place concrete by line pump / downline |  |  | 40 | 50 | 60 | CY/hr | Practitioner field range | Line pump with downline | Range 40-60; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | FCP-CONC | B
CN-PUMP-BOOM-63M | CN-PUMP-BOOM | Boom pump 47-63 m+ | Place concrete by boom pump (direct from boom) |  |  | 60 | 80 | 100 | CY/hr | Practitioner field range | Direct from boom; delivery & finishing govern | Range 60-100 CY/hr; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | FCP-CONC;ACI-S21 | B
CN-TELEBELT | CN-PLACE-BELT | 110 ft Telebelt | Place concrete by conveyor (Telebelt) | [5 empty] | CY/hr | n/a |  | No conveyor placement source |  | D | Needs production rate
CN-VIB-FLEX | CN-PLACE-SLAB | 2.5 in head, 16 ft shaft | Wet screed (hand/roller/vibratory screed) slab placement |  |  | 30 | 45 | 60 | CY/hr | Practitioner field range | Wet screed (hand/roller/vibratory screed) | Range 30-60; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | FCP-CONC | B
CN-VIB-MIH | CN-PLACE-SLAB | Motor-in-head vibrator | Wet screed (hand/roller/vibratory screed) slab placement |  |  | 30 | 45 | 60 | CY/hr | Practitioner field range | Wet screed (hand/roller/vibratory screed) | Range 30-60; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | FCP-CONC | B
CN-TROWEL-WB | CN-FINISH-WB | 36-46 in walk-behind | Power trowel finish, walk-behind 36 in |  |  | 700 | 1100 | 1500 | SF/day | Trade press (2002) | 36 in walk-behind | Range 700-1,500; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | RER-TROWEL | B
CN-TROWEL-RIDE-72 | CN-FINISH-RIDE | Ride-on 72 in | Power trowel finish, ride-on |  |  | 2100 | 4400 | 7500 | SF/day | Derived from trade press | Ride-on = 3-5x walk-behind | Low 3 x 700; typ 4 x 1,100; high 5 x 1,500. Crew/spread rate: equipment hours = crew days x hours/day. | RER-TROWEL | C
CN-TROWEL-RIDE-91 | CN-FINISH-RIDE | Ride-on 91 in | Power trowel finish, ride-on |  |  | 2100 | 4400 | 7500 | SF/day | Derived from trade press | Ride-on = 3-5x walk-behind | Low 3 x 700; typ 4 x 1,100; high 5 x 1,500. Crew/spread rate: equipment hours = crew days x hours/day. | RER-TROWEL | C
CN-TROWEL-RIDE-98 | CN-FINISH-RIDE | Ride-on 97.5 in | Power trowel finish, ride-on |  |  | 2100 | 4400 | 7500 | SF/day | Derived from trade press | Ride-on = 3-5x walk-behind | Low 3 x 700; typ 4 x 1,100; high 5 x 1,500. Crew/spread rate: equipment hours = crew days x hours/day. | RER-TROWEL | C
CN-SCREED-ROLLER | CN-PLACE-SLAB | Roller screed | Wet screed (hand/roller/vibratory screed) slab placement |  |  | 30 | 45 | 60 | CY/hr | Practitioner field range | Wet screed (hand/roller/vibratory screed) | Range 30-60; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | FCP-CONC | B
CN-SCREED-HAND | CN-PLACE-SLAB | Hand-held power screed | Wet screed (hand/roller/vibratory screed) slab placement |  |  | 30 | 45 | 60 | CY/hr | Practitioner field range | Wet screed (hand/roller/vibratory screed) | Range 30-60; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | FCP-CONC | B
CN-SCREED-VIB-10 | CN-PLACE-SLAB | 10 ft vibratory screed | Wet screed (hand/roller/vibratory screed) slab placement |  |  | 30 | 45 | 60 | CY/hr | Practitioner field range | Wet screed (hand/roller/vibratory screed) | Range 30-60; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | FCP-CONC | B
CN-SCREED-TRUSS-20 | CN-PLACE-SLAB | 20 ft base truss screed | Wet screed (hand/roller/vibratory screed) slab placement |  |  | 30 | 45 | 60 | CY/hr | Practitioner field range | Wet screed (hand/roller/vibratory screed) | Range 30-60; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | FCP-CONC | B
CN-LASER-SCREED | CN-PLACE-LASER | Laser screed | Truck dump + laser screed placement |  |  | 80 | 120 | 160 | CY/hr | Practitioner field range | Truck dump + laser screed | Range 80-160; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | FCP-CONC | B
CN-SAW-WB-14 | CN-SAWCUT | 14-20 in blade | Saw cut concrete/asphalt | [5 empty] | LF/hr | n/a |  | No saw LF/hr by depth source |  | D | Needs production rate
CN-SAW-26 | CN-SAWCUT | 26 in blade (35/48 hp) | Saw cut concrete/asphalt | [5 empty] | LF/hr | n/a |  | No saw LF/hr by depth source |  | D | Needs production rate
CN-SAW-36 | CN-SAWCUT | 36 in blade (66/70 hp) | Saw cut concrete/asphalt | [5 empty] | LF/hr | n/a |  | No saw LF/hr by depth source |  | D | Needs production rate
CN-SAW-DEEP-60 | CN-SAWCUT | 60 in blade | Saw cut concrete/asphalt | [5 empty] | LF/hr | n/a |  | No saw LF/hr by depth source |  | D | Needs production rate
CN-SAW-EARLY | CN-SAWCUT | Early-entry 13.5 in | Saw cut concrete/asphalt | [5 empty] | LF/hr | n/a |  | No saw LF/hr by depth source |  | D | Needs production rate
CN-BUGGY | CN-PLACE-BUGGY | Power buggy | Place concrete by power buggy | [5 empty] | CY/hr | n/a |  | No buggy CY/hr source |  | D | Needs production rate
CN-BUGGY-TRACK-16 | CN-PLACE-BUGGY | Tracked mud buggy 16 cf | Place concrete by power buggy | [5 empty] | CY/hr | n/a |  | No buggy CY/hr source |  | D | Needs production rate
CN-SLIPFORM-PAVER | CN-SLIPFORM-PAVE | Slipform paver (by width) | Slipform concrete paving |  |  | 850 | 2463 | 5000 | SY/day | DOT field daily median (crew) | Mainline concrete pavement | Typ = median of WisDOT 2,300, TxDOT 2,463, NCDOT mid 4,000; low WisDOT 850; high NCDOT 5,000. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;NCDOT;WSDOT | A
CN-CURB-MACHINE | CN-CURB | Curb & gutter slipform | Slipform curb & gutter |  |  | 288 | 775 | 1500 | LF/day | DOT field daily median (crew) | Slipform curb & gutter | Typ = median of WisDOT 800, TxDOT 554, WSDOT West 1,500, NCDOT mid 750; low TxDOT 288; high WisDOT/WSDOT 1,500. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;WSDOT;NCDOT | A
CR-RT-50T-BARE | LF-GIRDER-PRECAST | 50 t RT (bare) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-RT-50T-BARE | LF-STEEL-BEAM | 50 t RT (bare) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-RT-65T-BARE | LF-GIRDER-PRECAST | 65 t RT (bare) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-RT-65T-BARE | LF-STEEL-BEAM | 65 t RT (bare) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-RT-85T-BARE | LF-GIRDER-PRECAST | 85 t RT (bare) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-RT-85T-BARE | LF-STEEL-BEAM | 85 t RT (bare) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-RT-100T-BARE | LF-GIRDER-PRECAST | 100 t RT (bare) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-RT-100T-BARE | LF-STEEL-BEAM | 100 t RT (bare) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-40T-OP | LF-GIRDER-PRECAST | 40 t hydraulic (operated) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-40T-OP | LF-STEEL-BEAM | 40 t hydraulic (operated) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-50T-OP | LF-GIRDER-PRECAST | 50 t hydraulic (operated) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-50T-OP | LF-STEEL-BEAM | 50 t hydraulic (operated) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-60T-OP | LF-GIRDER-PRECAST | 60 t hydraulic (operated) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-60T-OP | LF-STEEL-BEAM | 60 t hydraulic (operated) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-75T-OP | LF-GIRDER-PRECAST | 75 t hydraulic (operated) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-75T-OP | LF-STEEL-BEAM | 75 t hydraulic (operated) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-80T-OP | LF-GIRDER-PRECAST | 80 t hydraulic (operated) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-80T-OP | LF-STEEL-BEAM | 80 t hydraulic (operated) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-100T-OP | LF-GIRDER-PRECAST | 100 t hydraulic (operated) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-100T-OP | LF-STEEL-BEAM | 100 t hydraulic (operated) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-110T-OP | LF-GIRDER-PRECAST | 110 t hydraulic (operated) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-110T-OP | LF-STEEL-BEAM | 110 t hydraulic (operated) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-120T-OP | LF-GIRDER-PRECAST | 120 t hydraulic (operated) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-120T-OP | LF-STEEL-BEAM | 120 t hydraulic (operated) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-165T-OP | LF-GIRDER-PRECAST | 165 t hydraulic (operated) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-165T-OP | LF-STEEL-BEAM | 165 t hydraulic (operated) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-210T-OP | LF-GIRDER-PRECAST | 210 t hydraulic (operated) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-210T-OP | LF-STEEL-BEAM | 210 t hydraulic (operated) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-240T-OP | LF-GIRDER-PRECAST | 240 t hydraulic (operated) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-240T-OP | LF-STEEL-BEAM | 240 t hydraulic (operated) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-275T-OP | LF-GIRDER-PRECAST | 275 t hydraulic (operated) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-HYD-275T-OP | LF-STEEL-BEAM | 275 t hydraulic (operated) | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-AT-35T | LF-GIRDER-PRECAST | 35 t all-terrain | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-AT-35T | LF-STEEL-BEAM | 35 t all-terrain | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-AT-60T | LF-GIRDER-PRECAST | 60 t all-terrain | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-AT-60T | LF-STEEL-BEAM | 60 t all-terrain | Erect structural steel bridge beams |  |  | 6 | 9 | 12 | EA/day | DOT field daily (crew) | Structural steel bridge beams | WisDOT 6-12; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-AT-HEAVY | LF-GIRDER-PRECAST | Heavy-lift AT (size not stated) | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-CRAWL-125T | LF-GIRDER-PRECAST | 125 t lattice crawler | Erect precast bridge girders |  |  | 5 | 6 | 8 | EA/day | DOT field daily median (crew) | Precast bridge girders | WisDOT 5-8, median 6. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT | B
CR-CRAWL-125T | FD-PILE-DRIVE | 125 t lattice crawler | Drive piles (crane + hammer + leads spread) |  |  | 100 | 215 | 400 | LF/day | DOT field daily median (crew) | Driven piles, all types | Typ = median of WisDOT 280 and TxDOT 150; low TxDOT 100; high WisDOT 400. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT | A
CR-TOWER | LF-TOWER-LIFTS | Tower crane (class not specified) | Tower crane hook (lifts per hour) |  |  |  | 11 | 12 | lifts/hr | Measured study (derived) | Frame erection; precast much lower | ~4 min median lift / 72% effective -> 10-12 lifts/hr theoretical. Crew/spread rate: equipment hours = crew days x hours/day. | VTT-CRANE | C
TR-WB-6x36 | UT-TRENCH-SMALL | ~6 in x 36 in walk-behind | Trench with walk-behind / SSL trencher | [5 empty] | LF/hr | n/a |  | No trencher LF/hr source | CE-TRENCH | D | Needs production rate
TR-SSL-4FT | UT-TRENCH-SMALL | 4 ft SSL trencher | Trench with walk-behind / SSL trencher | [5 empty] | LF/hr | n/a |  | No trencher LF/hr source | CE-TRENCH | D | Needs production rate
TR-RIDE-V120 | UT-TRENCH-CHAIN | 60 in depth (~116 hp) | Trench with ride-on chain trencher | [5 empty] | LF/hr | n/a |  | No trencher LF/hr source | CE-TRENCH | D | Needs production rate
TR-FEMA-8650 | UT-TRENCH-CHAIN | Seaman-Parsons trencher (FEMA 8650) | Trench with ride-on chain trencher | [5 empty] | LF/hr | n/a |  | No trencher LF/hr source | CE-TRENCH | D | Needs production rate
TR-FEMA-8651 | UT-TRENCH-CHAIN | Seaman-Parsons trencher (FEMA 8651) | Trench with ride-on chain trencher | [5 empty] | LF/hr | n/a |  | No trencher LF/hr source | CE-TRENCH | D | Needs production rate
TR-FEMA-8652 | UT-TRENCH-CHAIN | Trencher/ditcher (FEMA 8652) | Trench with ride-on chain trencher | [5 empty] | LF/hr | n/a |  | No trencher LF/hr source | CE-TRENCH | D | Needs production rate
TR-FEMA-8653 | UT-TRENCH-CHAIN | Trencher/ditcher (FEMA 8653) | Trench with ride-on chain trencher | [5 empty] | LF/hr | n/a |  | No trencher LF/hr source | CE-TRENCH | D | Needs production rate
TR-PLOW-8661 | UT-PLOW | DP-60 (18 in, 82 hp) | Vibratory cable plow | [5 empty] | LF/hr | n/a |  | No cable plow source |  | D | Needs production rate
TR-PLOW-8662 | UT-PLOW | DP-100 (42 in, 110 hp) | Vibratory cable plow | [5 empty] | LF/hr | n/a |  | No cable plow source |  | D | Needs production rate
TR-PLOW-8660 | UT-PLOW | Case Maxi-Sneaker (24 in, 210 hp) | Vibratory cable plow | [5 empty] | LF/hr | n/a |  | No cable plow source |  | D | Needs production rate
HDD-COMPACT | UT-HDD | 7,000 lb pullback (~25 hp) | HDD ream & pullback (12 in reamer, sand/dirt, 40 gpm) |  |  | 83 | 125 | 167 | LF/hr | Trade example (derived) | 500 ft bore, 12 in reamer, sand/dirt, 40 gpm; ~7 of 10 hr productive | 500 ft / 6 hr = 83; 500 / 3 = 167; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | DRILLER-BP | C
HDD-SMALL | UT-HDD | 24,000 lb class (Vermeer D24x40) | HDD ream & pullback (12 in reamer, sand/dirt, 40 gpm) |  |  | 83 | 125 | 167 | LF/hr | Trade example (derived) | 500 ft bore, 12 in reamer, sand/dirt, 40 gpm; ~7 of 10 hr productive | 500 ft / 6 hr = 83; 500 / 3 = 167; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | DRILLER-BP | C
HDD-MED | UT-HDD | 40,000-100,000 lb pullback | HDD ream & pullback (12 in reamer, sand/dirt, 40 gpm) |  |  | 83 | 125 | 167 | LF/hr | Trade example (derived) | 500 ft bore, 12 in reamer, sand/dirt, 40 gpm; ~7 of 10 hr productive | 500 ft / 6 hr = 83; 500 / 3 = 167; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | DRILLER-BP | C
HDD-LARGE | UT-HDD | 100,000 lb pullback (Vermeer D-140B 250x100 class) | HDD ream & pullback (12 in reamer, sand/dirt, 40 gpm) |  |  | 83 | 125 | 167 | LF/hr | Trade example (derived) | 500 ft bore, 12 in reamer, sand/dirt, 40 gpm; ~7 of 10 hr productive | 500 ft / 6 hr = 83; 500 / 3 = 167; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | DRILLER-BP | C
AUGER-BORE | UT-JACKBORE | To 30 ft flight | Jack and bore (auger boring) |  |  | 20 | 40 | 70 | LF/day | DOT field daily (crew) | Jack and bore | TxDOT Low/Med/High. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT | B
PIPEBURST-50T | UT-BURST-50 | 50-ton rig (4-8 in pipe) | Pipe bursting, 50-ton rig (4-8 in) |  |  | 300 | 350 | 400 | LF/day | Contractor-reported | 4-8 in pipe, 4x12 ft pit | Range 300-400; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | CLEANER-PB | B
PIPEBURST-100T | UT-BURST-100 | 100-ton rig (8-12 in, to 16 in) | Pipe bursting, 100-ton rig (8-12 in, to 16 in) |  |  | 500 | 625 | 750 | LF/day | Contractor-reported | 8-12 in typical, up to 16 in | Range 500-750; typ = midpoint. Crew/spread rate: equipment hours = crew days x hours/day. | CLEANER-PB | B
VAC-TRAILER | UT-VACEX | Vac-ex trailer | Vacuum (hydro) excavation, pure dig time |  |  | 1.7 | 4.2 | 6.6 | CY/hr | Measured test (GTI), pure dig time | Hydro (water) excavation, clay to silty clay; excludes setup/dumping | 0.78-2.96 ft3/min x 60/27 = 1.7-6.6 CY/hr; typ from mid 1.87 ft3/min. Crew/spread rate: equipment hours = crew days x hours/day. | GTI-VAC | C
VAC-HYDROVAC | UT-VACEX | 500 gal debris tank | Vacuum (hydro) excavation, pure dig time |  |  | 1.7 | 4.2 | 6.6 | CY/hr | Measured test (GTI), pure dig time | Hydro (water) excavation, clay to silty clay; excludes setup/dumping | 0.78-2.96 ft3/min x 60/27 = 1.7-6.6 CY/hr; typ from mid 1.87 ft3/min. Crew/spread rate: equipment hours = crew days x hours/day. | GTI-VAC | C
VAC-COMBO-VACTOR | UT-VACEX | Vactor 2100 Plus (12-13 CY, 310 hp) | Vacuum (hydro) excavation, pure dig time |  |  | 1.7 | 4.2 | 6.6 | CY/hr | Measured test (GTI), pure dig time | Hydro (water) excavation, clay to silty clay; excludes setup/dumping | 0.78-2.96 ft3/min x 60/27 = 1.7-6.6 CY/hr; typ from mid 1.87 ft3/min. Crew/spread rate: equipment hours = crew days x hours/day. | GTI-VAC | C
FD-VIBRO-EXC | FD-SHEET | Movax SP-60 sheet pile driver (28-32 t head, 178 hp) | Drive/extract sheet piling |  |  | 220 | 350 | 690 | SF/day | DOT field daily median (crew) | Temporary sheet piling | Typ = median of WisDOT 340, TxDOT 350, NCDOT 640; low 220; high 690. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;NCDOT | A
FD-VIBRO-NF-S | FD-SHEET | Normal-frequency vibro, small (ICE 55NF class) | Drive/extract sheet piling |  |  | 220 | 350 | 690 | SF/day | DOT field daily median (crew) | Temporary sheet piling | Typ = median of WisDOT 340, TxDOT 350, NCDOT 640; low 220; high 690. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;NCDOT | A
FD-VIBRO-NF-S | FD-PILE-DRIVE | Normal-frequency vibro, small (ICE 55NF class) | Drive piles (crane + hammer + leads spread) |  |  | 100 | 215 | 400 | LF/day | DOT field daily median (crew) | Driven piles, all types | Typ = median of WisDOT 280 and TxDOT 150; low TxDOT 100; high WisDOT 400. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT | A
FD-VIBRO-NF-M | FD-SHEET | Normal-frequency vibro, medium (ICE 170NF / PVE 150M class) | Drive/extract sheet piling |  |  | 220 | 350 | 690 | SF/day | DOT field daily median (crew) | Temporary sheet piling | Typ = median of WisDOT 340, TxDOT 350, NCDOT 640; low 220; high 690. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;NCDOT | A
FD-VIBRO-NF-M | FD-PILE-DRIVE | Normal-frequency vibro, medium (ICE 170NF / PVE 150M class) | Drive piles (crane + hammer + leads spread) |  |  | 100 | 215 | 400 | LF/day | DOT field daily median (crew) | Driven piles, all types | Typ = median of WisDOT 280 and TxDOT 150; low TxDOT 100; high WisDOT 400. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT | A
FD-VIBRO-NF-L | FD-SHEET | Normal-frequency vibro, large (PVE 500MU class) | Drive/extract sheet piling |  |  | 220 | 350 | 690 | SF/day | DOT field daily median (crew) | Temporary sheet piling | Typ = median of WisDOT 340, TxDOT 350, NCDOT 640; low 220; high 690. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;NCDOT | A
FD-VIBRO-NF-L | FD-PILE-DRIVE | Normal-frequency vibro, large (PVE 500MU class) | Drive piles (crane + hammer + leads spread) |  |  | 100 | 215 | 400 | LF/day | DOT field daily median (crew) | Driven piles, all types | Typ = median of WisDOT 280 and TxDOT 150; low TxDOT 100; high WisDOT 400. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT | A
FD-HAMMER-DIESEL | FD-PILE-DRIVE | Diesel impact hammer | Drive piles (crane + hammer + leads spread) |  |  | 100 | 215 | 400 | LF/day | DOT field daily median (crew) | Driven piles, all types | Typ = median of WisDOT 280 and TxDOT 150; low TxDOT 100; high WisDOT 400. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT | A
FD-HAMMER-HYD | FD-PILE-DRIVE | Hydraulic impact hammer | Drive piles (crane + hammer + leads spread) |  |  | 100 | 215 | 400 | LF/day | DOT field daily median (crew) | Driven piles, all types | Typ = median of WisDOT 280 and TxDOT 150; low TxDOT 100; high WisDOT 400. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT | A
FD-HAMMER-AIR | FD-PILE-DRIVE | Air/steam (drop) hammer (ram 500-50,000 lb) | Drive piles (crane + hammer + leads spread) |  |  | 100 | 215 | 400 | LF/day | DOT field daily median (crew) | Driven piles, all types | Typ = median of WisDOT 280 and TxDOT 150; low TxDOT 100; high WisDOT 400. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT | A
FD-LEADS-FIX-24 | FD-PILE-DRIVE | Fixed leads 0-24 ft | Drive piles (crane + hammer + leads spread) |  |  | 100 | 215 | 400 | LF/day | DOT field daily median (crew) | Driven piles, all types | Typ = median of WisDOT 280 and TxDOT 150; low TxDOT 100; high WisDOT 400. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT | A
FD-LEADS-FIX-49 | FD-PILE-DRIVE | Fixed leads 25-49 ft | Drive piles (crane + hammer + leads spread) |  |  | 100 | 215 | 400 | LF/day | DOT field daily median (crew) | Driven piles, all types | Typ = median of WisDOT 280 and TxDOT 150; low TxDOT 100; high WisDOT 400. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT | A
FD-LEADS-FIX-74 | FD-PILE-DRIVE | Fixed leads 50-74 ft | Drive piles (crane + hammer + leads spread) |  |  | 100 | 215 | 400 | LF/day | DOT field daily median (crew) | Driven piles, all types | Typ = median of WisDOT 280 and TxDOT 150; low TxDOT 100; high WisDOT 400. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT | A
FD-LEADS-SW-20 | FD-PILE-DRIVE | Swinging leads 0-20 ft | Drive piles (crane + hammer + leads spread) |  |  | 100 | 215 | 400 | LF/day | DOT field daily median (crew) | Driven piles, all types | Typ = median of WisDOT 280 and TxDOT 150; low TxDOT 100; high WisDOT 400. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT | A
FD-LEADS-SW-30 | FD-PILE-DRIVE | Swinging leads 21-30 ft | Drive piles (crane + hammer + leads spread) |  |  | 100 | 215 | 400 | LF/day | DOT field daily median (crew) | Driven piles, all types | Typ = median of WisDOT 280 and TxDOT 150; low TxDOT 100; high WisDOT 400. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT | A
FD-LEADS-SW-50 | FD-PILE-DRIVE | Swinging leads 31-50 ft | Drive piles (crane + hammer + leads spread) |  |  | 100 | 215 | 400 | LF/day | DOT field daily median (crew) | Driven piles, all types | Typ = median of WisDOT 280 and TxDOT 150; low TxDOT 100; high WisDOT 400. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT | A
FD-DRILL-KELLY | FD-SHAFT-SOIL | Drilled shaft rig (class not sourced) | Drill shafts in soil |  |  | 18 | 64.5 | 203 | LF/day | DOT field daily (crew) | Drilled shafts in soil (diameter-dependent) | Typ = median of TxDOT 104 and NCDOT <=60 in 25; low NCDOT >60 in 18; high TxDOT 203. Crew/spread rate: equipment hours = crew days x hours/day. | TXDOT;NCDOT | A
FD-DRILL-KELLY | FD-SHAFT-ROCK | Drilled shaft rig (class not sourced) | Drill shafts in rock |  |  | 3 | 5 | 5 | LF/day | DOT agency judgment | Drilled shafts not in soil | NCDOT <=60 in 5; >60 in 3. Crew/spread rate: equipment hours = crew days x hours/day. | NCDOT | B
DM-UHD-330 | DM-BLDG | 330 UHD (66.8 ft pin) | Building demolition (high-reach / excavator) | [5 empty] | SF/day | n/a |  | No building demolition SF/day source |  | D | Needs production rate
DM-UHD-340 | DM-BLDG | 340 UHD (72.2 ft pin) | Building demolition (high-reach / excavator) | [5 empty] | SF/day | n/a |  | No building demolition SF/day source |  | D | Needs production rate
DM-UHD-352 | DM-BLDG | 352 UHD (90.8 ft pin) | Building demolition (high-reach / excavator) | [5 empty] | SF/day | n/a |  | No building demolition SF/day source |  | D | Needs production rate
DM-SB-340 | DM-BLDG | 340 Straight Boom (39.4 ft) | Building demolition (high-reach / excavator) | [5 empty] | SF/day | n/a |  | No building demolition SF/day source |  | D | Needs production rate
DM-SB-352 | DM-BLDG | 352 Straight Boom (42.2 ft) | Building demolition (high-reach / excavator) | [5 empty] | SF/day | n/a |  | No building demolition SF/day source |  | D | Needs production rate
AT-BRK-MINI | DM-PAVE-CONC | Hydraulic breaker, mini-ex/SSL (~500-1,000 ft-lb) | Remove concrete pavement |  |  | 410 | 1000 | 4000 | SY/day | DOT field daily median (crew) | Remove concrete pavement | Typ = median of WisDOT 1,000, TxDOT 1,974, WSDOT 600; low 410; high 4,000. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;WSDOT | A
AT-BRK-BH | DM-PAVE-CONC | Hydraulic breaker, backhoe | Remove concrete pavement |  |  | 410 | 1000 | 4000 | SY/day | DOT field daily median (crew) | Remove concrete pavement | Typ = median of WisDOT 1,000, TxDOT 1,974, WSDOT 600; low 410; high 4,000. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;WSDOT | A
AT-BRK-13T | DM-PAVE-CONC | Hydraulic breaker for 13-17 t excavator (MB-1000) | Remove concrete pavement |  |  | 410 | 1000 | 4000 | SY/day | DOT field daily median (crew) | Remove concrete pavement | Typ = median of WisDOT 1,000, TxDOT 1,974, WSDOT 600; low 410; high 4,000. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;WSDOT | A
AT-BRK-20T | DM-PAVE-CONC | Hydraulic breaker for 20-30 t excavator | Remove concrete pavement |  |  | 410 | 1000 | 4000 | SY/day | DOT field daily median (crew) | Remove concrete pavement | Typ = median of WisDOT 1,000, TxDOT 1,974, WSDOT 600; low 410; high 4,000. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;WSDOT | A
AT-BRK-36T | DM-PAVE-CONC | Hydraulic breaker for ~36 t excavator (HB-3100) | Remove concrete pavement |  |  | 410 | 1000 | 4000 | SY/day | DOT field daily median (crew) | Remove concrete pavement | Typ = median of WisDOT 1,000, TxDOT 1,974, WSDOT 600; low 410; high 4,000. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;WSDOT | A
AT-BRK-10KLB | DM-PAVE-CONC | Hydraulic breaker ~10,000 lb hammer | Remove concrete pavement |  |  | 410 | 1000 | 4000 | SY/day | DOT field daily median (crew) | Remove concrete pavement | Typ = median of WisDOT 1,000, TxDOT 1,974, WSDOT 600; low 410; high 4,000. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;WSDOT | A
AT-BRK-15KLB | DM-PAVE-CONC | Hydraulic breaker ~15,000 lb hammer | Remove concrete pavement |  |  | 410 | 1000 | 4000 | SY/day | DOT field daily median (crew) | Remove concrete pavement | Typ = median of WisDOT 1,000, TxDOT 1,974, WSDOT 600; low 410; high 4,000. Crew/spread rate: equipment hours = crew days x hours/day. | WISDOT;TXDOT;WSDOT | A
LC-CHIP-8201 | EW-CLR-CHIP | Brush chipper 12 in (Vermeer BC1000XL) | Chip brush | [5 empty] | ton/hr | n/a |  | No chipper production source |  | D | Needs production rate
LC-CHIP-8202 | EW-CLR-CHIP | Brush chipper 15 in (Vermeer BC1500) | Chip brush | [5 empty] | ton/hr | n/a |  | No chipper production source |  | D | Needs production rate
LC-CHIP-8203 | EW-CLR-CHIP | Brush chipper 19 in (Vermeer BC1800XL) | Chip brush | [5 empty] | ton/hr | n/a |  | No chipper production source |  | D | Needs production rate
LC-CHIP-8200 | EW-CLR-CHIP | Vermeer BC900XL (~9 in) | Chip brush | [5 empty] | ton/hr | n/a |  | No chipper production source |  | D | Needs production rate
TRK-TRAC-8789 | EW-HAUL-TRK-10 | Truck tractor 4x2 26,001-33,000 lb (Freightliner M2 106+) | Haul with on-road dump truck, 1 mi one-way |  | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity not in notes/specs. Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6 | D | Needs haul speeds (Settings B22-B25; not sourced); Needs truck capacity
TRK-TRAC-8790 | EW-HAUL-TRK-10 | Truck tractor 6x4 33,001-52,000 lb (Freightliner M2 106) | Haul with on-road dump truck, 1 mi one-way |  | LCY per load |  |  |  | BCY/hr per truck | Calculated: job-adjusted (E from Settings) | One-way 1.0 mi; load time = capacity / 2.7 LCY per pass x 0.5 min (Settings B36-B37, worked example); dump/maneuver 1.5 min; loam L->B 0.80; speeds from Settings (truck) | Cycle = Cap/2.7 x 0.5 + 1.5 + 1.0x60/v_loaded + 1.0x60/v_empty; BCY/hr = Cap x 60 x E / cycle x 0.80. Capacity not in notes/specs. Trucks needed N = cycle / load time. | OEP;KSU-T5;KSU-T6 | D | Needs haul speeds (Settings B22-B25; not sourced); Needs truck capacity
ERO-HS-8630 | SITE-HYDROSEED | Hydroseeder Reinco HG-5 | Hydroseed / seed, fertilize & mulch |  |  | 1 | 3.5 | 10 | acre/day | DOT field daily (crew) | Seed, fertilize & mulch | Typ = median of WSDOT West normal 5 and NCDOT mid 2; low NCDOT 1; high WSDOT 10. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT;NCDOT | A
ERO-HS-8631 | SITE-HYDROSEED | Hydroseeder Reinco HG-10 | Hydroseed / seed, fertilize & mulch |  |  | 1 | 3.5 | 10 | acre/day | DOT field daily (crew) | Seed, fertilize & mulch | Typ = median of WSDOT West normal 5 and NCDOT mid 2; low NCDOT 1; high WSDOT 10. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT;NCDOT | A
ERO-HS-8632 | SITE-HYDROSEED | Hydroseeder Reinco HG-30 | Hydroseed / seed, fertilize & mulch |  |  | 1 | 3.5 | 10 | acre/day | DOT field daily (crew) | Seed, fertilize & mulch | Typ = median of WSDOT West normal 5 and NCDOT mid 2; low NCDOT 1; high WSDOT 10. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT;NCDOT | A
ERO-MULCH-8633 | SITE-HYDROSEED | Straw mulcher Finn B70 | Hydroseed / seed, fertilize & mulch |  |  | 1 | 3.5 | 10 | acre/day | DOT field daily (crew) | Seed, fertilize & mulch | Typ = median of WSDOT West normal 5 and NCDOT mid 2; low NCDOT 1; high WSDOT 10. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT;NCDOT | A
ERO-MULCH-8634 | SITE-HYDROSEED | Straw mulcher Reinco M65 | Hydroseed / seed, fertilize & mulch |  |  | 1 | 3.5 | 10 | acre/day | DOT field daily (crew) | Seed, fertilize & mulch | Typ = median of WSDOT West normal 5 and NCDOT mid 2; low NCDOT 1; high WSDOT 10. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT;NCDOT | A
ERO-MULCH-8635 | SITE-HYDROSEED | Straw mulcher Reinco M90 | Hydroseed / seed, fertilize & mulch |  |  | 1 | 3.5 | 10 | acre/day | DOT field daily (crew) | Seed, fertilize & mulch | Typ = median of WSDOT West normal 5 and NCDOT mid 2; low NCDOT 1; high WSDOT 10. Crew/spread rate: equipment hours = crew days x hours/day. | WSDOT;NCDOT | A
Note on E1: Blue/yellow = editable input driving the formulas (bucket CY, blade LCY, drum width, moldboard, payload). Blank = not in notes -> row is D until entered.

## Duration_Norms
Equipment_group | Duration driver (how hours/days are derived) | Minimum rental / minimum hours | Shift / overtime rule | Standby / idle | Mob/demob note | Source_ids | Confidence
Mobile cranes (operated hourly) | Pieces / pieces per day (LF-GIRDER, LF-STEEL) or the lift plan; add travel (portal-to-portal) and setup | NTX 3-4 hr; Dependable 1-8 hr (22 t 1 hr, 40 t 2 hr, 75 t 4 hr, 115 t 8 hr); CFCS 4 hr small, 6 hr mid/large, 8 hr RT/crawler/heavy-lift; BigRentz 3-8 hr | OT after 8 hr or before 7 am / after 5 pm, Sat/Sun: +$50/hr per man (NTX), Sun/holiday +$85; CFCS OT +$74/hr (1 operator), double time +$144, holiday +$224 | Standby $95/hr per man (NTX); riggers $88-160/hr, 4 hr minimum | Counterweight trailer add $1,200 (Dependable); permits $52-275 (NTX) | NTXC;DEPC;CFCS;BIGR-CR | A
Crawler / large mobile cranes (monthly) | Monthly rental for the erection duration + assembly/disassembly | Monthly (not sourced as a minimum) | Owned: Caltrans HCECL OT factor 0.85/0.86 | Caltrans delay factor 0.17/0.16 (HCECL) | Multiple lowbeds + counterweight + boom + assist crane (counts not sourced) | CALT-2627;CALT-INT | C
Tower crane | Frame/erection duration; ~10-12 lifts/hr theoretical; 70-75% effective hook time | $15,000-60,000/month (BigRentz) |  |  | Erection/dismantle not sourced | BIGR-CR;VTT-CRANE | B
Concrete pumps (operated) | Pour CY / placement rate (60-100 boom, 40-60 line) + setup + washout | 3-4 hr minimum block; minimum charge $600-1,600 (CCE) | Over 8 hr total or prevailing-wage jobs +$45/hr (Ohio); weekend/after-hours +25-50% (CCE); extra operator +$80/hr, 4 hr min | Cancellation within 2 hr $225 (Ohio) | Travel billed hourly ($110-130/hr Ohio); permit $210 (46 m) | CPO;CCE | A
Aerial work platforms | Trade crew duration served (finishes, MEP rough-in, envelope); round to day/week/4-week, whichever totals cheaper | 1 day | Single shift 0-8 h; double shift 1.5x; triple 2x (COSTARS) | Rental accrues per calendar period; owned delay factor 0.21 (HYLFT) | Delivery ~$75-350 each way <=60 ft; $300-800+ large booms | COSTARS;SCAFEX;DOZR-SC;DOZR-BM;CALT-2627 | B
Telehandlers / forklifts | Trade crew duration served (framing, masonry, roofing, MEP) | 1 day | 8/40/160 hr; OT pro-rata (rate / 8, 40, 160) | Owned delay factor 0.22 (FKLFT) | Delivery $200-500+ each way; can add 10-15% to short rentals (DOZR) | DOZR-TH;URI-TERMS;CALT-2627 | B
Compressors | Duration of the tool-using activity (breakers, drills, blasting) | 1 day | 8/40/160; double 1.5x, triple 2x | Owned delay factor 0.14/0.13 (AIRCP) | Delivery $75-200 each way (rentd) | RENTD;URI-TERMS;CALT-2627 | B
Generators / welders | Powered activity duration; standby power runs 24/7 -> price 3 shifts (2x) or hours over 176/month | 1 day | Wheeler single shift; double/triple shift extra; Burris 10/50/200 hr basis on generators | Owned delay factor 0.13/0.12 (ELGEN) | Towable delivery $125-400 (EquipNearby) | W25;B25;EQNB;CALT-2627 | B
Light towers | Night-shift duration | 1 day | Per shift |  | Pickup-towed | W25;B25 | C
Dewatering pumps | Open excavation below water table; often 24 hr/day -> 3-shift or 24/7 pricing + fuel per running hour (inference) | 1 day | Monthly OT over 176 hr applies (EquipmentWatch rule) | No source | Hoses not included in FEMA rates | EW-TIME | C
Trench boxes / plates / shoring | Open-trench duration = pipe LF / crew LF per day + set/move days | 1 day (Wheeler) | Calendar-based |  | Flatbed haul | W25;WSDOT | C
Heaters | Cold-weather protection period | 1 day | Calendar-based |  | Pickup-towed | W25 | C
Office trailers / containers / fence | Project or phase duration | 1 month typical | Monthly |  | Office delivery $500-1,500; delivery+setup $1,000-5,000+; pickup ~= delivery; containers $100-500; fence $150-600+ plus setup/removal $200-1,000+ | PRICER-OT;BNB-CONT;PRICER-FN | B
Operated dump trucks | Haul cycle (Production sheet) -> truck-hours; or tons/day / truck capacity | Not sourced | Hourly with driver |  | Self-propelled | MNDLI;DTR | B
All rented equipment (general) | Activity quantity / production -> hours -> days at shift hours; round to rental increment | Day = 8 hr, week = 40 hr, 4-week = 160 hr (176 at Wheeler/EquipmentWatch) | OT = rate / 8, 40, 160 (or 176) per extra hour; double shift 1.5x, triple 2x | Charges accrue Sat/Sun/holidays (URI) | See Mob_Demob | URI-TERMS;W25;C25;B25;EW-TIME | A
All owned equipment (general) | Operating hours from production | n/a | Caltrans OT factor 0.80-0.92 x rate after 8 hr/day; USACE prorates FCCM above 40 hr/wk | USACE: 0.5 x DEPR + FCCM, max 40 hr/wk; Caltrans delay factor 0.09-0.45 x rate, max 8 hr/day & 40 hr/wk; FEMA: not eligible unless intermittent >1/2 day |  | USACE-EP;CALT-2627;FEMA-PG;FEMA-IS1000 | A
Caltrans delay (standby) and overtime factors - owned equipment (applied to the all-in hourly rate)
Caltrans class | Delay factor (book 26-27) | OT factor (book 26-27) | Delay factor (Sep 2026 interim) | OT factor (Sep 2026 interim)
HCECL hydraulic cranes & excavators, crawler | 0.17 | 0.85 | 0.16 | 0.86
HCESP self-propelled | 0.13 | 0.88
HCETD truck-mounted w/ carrier | 0.12 | 0.89
HCETG truck-mounted less carrier | 0.09 | 0.92
GRADR graders | 0.11 | 0.9 | 0.1 | 0.91
LDRCL loaders, crawler | 0.11 | 0.9
LDRRT loaders, rubber tire incl. backhoe | 0.11 | 0.9 | 0.1 | 0.91
ELGEN generators & light plants | 0.13 | 0.88 | 0.12 | 0.89
AIRCP air compressors | 0.14 | 0.87 | 0.13 | 0.89
HYLFT personnel lifts / AWPs | 0.21 | 0.8
HAMMR hammers | 0.21 | 0.81
FKLFT forklifts | 0.22 | 0.8
LEADS pile leads | 0.45 | 0.59
Sources: CALT-2627; CALT-INT. Two extracts differ by ~0.01 for some classes.

## Factors
1. Soil volume conversion (FM 5-434 Table 1-1; verified against 3 worked examples)
Multiply initial volume by the factor. Default mapping: sand -> Sand/gravel; sandy clay/common earth -> Loam; clay -> Clay; rock -> Blasted rock. Sources: FM5434; USMC-PE
Soil | Bank->Loose | Bank->Compacted | Loose->Bank (load factor) | Loose->Compacted | Compacted->Bank | Compacted->Loose | Swell % (B->L - 1) | Source_ids
Sand / gravel | 1.11 | 0.95 | 0.9 | 0.86 | 1.05 | 1.17 | 11% | FM5434;USMC-PE
Loam (common earth) | 1.25 | 0.9 | 0.8 | 0.72 | 1.11 | 1.39 | 25% | FM5434;USMC-PE
Clay | 1.43 | 0.9 | 0.7 | 0.63 | 1.11 | 1.59 | 43% | FM5434;USMC-PE
Rock, blasted (also coral) | 1.5 | 1.3 | 0.67 | 0.87 | 0.77 | 1.15 | 50% | FM5434;USMC-PE
1b. Secondary ranges (cross-check only; notes advise confirming with geotech)
Material | Bulking (loose/bank) | Shrinkage (compacted/bank) | Source_ids
Blasted rock | 1.40-1.50 (EduRev 1.50-1.80) | 0.95-1.05 (conflicts with FM B->C 1.30) | CIVILS;EDUREV
Clay | 1.20-1.30 (EduRev 1.25-1.40) | 0.80-0.90 | CIVILS;EDUREV
Sandy clay / common earth | 1.15-1.25 (EduRev common 1.25) | 0.85-0.95 | CIVILS;EDUREV
Sand | 1.05-1.15 | 0.90-1.00 | CIVILS
Gravel | 1.10-1.20 | 0.90-1.00 | CIVILS
Loam/topsoil | 1.20-1.25 | 0.85-0.95 | CIVILS
Formulas | Swell % = (bank density / loose density - 1) x 100; Load factor = 1/(1+swell) | Shrinkage % = (1 - bank / compacted density) x 100 | KSU-2
2. Bucket fill factors
Material | Fill factor | Source_ids
Moist loam / sandy clay (hoe) | 1.00-1.10 | FM5434-8
Sand and gravel (hoe) | 0.95-1.10 | FM5434-8
Hard tough clay (hoe) | 0.80-0.90 | FM5434-8
Rock well blasted (hoe) | 0.60-0.75 (Cat: 0.80-0.95) | FM5434-8;CAT-FILL
Rock poorly blasted (hoe) | 0.40-0.50 (Cat: 0.60-0.75) - CONFLICT | FM5434-8;CAT-FILL
Mixed moist aggregates (loader) | 0.95-1.00 | CAT-FILL
Uniform aggregate to 1/8 in | 0.95-1.00 | CAT-FILL
1/8-3/8 in | 0.90-0.95 | CAT-FILL
1/2-3/4 in | 0.85-0.90 | CAT-FILL
1 in and over | 0.85-0.90 | CAT-FILL
Blasted rock average (Cat) | 0.75-0.90 | CAT-FILL
Rock/dirt mixtures | 1.00-1.20 | CAT-FILL
Soil, boulders and roots | 0.80-1.00 | CAT-FILL
Cemented materials | 0.85-0.95 | CAT-FILL
Catalog default (Production sheet) | Excavators 0.80/1.00/1.10 low/typ/high (bank cut); loaders 0.85/0.95/1.00; backfill 0.85/0.95/1.00 | Derived from above
3. Job efficiency and operator / condition factors
Factor | Value | Note | Source_ids
Job efficiency, well-managed (50-min hour) | 0.83 | Settings B7 default | FM5434
Job efficiency, alternative (45-min hour) | 0.75 |  | FM5434;EDUREV
Overall efficiency E range | 0.75-0.90 | Job condition factor J 0.80-1.00 | EDUREV
Grader efficiency | 0.70-0.85 |  | CAT-MG
Tracked operator: excellent day / night | 1.00 / 0.75 | Includes visibility; assumes 60-min hour, so E still applies | FM5434;USMC-PE
Tracked operator: average day / night | 0.75 / 0.56 |  | FM5434;USMC-PE
Tracked operator: poor day / night | 0.60 / 0.45 |  | FM5434;USMC-PE
Wheeled operator: excellent / average / poor (day) | 1.00 / 0.60 / 0.50 | Night 0.67 / 0.40 / 0.33 | USMC-PE
4. Dozer correction factors (Cat push curves NOT obtained; catalog uses blade/cycle method)
Factor | Value | Source_ids
Material: loose stockpile | 1.20 | FM5434
Material: hard to cut/frozen, with tilt | 0.80 | FM5434
Material: hard to cut, without tilt | 0.70 | FM5434
Material: hard to drift (dead, dry non-cohesive, sticky) | 0.80 | FM5434
Material: rock ripped or blasted | 0.60-0.80 | FM5434;USMC-PE
Technique: slot dozing | 1.20 | FM5434
Technique: side-by-side | 1.15-1.25 (USMC uses 1.15) | FM5434;USMC-PE
Grade: per 2% grade | +/-0.04 (e.g. +2% uphill = 0.96; -10% = 1.15; -15% = 1.30) | USMC-PE;FM5434
Soil weight | 2,300 / actual lb per LCY | FM5434
Blade load (first principles) | LCY = 0.0139 x H x W x L (ft) of leveled pile | KSU-4
Dozer cycle | fixed 0.05 min + D/doze speed + D/reverse speed; example 4.0 km/h doze, 8 km/h reverse | KSU-4
Ripping maintenance | +30-40% machine maintenance | FM5434
Shanks | 3 packed soil/hardpan/shale; 2 fractured rock; 1 solid rock | FM5434
5. Rolling resistance and grade (haul roads)
Surface | Rolling resistance (lb per short ton)
Hard, smooth, stabilized | 40
Firm, ~1 in penetration (gravel-topped) | 65
Rutted dirt, 2-3 in penetration | 100
Rutted, 4-6 in penetration | 150
Soft, muddy or sand, 7+ in | 400
Effective grade % = grade % + RR (lb/ton) / 20; travel time (min) = ft / (mph x 88); GR = tons x 20 x % grade. Sources: USMC-PE; KSU-T6
6. Cycle time components
Component | Value | Source_ids
Hydraulic excavator <1 CY | 14 s at 40-60% max depth, 30-60 deg swing | FM5434-8
Hydraulic excavator 1-2.5 CY | 15 s (8-12 ft depth) | FM5434-8
Optimum hoe depth | 30-60% of max digging depth | FM5434-8
Trench factor | 0.95-1.0 (avg 0.98) | KSU-T3
Swing-depth S | 1.1 at 50% depth / 1.0 at 70% (90 deg swing); full table not retrieved | KSU-T3
Wheel loader basic cycle | 27-33 s (load, dump, 4 reversals, min travel) | CAT-WL
Truck dump & maneuver | 1.5 min (worked example) | OEP
Truck fixed time | 2.0 min (KSU example) | KSU-T5
Scraper turn/dump | 0.81 min (0.3 dump, 0.3 cut turn, 0.21 fill turn) | FM5434
Scraper load time | 0.85 min D8 pusher; 1.0 D7; 0.9 self-loading 613 | FM5434
Scraper fixed time | push-loaded 1.43-1.93 min struck; self-loading 2.5-3.0 | USMC-PE
Pusher cycle | 1.4 x load time + 0.25 min | FM5434;USMC-PE
Scraper load | 52,800 lb / soil weight, capped 22 CY (621G) | USMC-PE
Haul speeds (truck, ADT, scraper) | NOT IN NOTES - Settings B22-B27 left blank (Cat rimpull/speed curves not retrieved) | Gap
7. Compaction
Item | Value | Source_ids
Compaction formula | CCY/hr = 16.3 x W(ft) x S(mph) x L(in) x E / P | KSU-T7
Constant 16.3 | 5,280 / 12 / 27 = 16.30 | KSU-T7 (derived)
Passes | Typically 4-6 (set from test strip) | EDUREV;MST-GE441
Vibratory speed rule | ~1 impact per inch of travel; 1,200-2,500 vpm -> 1.14-2.37 mph | STORMW (speed derived)
Lift range overall | 6-18 in by equipment | KFUPM
Trench compactors (~3,000 lb) | lifts <= 4-5 in | MST-GE441
Hand tampers / rammers | 2-3 in lifts, 7-18 psi | MST-GE441
Plates | 5-13 psi; ATE TP-1830H 8,550 ft2/hr, 13 in max depth | MST-GE441;ATE-PLATE
Asphalt roller speed | <= 3 mph; 10-12 impacts/ft recommended | AI-ROLL;PSU-SP
Roller selection | Rock fill: vibratory; CH/MH: padfoot then pneumatic; CL/ML: padfoot; GC/SC: vibratory or pneumatic; SM/GM/SW/SP/GW/GP: vibratory | MST-GE441
Roller widths (catalog) | Cat CS5/CP5 50 in; CS7/CP7/CS44 66 in; CS10-CS19 84 in; CB1.7 35 in to CB4.4 55 in; CB7 59 in; CB8/10 67 in; CB13 79 in; CB15/16 84 in; CW16 68/84 in; CW34 82 in | ZIEGLER
Roller speeds by type (sheepsfoot/pneumatic) | NOT RETRIEVED (FM 5-434 Ch.11 tables blocked) | Gap
8. Water for compaction and dust
Item | Value | Source_ids
Gal per CCY | dry density (pcf) x 27 x moisture to add (fraction) / 8.33; 120 pcf, +7% -> ~27 gal/CCY | FM5434-11 (derived)
Gal per SY | dry density x % added x lift (ft) x 9 / 8.33 | FM5434-11
Worked example | 6 in lift, 120 pcf, OMC 12%, borrow 5%, 40 ft width -> 2,017 gal per station per lift | FM5434-11
Distributor | 1,000 gal truck, 12 ft spray bar (4-24 ft) | FM5434-11
OMC | fine-grained 12-25%; granular 7-12%; work within +/-2% of OMC | FM5434-11
Project budget example | 38.75 gal/CY fill (OMC - antecedent) | CPUC-WATER
Dust control | 1,815 gal/acre/day active (1,210 staging); 3 applications/day; ~10% of graded area active | CPUC-WATER
9. Grader
Item | Value | Source_ids
Area formula | ft2/hr = S (mph) x (Le - Lo) x 5,280 x E | CAT-MG
Speeds | finish 0-2.5 mph; heavy blading 0-6; ditch 0-3; ripping 0-3; road maint. 3-9.5 | CAT-MG
Effective blade at 30 / 45 deg | 12 ft: 10.4 / 8.5; 14 ft: 12.1 / 9.9; 16 ft: 13.9 / 11.3; 24 ft: 20.8 / 17.0 | CAT-MG
Overlap | ~2 ft | CAT-MG
Time method | T = sum(passes x length / speed) / E | KSU-T7
10. Fuel
Item | Value | Source_ids
Diesel fuel factor | 0.34 lb/bhp-hr / 7 lb/gal = 0.0486 gal/bhp-hr at full load | USACE-EP
Gasoline | 0.55 / 6 = 0.0917 gal/bhp-hr | USACE-EP
Load factor typical | 0.35-0.60; D6 implied 0.46 | USACE-EP;CATFUEL22 (derived)
Severe conditions | +30% fuel | USACE-EP
Cat idle definitions | low 50% idle, medium 30%, high 10% | CATFUEL22
VisionLink vs Ed.46 | 2022 medium runs ~20-30% below Ed. 46 medium ranges | CATFUEL22;CATPHB46

## Mob_Demob
Mobilization / demobilization - one-time cost per move, per resource (counted once per resource per project; demob stored separately)
One-way move = MAX(minimum charge, $/loaded mile x one-way miles) + permits x states (if Permit_likely = Y) + escorts x escort $/mi x miles + load/unload hr x $/hr. Default distance = Settings!B6. Equipment sheet columns Default_mob_one_way / Default_demob_one_way use the TYPICAL columns below. Owned vs rental: the same haul formula applies (rental delivery for large machines is a pass-through haul).
Transport_class | Typical equipment | $/mi low | $/mi typical | $/mi high | Min low | Min typical | Min high | Permit $/state (typ) | Permit range | Escort $/mi (typ) | Escorts (default count) | Load/unload hr (typ) | Load/unload $/hr | Basis / sources | Confidence
self-propelled | Drives or tows itself on road (trucks, truck-mounted cranes/pumps, bucket trucks) | [7 empty] | n/a |  |  |  |  | Mob = travel hours x (unit rate + operator/driver from labor); no trailer. Not computed here. | D
pickup-towed | Towed by contractor pickup or supplier (compressors, generators, light towers, pumps, small trailers) | 1 | 1.5 | 2 | 75 | 200 | 400 |  | n/a |  |  |  |  | $/mi = hotshot standard $1-2 (OTR-HOT) as proxy; minimum = towable delivery norms: compressors $75-200, generators $125-400 (RENTD; EQNB); typ $200 chosen within both bands | C
tilt-trailer | Tag / hotshot / tilt trailer (skid steer, CTL, mini ex <~10 t, small rollers) | 1 | 1.5 | 2 | 200 | 500 | 800 |  | n/a |  |  |  |  | Hotshot standard $1-2/mi; local <100 mi flat $200-800 (OTR-HOT, Feb-Oct 2026); typ = midpoints | B
flatbed | Flatbed / step deck (telehandlers, backhoes, forklifts, trench boxes, attachments) | 2 | 2.75 | 3.5 | 300 | 400 | 500 |  | n/a |  |  |  |  | Flatbed $2.00-3.50/mi (OTR-RGN); DAT Sep 2026 flatbed spot $3.61/mi incl. fuel ($2.60 ex-fuel); minimum dispatch $300-500 (OTR-LOW) | B
lowboy-legal | Lowboy/RGN within 80,000 lb gross and 8'6" (approx. <=20-30 t machines) | 3.5 | 4.75 | 6 | 300 | 550 | 800 |  | n/a |  |  |  |  | RGN legal $3.50-6.00/mi (OTR-RGN); lowboy table $3.50-5.00 (OTR-LOW, inconsistent); local legal flat $300-800 | B
lowboy-permitted | Lowboy/RGN oversize and/or overweight (80-120K GVW or >8'6") | 5 | 6.5 | 12 | 800 | 1650 | 2500 | 150 | $15-500 per state; TX 80,001-120,000 lb $210 | 2.25 | 0 |  |  | Oversize $5-8, overweight $6-12, OS+OW $8-15 (OTR-RGN); local oversize flat $800-2,500+ (OTR-LOW); permit budgeting ~$150/state; escort $1.50-3.00/mi each (one front escort >12 ft wide) | B
multi-axle-heavy | Multi-axle / superload (D9+, 50 t+ excavators, large planers) | 8 | 11.5 | 15 | 800 | 1650 | 2500 | 150 | $15-500 standard; superload $500-5,000+ (2-4 wk); TX >200,000 lb $435 + $35 | 2.25 | 1 |  |  | OS+OW $8-15+ (superload $10-20+); escort $1.50-3.00/mi (default 1 escort = inference); route survey $500-5,000+; bridge analysis $200-1,000 per bridge | C
crane-assembled | Crane needing multiple truckloads + assist crane + assembly | [7 empty] | quote |  |  |  |  | Quote only: N truckloads (boom, counterweight) + assembly/disassembly hours (not sourced) + permits | D
delivered-by-supplier | Rental house delivery (aerial lifts <=60 ft, site trailers, containers, fence) |  |  |  | 75 | 200 | 350 |  | n/a |  |  |  |  | Scissor/45-60 ft boom local delivery $75-350 each way (SCAFEX; DOZR-SC $100-350); typ $200 = notes inference ($150-250) | B
Load/unload hours and truck+driver $/hr: NOT SOURCED (blank = 0 in formulas). Haul rates were published when diesel averaged ~$6.29 (Sep 2026); rates run 10-20% higher Mar-Sep (OTR-RGN). Sources: OTR-RGN; OTR-LOW; OTR-HOT; DAT-0926; SCAFEX; DOZR-SC; RENTD; EQNB; TXDMV
Calculator (edit blue cells)
Transport class | lowboy-permitted
One-way miles | 50
States crossed (permits) | 1
Permit required? (Y/N) | Y
Escorts (count) | 1
Load/unload hours
Load/unload $/hr
Line-haul (max of minimum, $/mi x miles) | 1650
Permits | 150
Escorts | 112.5
Load/unload | 0
One-way MOB | 1912.5
One-way DEMOB (x Settings demob factor) | 1912.5
Mob + demob per resource (once per project) | 3825
Legal limits and permit triggers
Item | Value | Source_ids
Gross vehicle weight (federal) | 80,000 lb | CFR658
Single axle / tandem | 20,000 lb / 34,000 lb; bridge formula W = 500(LN/(N-1) + 12N + 36) | CFR658
Width | 8'6" (102 in); wider = oversize permit; tracks wider than 8.5 ft need permits | PROJUL
Height | 13'6"-14' by state (162 in) | PROJUL
Overweight band | 80,000-120,000 lb GVW | OTR-LOW;OTR-RGN
Superload | >200,000 lb, >16 ft wide/tall, >120 ft long (Projul); 120K+ (RGN guide) vs 150K+ (lowboy guide) - inconsistent | PROJUL;OTR-RGN;OTR-LOW
Texas permit schedule | 80,001-120,000 lb $210; 120,001-160,000 $285; 160,001-200,000 $360; >200,000 $435 + $35; >254,300 lb Super Heavy; route inspection >20 ft wide, 18'11" high or 125 ft long | TXDMV
Escorts | one front escort >12 ft wide; front and rear >14-16 ft (state-specific); pilot car $500-1,500/day; police $50-200/hr | PROJUL;OTR-LOW;OTR-RGN
Example | Cat 336D L transport width 133.5 in (11.1 ft) -> oversize on width alone; 30 t+ excavators default to permitted | RITCHIE-336
Catalog transport-class rule (inference) | Weight <=22,000 lb -> tilt-trailer; <66,000 -> lowboy-legal; <100,000 -> lowboy-permitted; >=100,000 -> multi-axle-heavy; width >8.5 ft -> permit Y. Tractor+lowboy tare NOT sourced, so 44,000-66,000 lb rows are 'maybe'. | Inference from CFR658/PROJUL
Rental supplier delivery fee norms (each way unless stated)
Equipment | Delivery norm | Source_ids | Date
Excavators <4 t | $200-400 round trip | DOZR-EX | Mar 2026
Excavators 5-25 t | $300-500 round trip | DOZR-EX | Mar 2026
Excavators 30 t+ | $500-1,000+ round trip | DOZR-EX | Mar 2026
Mini ex (consumer) | $50-150 (one-way/both not stated) | FJD | Apr 2025
Consumer excavator (home-center) | $60-100 within 10 mi + $3-4/mi | ANGI | Oct 2026
Telehandlers | $200-500+ each way (adds 10-15% to short rentals) | DOZR-TH | Mar 2026
Scissors | $100-350 each way | DOZR-SC | Mar 2026
Scissor / 45 ft boom local | $75-250 each way | SCAFEX | Sep 2026
Booms | $150-500+; 80 ft+ may need lowboy; long hauls >$1,000 | DOZR-BM | Mar 2026
Large telescopic on lowboy | $300-800 each way | SCAFEX | Sep 2026
Towable generators | $125-400 | EQNB | Sep 2026
Compressors | $75-200 each way | RENTD | Jul 2026
Wheeler haulage (dealer, UT) | <25 mi $224; 25-60 mi $364; >60 mi = 25-60 rate + $8.00-18.00/mi by class; pavers/pneumatic rollers $434 / $664 / $8.90/mi; cold planers $664-965 (<25 mi), $965-1,233 (25-60) | W25 | 2025
Wheeler on-site standby | $200/hr after first 30 min | W25 | 2025
Office trailer | Delivery $500-1,500; delivery+setup $1,000-5,000+; pickup ~= delivery; ADA ramp $300-800+ | PRICER-OT | Oct 2026
Storage container | $100-500 | BNB-CONT | Mar 2025
Temporary fence | Delivery/pickup $150-600+; setup/removal $200-1,000+ | PRICER-FN | Jun 2026
Project mobilization sanity check only: Caltrans notes contractors bid mobilization ~10% of contract (2006 memo) [CALT-MOB]; ODOT caps partial payments [ODOT624]. Not an equipment default.

## Rental_Terms
Term | Value / rule | Source_ids | Date | Catalog default
Hours per period (industry) | 1 shift = 8 hr/day, 40 hr/week, 160 hr/4-week | URI-TERMS;B25;C25 | 2025-2026 | Use 8/40/160
Hours per period (Cat Rental Store) | 8 / 40 / 176 hr (4-week buys ~10% more hours) | W25;EW-TIME | 2025 | Note on Wheeler-sourced rows
Hours per period (some items) | 10 / 50 / 200 hr (Burris generators etc.) | B25 | Mar 2025
Month definition | Columbus: 28-day month, max 160 hr; days after first month at 1/28 of monthly | C25 | Jun 2025 | 4-week = 28 days
Overtime - pro rata | Daily / 8, weekly / 40, 4-week / 160 (176) per hour over | W25;B25;C25;EW-TIME | 2025 | Pro-rata hourly
Overtime - shift multipliers | Double shift 1.5x; triple shift 2x (URI, COSTARS); Burris three-shift = 2x on a 480 hr 4-week; FL Air Tool 2 shifts 1.5x, 3 shifts 2x (2019) | URI-TERMS;COSTARS;B25;FAT19 | 2023-2025 | 1.5x / 2x
Weekend / holiday | Charges accrue on Saturdays, Sundays and holidays | URI-TERMS | Oct 2026
Short rental | <24 hr late return charged a full day | URI-TERMS | Oct 2026
Week / day ratio observed | Wheeler 2.90; Burris 3.00; Columbus 2.47; RTL 3.26-4.24; Nu-Way 3.49; Ahearn 3.00; DOZR 2.81; aerial 2.2-2.8 | W25;B25;C25;R25;N25;A26;DOZR-EX;COSTARS | 2025-2026 | 3.0 (Settings B16)
4-week / week ratio observed | Wheeler 2.90; Burris 3.00; Columbus 2.49; RTL 2.58-2.91; Nu-Way 2.73; Ahearn 2.17; DOZR 2.53; aerial 2.0-2.5 | W25;B25;C25;R25;N25;A26;DOZR-EX;COSTARS | 2025-2026 | 2.9 (Settings B17)
4-week / day ratio observed | 6.1 (Columbus) to 10.9 (RTL E35); dealer cluster 8.4-9.0; aerial 5-7 | same |  | ~8.7
Columbus ladder | Weekly = 40% of monthly; daily = 40% of weekly | C25 | Jun 2025
Damage waiver / RPP | Wheeler 16% (deductible $1,000 <$24,999 equipment, $2,500 above; waivable with insurance); DOZR LDW 10-15%; Sunbelt/Herc/H&E % not found | W25;DOZR-EX | 2025-2026 | 12-16%
Environmental fee | URI 2.00% of service charge, capped at $99 | URI-TERMS | Oct 2026 | 2% (cap $99)
Refuel charge | Columbus $8.00/gal if not returned full; URI refuel at store price; Wheeler fuel + service charge | C25;URI-TERMS;W25 | 2025-2026 | Return full or $8/gal
Fuel included? | No - all bare rates exclude fuel (DOZR: fuel not included) | DOZR-EX;B25 |  | Fuel from gal/hr x fuel price
Delivery | Excluded from rates; see Mob_Demob delivery norms | B25;W25
Tax / insurance | Excluded; Columbus requires >= $1M GL with Columbus loss payee; CA personal-property-tax reimbursement up to 0.75% (URI) | C25;URI-TERMS
Damage responsibility | Customer responsible for track damage and flat tires (Burris) | B25 | Mar 2025
Machine-control models | 'i' intelligent machine-control models ~25-75% more (Columbus PC210LCi $1,400/4,150/12,400) | C25 | Jun 2025
Attachments | Generally rented only with vendor's carrier; buckets not included in Burris base rates; standard bucket included (DOZR) | C25;B25;DOZR-EX
Set-up / dismantle | PC490 and larger may bill set-up/dismantle separately (Columbus) | C25 | Jun 2025
Paver cleaning | $600 if AP paver not returned clean (Wheeler) | W25 | 2025
Crane terms | Portal-to-portal; 7% fuel surcharge (NTX), 8-10% elsewhere; spreader bar $150/day, man basket $150/day | NTXC;CFCS | 2025-2026
Concrete pump terms | Fuel surcharge 8-12%; washout $250-450; included hose 150-200 ft, extra $1.50-3.00/ft (Ohio $1/ft beyond 50 ft) | CCE;CPO | 2026
Regional rental variation | Market-driven; 2001 URI CEO: one region +7% while another -2.5% same day. No current ARA/Rouse public data | RER-2001 | 2001 | Use Location factor + local quote

## Location
Location adjustment - three separate parts
1) Bare equipment rate (rental or owned ex-fuel) x EQUIPMENT location factor (Settings!B8, default 1.00; suggested clamp 0.85-1.15 lower 48 = inference; higher for AK/HI).
2) Fuel = gal/hr x LOCAL fuel price (Settings!B4; use PADD table below or user price; off-road dyed diesel is lower than on-highway because road taxes are excluded).
3) Operator = hours x project wage set (prevailing or open shop). Never from this workbook.
Mob/demob uses the haul formula with diesel-indexed per-mile rates - NOT the location factor.
WARNING: Do NOT apply the labor or total City Cost Index to equipment. In RSMeans 2025 Illinois the equipment index moves opposite to labor (lowest in Chicago metro where labor is highest).
Formula: hourly_cost = bare_rate x equip_location_factor + fuel_gal_hr x local_fuel_price + operator_hours x local_wage [Blue Book applies regional factor to ownership only; operating at 1.00 - EW-FHWA]
Evidence A - RSMeans 2025 City Cost Index, Illinois (student-uploaded copy; verify) [RSM-IL25]
City | 015433 Contractor Equipment | Weighted avg MAT | Weighted avg INST (labor) | Weighted avg TOTAL
Chicago | 96.1 | 98.2 | 144.2 | 116.1
Joliet | 89.9 | 97.3 | 141.4 | 114.5
North Suburban | 89.9 | 96.4 | 140.1 | 113.4
Carbondale | 105.1 | 93.7 | 102.6 | 97.2
Centralia | 105.1 | 93.9 | 104.4 | 98
Rock Island | 96.7 | 95.4 | 99.3 | 96.9
Peoria | 93.8 |  | 106.1
Springfield | 101.7 |  | 104.7
Equipment range (max-min) | 15.2 |  | 44.9
Equipment range / labor range | 0.33853
Evidence B - EquipmentWatch Blue Book regional adjustments (crawler excavators; undated page) [EW-REG; EW-FHWA]
Item | Value
Range | 82.2% (New Mexico) to 142.7% (Alaska North)
Above 108% | Alaska (3 regions), Minnesota, Wisconsin
88.9% or lower | Texas, Arizona, Utah, New Mexico
Skid steer example (monthly ownership) | $2,385.37 -> $3,403.92 (AK x1.427) / $1,960.77 (NM x0.822)
Contiguous-US band | ~82-108%+ (exact max not given)
Drivers | Climate (shorter seasons = fewer hours to recover fixed cost) first; per-capita income (mechanic wages, sales tax, freight) second
Applies to | Ownership only; hourly operating cost added at 1.00
Evidence C - EIA on-highway diesel and regular gasoline, $/gal incl. taxes, week of Oct 19, 2026 (released Oct 20, 2026) [EIA-GDU]
Region | Diesel $/gal | Gasoline $/gal | Diesel ratio to US avg
US average | 6.276 | 4.284 | 1
East Coast (PADD 1) | 5.984 |  | 0.95347
New England (1A) | 6.47 |  | 1.0309
Central Atlantic (1B) | 6.508 |  | 1.037
Lower Atlantic (1C) | 5.74 | 3.86 | 0.9146
Midwest (PADD 2) | 6.352 |  | 1.0121
Gulf Coast (PADD 3) | 5.903 | 3.784 | 0.94057
Rocky Mountain (PADD 4) | 6.422 |  | 1.0233
West Coast (PADD 5) | 7.394 |  | 1.1781
West Coast less California | 6.659 |  | 1.061
California | 8.242 | 6.031 | 1.3133
Spread max-min ($/gal): | 2.502
DAT September 2026 national average diesel $6.291/gal [DAT-0926]. No EIA off-road/dyed diesel regional series retrieved.
USACE EP 1110-1-8 regionalizes only fuel, the labor adjustment factor (FOG, repair, tire repair) and freight; depreciation and FCCM are not regionalized. Regional tables not retrieved. [USACE-EP]

## Sources
Source_ID | Title | Publisher | Edition / date | URL | Supports
FEMA25 | FEMA Schedule of Equipment Rates 2025 | FEMA | 2025 ed.; declarations on/after Jul 1 2025 | https://www.fema.gov/sites/default/files/documents/fema_pa_schedule-equipment-rates_2025.pdf | Owned hourly rates (fuel incl., operator excl.); FEMA code list
FEMA-PG | FEMA 2025 Schedule page (rules) | FEMA | 2025 | https://www.fema.gov/sr/node/500264 | What FEMA rates include; operator excluded; standby not eligible
FEMA-IS1000 | IS-1000 Applicant (Force Account) Equipment | FEMA EMI | accessed Oct 2026 | https://emilms.fema.gov/is_1000/groups/247.html | Intermittent-use standby exception
USACE-EP | EP 1110-1-8 Construction Equipment Ownership & Operating Expense Schedule (pamphlet) | USACE | 12 Aug 2021 | https://www.publications.usace.army.mil/Portals/76/Users/182/86/2486/EP%201110-1-8_RV1-12.pdf | Method: depreciation, FCCM, fuel factor 0.34 lb/bhp-hr, standby 0.5xDEPR+FCCM
CALT-2627 | Caltrans Labor Surcharge & Equipment Rental Rates 2026-27 | Caltrans | Apr 1 2026-Mar 31 2027 | https://dot.ca.gov/-/media/dot-media/programs/construction/documents/equipment-rental-rates-and-labor-surcharge/book_26_27.pdf | Delay (standby) and overtime factors; rate inclusions
CALT-INT | Caltrans 2026-27 interim (fuel) update | Caltrans | Sep 1 2026-Mar 31 2027 | https://dot.ca.gov/-/media/dot-media/programs/construction/documents/equipment-rental-rates-and-labor-surcharge/book_26_27_intv2.pdf | Updated delay/OT factors
CALT-26V3 | Caltrans Equipment Rental Rates book 26v3 | Caltrans | Apr 1-Aug 31 2026 | https://dot.ca.gov/-/media/dot-media/programs/construction/documents/equipment-rental-rates-and-labor-surcharge/book_26v3.pdf | Category codes and size bands (taxonomy)
CATFUEL22 | Cat Performance Handbook fuel consumption tables (VisionLink) | Caterpillar via Wheeler Cat | 9 Dec 2022 | https://wheelercat.com/wp-content/uploads/2023/01/Cat-Performance-Handbook-from-VST-fuel-consumption-2022-12-09T21-20-09.pdf | Fuel gal/hr low/med/high by model
CATPHB46 | Cat PHB Ed. 46 s.25-9 dozer fuel table | Caterpillar | Ed. 46 | https://static1.squarespace.com/static/58877529414fb5283ed14a6b/t/58921922893fc04d5f058f32/1485969698763/Fuel+Table+-+Dozers.pdf | Older dozer fuel ranges; load definitions
CATPHB50 | Cat Performance Handbook Ed. 50 (front matter only) | Caterpillar | Jun 2022 | https://wheelercat.com/wp-content/uploads/2025/03/Cat-Performance-Handbook-Edition-50-June-2022.pdf | 100% efficiency basis; section locations (curves NOT retrieved)
EIA-HIST | EIA US No.2 diesel retail price, annual | US EIA | 2018-2025 | https://www.eia.gov/dnav/pet/hist/LeafHandler.ashx?n=PET&s=EMD_EPD2D_PTE_NUS_DPG&f=A | 2025 avg $3.660 used for FEMA back-out
EIA-GDU | EIA Gasoline and Diesel Fuel Update | US EIA | week of Oct 19 2026 (rel. Oct 20 2026) | https://www.eia.gov/petroleum/gasdiesel/ | US/PADD diesel and gasoline prices
EW-STBY | EquipmentWatch: Standby rates | EquipmentWatch | accessed Oct 2026 | https://equipmentwatch.com/resource/standby-rates/ | 176 hr/month FHWA basis; standby components
EW-TIME | EquipmentWatch: Calculating time basis of rates | EquipmentWatch | accessed Oct 2026 | https://equipmentwatch.com/resource/calculating-time-basis-of-rates/ | 8/40/176 hr basis; overtime 1/8,1/40,1/176
EW-FHWA | EquipmentWatch: FHWA rate | EquipmentWatch | mod. Sep 9 2024 | https://equipmentwatch.com/resource/fhwa-rate/ | Regional adjustment applies to ownership only
EW-REG | EquipmentWatch: Regional adjustments | EquipmentWatch | undated | https://equipmentwatch.com/?p=30581 | State multipliers 82.2%-142.7% (crawler excavators)
W25 | Wheeler Machinery / Cat Rental Store 2025 Rental Rates (UT) | Wheeler Machinery | 2025 (Mar 2025) | https://wheelercat.com/wp-content/uploads/2025/03/2025-Construction-Equipment-Rental-Rates.pdf | Bare day/week/4-week (8/40/176 hr); haulage; protection 16%
C25 | Columbus Equipment rental rate sheet 2025 REVISED 6.25 (OH) | Columbus Equipment | Jun 2025 | https://www.columbusequipment.com/wp-content/uploads/2025/09/CER-Rental-Rate-Sheet-2025_REVISED-6.25.pdf | Bare day/week/4-week (8/40/160); terms
B25 | Burris Equipment (Alta) Rental Rate Guide (IL) | Burris Equipment | Mar 2025 | https://burris-media-cloud.s3.us-west-2.amazonaws.com/2025/03/Rental-Rate-Guide-Printable.pdf | Bare day/week/4-week (8/40/160)
R25 | RTL Equipment Rate Sheet Spring 2025 (MN) | RTL Equipment | Spring 2025 | https://www.rtlequipment.com/fckimages/rtlequipment-RentalRateSheet-2025.pdf | Bare day/week/month
N25 | Nu-Way Winter 2025 rental rates (MO) | Nu-Way | eff. Jan 22 2025 | https://nuwayinc.com/Uploaded/Catalog/PDF/rentalrates_January2025.pdf | Bare day/week/month
A26 | Ahearn Rents rates page (MA/RI/NH) | Ahearn Rents | undated; read Oct 2026 | https://ahearnrents.com/rates/ | Bare day/week/month
DOZR-EX | DOZR excavator rental cost guide | DOZR | Mar 2026 | https://dozr.com/blog/excavator-rental-cost | Marketplace ranges; delivery; LDW 10-15%
DOZR-TH | DOZR telehandler rental cost guide | DOZR | Mar 2026 | https://dozr.com/blog/telehandler-rental-cost | Telehandler ranges; delivery
DOZR-DZ | DOZR dozer rental cost guide | DOZR | Mar 2026 | https://dozr.com/blog/dozer-rental-cost | All-size dozer average
DOZR-SS | DOZR skid steer rental cost guide | DOZR | Jul 2023 | https://dozr.com/blog/skid-steer-rental-cost | Older cross-check
DOZR-SC | DOZR scissor lift rental cost guide | DOZR | Mar 2026 | https://dozr.com/blog/scissor-lift-rental-cost | Scissor ranges; delivery
DOZR-BM | DOZR boom lift rental cost guide | DOZR | Mar 2026 | https://dozr.com/blog/boom-lift-rental-cost | Boom ranges; towable; delivery
RENTD | rentd.com air compressor rental guide | rentd | Jul 2026 | https://www.rentd.com/air-compressor-rental/ | Compressor ranges; delivery
ANGI | Angi excavator rental prices | Angi | Oct 19 2026 | https://www.angi.com/articles/excavator-rental-prices.htm | Consumer ranges; delivery
NTXC | North Texas Crane 2025 rate sheet | North Texas Crane | 2025 | https://www.northtexascrane.com/siteart/pdf/2025-Crane-Rental-Rate-Sheet-1.pdf | Operated crane $/hr, minimums, terms
DEPC | Dependable Crane pricing (Sacramento CA) | Dependable Crane | mod. Oct 2025 | https://dependablecrane.com/pricing/ | Operated crane $/hr, minimums
CFCS | Central Florida Crane Service rate benchmarks | CFCS | Jun 4 2026 | https://centralfloridacraneservice.com/feeds/blog/crane-rental-rates-operator | Operated crane bands; minimums; OT
BIGR-CR | BigRentz crane rental cost | BigRentz | Apr 27 2026 | https://www.bigrentz.com/blog/crane-rental-cost | Crane ranges; tower crane monthly
CPO | Concrete Pumping Ohio rental rates | Concrete Pumping Ohio | undated; read Oct 2026 | https://concretepumpingohio.com/rental-rates/ | Operated pump $/hr, $/yd3, travel
CCE | CCE News concrete pump rental cost USA | CCE News | Mar 23 2026 | https://cceonlinenews.com/concrete/concrete-pump-rental-cost-usa/ | Pump ranges, minimums, surcharges
MNDLI | MN DLI Region 1 minimum truck rental rates (with driver) | Minnesota DLI | Dec 22 2025 / May 1 2026 | https://www.dli.mn.gov/business/employment-practices/prevailing-wage-region-1-minimum-truck-rental-rates | Operated dump truck $/hr
DTR | dumptruckrates.com tri-axle | dumptruckrates.com | Sep 23 2026 | https://dumptruckrates.com/trucks/tri-axle-dump-truck/ | Operated dump truck $85-130/hr
PRICER-OT | ThePricer office trailer rental costs | ThePricer | Oct 1 2026 | https://www.thepricer.org/office-trailer-rental-costs/ | Office trailer $/mo; delivery
BNB-CONT | Boom & Bucket storage container cost | Boom & Bucket | Mar 27 2025 | https://www.boomandbucket.com/es/blog/cost-of-storage-containers | Container $/mo; delivery
PRICER-FN | ThePricer temporary fence rental cost | ThePricer | Jun 30 2026 | https://www.thepricer.org/temporary-fence-rental-cost/ | Fence $/lf/mo; gates; delivery
EQNB | EquipNearby generator rental guide | EquipNearby | Sep 16 2026 | https://equipnearby.com/guides/generator-rental-guide/ | Generator ranges; delivery $125-400
FAT19 | Florida Air Tool rate sheet (EXCLUDED, 2019) | Florida Air Tool | 06/06/2019 | https://floridaairtool.com/rate-sheet/ | Shift multipliers only; rates outdated
URI-TERMS | United Rentals US Rental Service Terms | United Rentals | accessed Oct 2026 | https://www.unitedrentals.com/legal/rental-service-terms-us | 8/40/160 basis; shifts 1.5x/2x; env. fee 2% cap $99
COSTARS | PA COSTARS Sunbelt not-to-exceed rate list | PA DGS / Sunbelt Rentals | 3/15/2023-3/14/2024 | https://www.dgs.internet.state.pa.us/COSTARSElecBiddAdmin/Supplier/DownloadCustomList/4586 | Aerial lift day/week/4-week by class
KS18 | Kansas DOA rate list (EXCLUDED, 2018) | Kansas Dept. of Administration | thru 10/31/2018 | https://admin.ks.gov/media/cms/1d10fe2c-549f-493b-939a-45bd1482fc2d.pdf | Class names only; rates too old
BIGR-SC | BigRentz scissor lift rental cost (23 cities) | BigRentz | data Dec 2022 | https://www.bigrentz.com/blog/scissor-lift-rental-cost | Scissor means
BIGR-BM | BigRentz boom lift rental cost (23 cities) | BigRentz | data Dec 2022 | https://www.bigrentz.com/blog/boom-lift-rental-cost | Boom means
SCAFEX | ScaffoldExchange aerial lift rental cost | ScaffoldExchange | Sep 26 2026 | https://scaffoldexchange.com/lifts-and-access/aerial-lift-rental-cost | 2026 aerial ranges; delivery
LIFTINC | Lift Inc. Genie slab & RT scissor catalog | Lift Inc. | accessed Oct 2026 | https://www.liftincorporated.adpearance.com/catalog/aerial-and-material-handling-equipment/scissor-lifts/slab-scissor-lifts | Scissor specs
LEPCO | Lepco Rents Genie/JLG boom catalog | Lepco Rents | accessed Oct 2026 | https://lepporents.adpearance.com/catalog/access-equipment/boom-lifts | Boom specs
JLG600 | JLG 600 Series spec sheet | JLG | A92.20 | https://cdn2.antbuildz.com/images/600%20Series%20Spec%20Sheet%20A9220%20Compliant.pdf | 600S/660SJ specs
JLG-A92 | JLG new terminology ANSI/CSA | JLG | accessed Oct 2026 | https://www.jlg.com/en/directaccess/new-terminology-in-the-ansi-and-csa-standards | MEWP groups/types
FM5434 | US Army FM 5-434 Earthmoving Operations | US Army | Jun 2000 | https://vulcanhammer.net/wp-content/uploads/2017/01/fm5_434.pdf | Production method, factors, clearing, scraper, soil conversion
FM5434-8 | FM 5-434 Ch.8 Excavators | US Army | Jun 2000 | https://www.globalsecurity.org/military/library/policy/army/fm/5-434/chap8.pdf | Hoe cycle times, fill factors
FM5434-11 | FM 5-434 Ch.11 Soil processing & compaction | US Army | Jun 2000 | https://pdf4pro.com/view/soil-processing-and-compaction-sweethaven02-com-152702.html | Water formulas
USMC-PE | USMC Production Estimations instructor outline | USMC | accessed Oct 2026 | https://www.trngcmd.marines.mil/Portals/207/Docs/FLW/PRODUCTION%20ESTIMATIONS%20(Proposed%20Instructor%20Outline).pdf | Soil conversions, operator factors, RR, scraper
KSU-2 | KSU CE419 Ch.2 (Peurifoy-based) | King Saud Univ. | accessed Oct 2026 | https://faculty.ksu.edu.sa/sites/default/files/2.CE419_Ch2_0.pdf | Production equation; swell/shrink
KSU-3 | KSU CE419 Ch.3.1 excavators | King Saud Univ. | accessed Oct 2026 | https://faculty.ksu.edu.sa/sites/default/files/3.CE419-Ch3.1.pdf | Excavator production equation
KSU-4 | KSU CE419 Ch.4.2 dozers | King Saud Univ. | accessed Oct 2026 | https://faculty.ksu.edu.sa/sites/default/files/4.CE419-Ch4.2.pdf | Dozer blade/cycle method; speeds 4/8 km/h; fixed 0.05 min
KSU-T3 | KSU Tutorial 3 | King Saud Univ. | accessed Oct 2026 | https://fac.ksu.edu.sa/sites/default/files/Tutorial%203.pdf | Trench factor 0.95-1.0; fill factors
KSU-T5 | KSU Tutorial 5 | King Saud Univ. | accessed Oct 2026 | https://faculty.ksu.edu.sa/sites/default/files/Tutorial%205.pdf | Truck/loader balancing
KSU-T6 | KSU Tutorial 6 | King Saud Univ. | accessed Oct 2026 | https://fac.ksu.edu.sa/sites/default/files/tutorial%206.pdf | Travel time; effective grade; scrapers
KSU-T7 | KSU Tutorial 7 | King Saud Univ. | accessed Oct 2026 | https://fac.ksu.edu.sa/sites/default/files/Tutorial%207.pdf | Compaction 16.3 formula; grader passes
KSU-EQ | KSU CE417 list of equations | King Saud Univ. | accessed Oct 2026 | https://fac.ksu.edu.sa/sites/default/files/list_of_equations_for_ce_417.pdf | Loader/truck/compaction equations
CAT-FILL | Cat: Bucket fill factors | Caterpillar | accessed Oct 2026 | https://www.cat.com/en_US/articles/ci-articles/bucket-fill-factors.html | Fill factors
CAT-WL | Cat: How to calculate wheel loader productivity | Caterpillar | accessed Oct 2026 | https://www.cat.com/en_US/articles/for-owners/how-to-calculate-cat-wheel-loader-productivity.html | Basic cycle 27-33 s; 50-min hour
CAT-MG | Cat: Measure your motor grader productivity | Caterpillar | accessed Oct 2026 | https://cat.com/en_US/articles/for-owners/measure-your-motor-grader-productivity.html | Grader area formula, speeds, effective blade
OEP | Open Exam Prep PE Construction: equipment production | Open Exam Prep | accessed Oct 2026 | https://open-exam-prep.com/study-guides/pe-construction/operations-and-methods/equipment-selection-production | Cycle components; truck fleet example
GEOM | Geometrics S-TR15 rippability | Geometrics | accessed Oct 2026 | https://www.geometrics.com/wp-content/uploads/2018/10/S-TR15.pdf | Indicative ripping BCY/hr vs seismic velocity
MST-GE441 | Missouri S&T GE441 compaction lecture | Missouri S&T | accessed Oct 2026 | https://web.mst.edu/rogersda/umrcourses/ge441/online_lectures/compaction/GE441-Lecture2-7.pdf | Roller selection; trench lifts
ATE-PLATE | ATE TP-1830H plate compactor spec | Jamieson Equipment | accessed Oct 2026 | https://catalog.jamiesonequipment.com/printitem/all-categories-vibrators-plate-compactor-vibrators/ate-compactors-tp-series-vibrator-plate-compactors/tp-1830h | 8,550 ft2/hr, 13 in depth, 465 lb
STORMW | Stormwater: How to select a soil roller | Stormwater | accessed Oct 2026 | https://stormwater.com/bmps/article/13004765/how-to-select-a-soil-roller | 1 impact per inch; 1,200-2,500 vpm
CPUC-WATER | CPUC ELM PEA App. M water usage | CPUC | accessed Oct 2026 | https://files.cpuc.ca.gov/Environment/info/aspen/elm/pea/vol8_apx_m_water_usage.pdf | 38.75 gal/CY; dust control gal/acre/day
EDUREV | EduRev PE Civil formula sheet (secondary) | EduRev | accessed Oct 2026 | https://edurev.in/t/516184/Formula-Sheet-Construction-Methods | E 0.75-0.90; passes 4-6; swell ranges
CIVILS | civils.ai soil bulking/swell factor (secondary) | civils.ai | accessed Oct 2026 | https://civils.ai/free-construction-estimating-software/soil-bulking-swell-factor | Bulking/shrinkage ranges
WISDOT | WisDOT FDM 19-10-30 production rate table | WisDOT | 12/2/2022 | https://www.wisconsindot.gov/Documents/doing-bus/eng-consultants/cnslt-rsrces/tools/estimating/production-rate-table.pdf | Field daily rates (median = typical)
TXDOT | TxDOT Construction Production Rates | TxDOT | Mar 12 2024 | https://ftp.txdot.gov/pub/txdot/cst/cst-production-rates.pdf | Low/Med/High daily rates
WSDOT | WSDOT M 22-31.10 Appendix 6 | WSDOT | Feb 2023 | https://appstest.wsdot.wa.gov/publications/manuals/fulltext/M22-31/Appendix6.pdf | Per 8-hr day rates
NCDOT | NCDOT Contract Time Guidelines | NCDOT | structures rev. Jan 5 2016 | https://connect.ncdot.gov/letting/Division%20Letting%20Resources/Contract%20Time%20Guidelines.pdf | Per working day rates
FHWA-CFL | FHWA Central Federal Lands contract time guidelines | FHWA | accessed Oct 2026 | https://highways.dot.gov/sites/fhwa.dot.gov/files/docs/federal-lands/pddm/cfl/27321/cfl_guidelines.pdf | HACP 1,320-1,980 TON/day
PSU-SP | Penn State Superpave Constructing Quality Asphalt Pavements booklet | Penn State / PennDOT | 2025 | https://www.superpave.psu.edu/assets/docs/2025/Constructing-Quality-Asphalt-Pavements-Checklist-Booklet-2025-FINAL.pdf | Paver/roller/truck worked example; yield
AI-ROLL | Asphalt Institute FAQ: how many rollers | Asphalt Institute | accessed Oct 2026 | https://www.asphaltinstitute.org/faq/how-many-rollers-are-required/ | Roller speed <=3 mph; spreads
CAT-PM310 | Cat PM310 cold planer product page | Caterpillar | accessed Oct 2026 | https://www.cat.com/en_US/products/new/equipment/cold-planers/cold-planer/227227255583048.html | 39.4 in width; max 108 fpm
FCP-CONC | ForConstructionPros: Placing concrete smarter | ForConstructionPros | accessed Oct 2026 | https://www.forconstructionpros.com/concrete/article/21006661/placing-concrete-smarter | Placement CY/hr by method
ACI-S21 | ACI webinar S21 (Connolly) pumping | ACI | accessed Oct 2026 | https://www.concrete.org/portals/0/files/pdf/webinars/ws_S21_Connolly.pdf | Rated pump ~133 CY/hr; boom 24-42 m
RER-TROWEL | RER: Trowel power | Rental Equipment Register | 2002 | https://www.rermag.com/mag/article/20938274/trowel-power | Trowel SF/day (dated)
DRILLER-BP | The Driller: Bore planning | The Driller | accessed Oct 2026 | https://thedriller.com/articles/86303-bore-planning | HDD pullback example; fluid
DRILLER-SZ | The Driller: What size HDD rig | The Driller | accessed Oct 2026 | https://thedriller.com/articles/85848-what-size-hdd-rig | HDD classes by pullback
GTI-VAC | GTI vacuum excavation project update | GTI Energy | Spring 2019 | https://www.gti.energy/wp-content/uploads/2019/04/08-KeyholeSpring2019-GTI-OTD-Vacuum-Excavation-Project-Update-Presentation.pdf | Vac-ex ft3/min
CLEANER-PB | Cleaner.com: complementary pipe bursting rigs | Cleaner | Jun 2016 | https://www.cleaner.com/online_exclusives/2016/06/complementary_pipe_bursting_rigs_boost_contractors_productivity | Bursting LF/day
VTT-CRANE | IAARC/VTT: crane operations study | IAARC | accessed Oct 2026 | https://www.iaarc.org/publications/fulltext/An_integrated_approach_to_the_development_of_construction_site_crane_operations.PDF | Tower crane lift times; 70-75% effective
PROJUL | Projul heavy haul equipment transport guide | Projul | Oct 8 2025; mod. Mar 21 2026 | https://projul.com/blog/construction-heavy-haul-equipment-transport-guide/ | Trailer types; legal envelope; escorts
OTR-LOW | OTrucking lowboy trucking rates guide | OTrucking | Feb 20 2026; upd. Sep 1 2026 | https://otrucking.com/resources/guides/lowboy-trucking-rates/ | Lowboy $/mi, minimums, permits, escorts
OTR-RGN | OTrucking RGN trailer rates guide | OTrucking | Feb 20 2026; upd. Sep 1 2026 | https://otrucking.com/resources/guides/rgn-trailer-rates/ | RGN $/mi by permit class; escorts; surveys
OTR-HOT | OTrucking hotshot rates per mile | OTrucking | Feb 20 2026; upd. Oct 4 2026 | https://otrucking.com/resources/guides/hotshot-trucking-rates-per-mile/ | Hotshot $/mi; local flat
DAT-0926 | DAT truckload rates Sept 2026 | DAT | Oct 13 2026 | https://www.dat.com/company/news-events/news-releases/dat-truckload-rates-rise-in-september-as-diesel-tops-6-a-gallon | Flatbed spot $3.61/mi incl. fuel
TXDMV | TxDMV general single trip permit | Texas DMV | accessed Oct 2026 | https://www.txdmv.gov/motor-carriers/oversize-overweight-permits/general-single-trip | Permit fee schedule
CFR658 | 23 CFR 658.17 weight limits | US Code of Federal Regulations | current | https://www.law.cornell.edu/cfr/text/23/658.17 | 80,000 lb gross; axle limits
RITCHIE-336 | RitchieSpecs Cat 336D L | RitchieSpecs | accessed Oct 2026 | https://www.ritchiespecs.com/model/caterpillar-336d-l-hydraulic-excavator | Transport width 133.5 in
CALT-MOB | Caltrans contract cost memo (mobilization) | Caltrans | Feb 17 2006 | https://sv08data.dot.ca.gov/contractcost/memo.pdf | Mobilization ~10% of contract (sanity check)
RSM-IL25 | RSMeans 2025 City Cost Index, Illinois (student upload) | Gordian/RSMeans via CliffsNotes | 2025 | https://www.cliffsnotes.com/study-notes/28519784 | 015433 equipment vs installation index
GORDIAN | Gordian City Cost Index page | Gordian | accessed Oct 2026 | https://www.gordian.com/resources/city-cost-index/ | CCI basket incl. 6 equipment items
CARTER | Carter Machinery: Cat dozers new names | Carter Machinery | accessed Oct 2026 | https://cartermachinery.com/uncategorized/cat-dozers-new-names-same-great-performance/ | D1-D11 classes
ZIEGLER | Ziegler Cat new equipment pages (dozers, excavators, loaders, graders, backhoes, compactors, pavers, telehandlers) | Ziegler Cat | accessed Oct 2026 | https://www.zieglercat.com/equipment/new/dozers | Model specs: HP, weight, bucket, widths
CAT-HAUL | Cat hauling resources | Caterpillar | accessed Oct 2026 | https://www.cat.com/en_US/by-industry/cross-industry-resources/hauling.html | ADT/rigid/scraper capacities
BOBCAT-EX | Bobcat compact excavator buyer's guide | Bobcat | accessed Oct 2026 | https://www.bobcat.com/na/en/buying-resources/excavators/compact-excavator-buyers-guide/sizes-specifications | Mini ex classes; tail swing
URI-CAT | United Rentals catalog pages (mini ex sizes, earthmoving, compaction, trench safety, telehandlers) | United Rentals | accessed Oct 2026 | https://www.unitedrentals.com/marketplace/equipment/earthmoving-equipment | Class structure
SKIDSTEERS | SkidSteers.com sizes / DOZR spec guide | SkidSteers.com; DOZR | accessed Oct 2026 | https://www.skidsteers.com/blog/skid-steer-sizes/ | ROC breakpoints
CRANE-TYPES | AllCrane and SANY crane type ranges | AllCrane; SANY | accessed Oct 2026 | https://www.allcrane.com/resources/case-study/article/all-terrain-crane-vs.-truck-crane-vs.-boom-truck | Crane capacity ranges by type
PUTZ | Putzmeister truck-mounted pumps | Putzmeister | accessed Oct 2026 | https://www.putzmeister.com/web/middle-east/products/-/product-navigation/truck_mounted-concrete-pumps | Boom pump families
ONECREW | OneCrew asphalt milling machine guide | OneCrew | accessed Oct 2026 | https://www.getonecrew.com/post/asphalt-milling-machine | Cold planer classes
DIESEKO | Dieseko Group vibratory hammers | Dieseko | accessed Oct 2026 | https://diesekogroup.com/vibratory-hammers/ | Eccentric moment 14-500 kgm
EIFFEL | Eiffel Trading: 4 types of pile hammers | Eiffel Trading | accessed Oct 2026 | https://eiffeltrading.com/blog/post/eiffel-101-4-types-of-pile-driving-hammers | Hammer types
MODOT | MoDOT EPG 237.8 contract time | MoDOT | accessed Oct 2026 | https://epgtest.modot.org/files/a/a3/237.8_Contract_Time_Determination.pdf | Working day definition
PROFILE-HS | Profile Products 800-gal hydroseeder calibration | Profile Products | Mar 2026 | https://www.profileproducts.com/wp-content/uploads/2026/03/hydroseeder-calibration-sheet-800gal.pdf | SF per tank
FJD | FJ Dynamics mini excavator rental cost | FJ Dynamics | Apr 25 2025 | https://www.fjdynamics.com/blog/industry-insights-65/mini-excavator-rental-cost-539 | Mini ex delivery $50-150
FHWA-86 | FHWA memo on USACE schedule | FHWA | Aug 22 1986 | https://www.fhwa.dot.gov/construction/contracts/860822.cfm | USACE schedule accepted without modification
RER-2001 | RER: All over the place (regional rates) | Rental Equipment Register | Feb 1 2001 | https://www.rermag.com/mag/article/20932580/all-over-the-place | Regional rental volatility (anecdotal)
ODOT624 | Ohio DOT Item 624 mobilization | ODOT | 2013 CMS | https://www.dot.state.oh.us/Divisions/ConstructionMgt/OnlineDocs/Specifications/2013CMS/600/624.htm | Mobilization payment caps
ASPHCALC | asphaltcalculator.me equipment rental (aggregator, low quality) | asphaltcalculator.me | 2026 undated | https://asphaltcalculator.me/cost-estimator/equipment-rental | Paver/miller/roller day ranges
CTR-4416 | TxDOT CTR 0-4416-1 measured rates (NOT RETRIEVED) | UT Austin CTR | n/a | https://library.ctr.utexas.edu/ctr-publications/0-4416-1.pdf | Gap: field-observed rates
WYDOT-RIP | WYDOT rock rippability research proposal | WYDOT | accessed Oct 2026 | https://www.dot.state.wy.us/files/live/sites/wydot/files/shared/Planning/Research/Rock%20Rippability.pdf | Limits of seismic rippability charts
CE-TRENCH | Construction Equipment: trencher set and speed | Construction Equipment | accessed Oct 2026 | https://www.constructionequipment.com/refine-set-and-speed-profitable-trencher-production | Trencher operating guidance (no LF/hr)
SUNBELT-19 | Sunbelt 19 ft scissor page | Sunbelt Rentals | accessed Oct 2026 | https://www.sunbeltrentals.com/equipment-rental/0070025/19-electric-scissor-lift/ | Spec; quote-only pricing
KFUPM | KFUPM CE353 Ch.4 compaction | KFUPM | accessed Oct 2026 | https://faculty.kfupm.edu.sa/ce/nshayea/CE353-071/CE353CH4.pdf | Typical lift range 6-18 in
ASCE-HDD | ASCE Pipelines: HDD productivity case study (paywalled) | ASCE | 2013 | https://ascelibrary.com/doi/10.1061/9780784412480.079 | Gap: HDD rates by soil
DEERE-135P | Deere 135 P-Tier excavator spec | Deere | accessed Oct 2026 | https://www.deere.com/assets/pdfs/common/products/sync/ME135PAJ-135-p-tier-excavator.pdf | HD buckets 0.47-0.99 yd3; 20 ft dig
DEERE-210P | Deere 210 P-Tier excavator spec | Deere | accessed Oct 2026 | https://www.deere.com/assets/pdfs/common/products/sync/ME210PAU-210-p-tier-excavator.pdf | Buckets 0.56-1.29 yd3; 21'11" dig
DEERE-345P | Deere 345 P-Tier excavator spec | Deere | accessed Oct 2026 | https://www.deere.com/assets/pdfs/common/products/sync/ME345PAJ-345-p-tier-excavator.pdf | Buckets 1.11-2.09 yd3
DEERE-350P | Deere 350 P-Tier excavator spec | Deere | accessed Oct 2026 | https://www.deere.com/assets/pdfs/common/products/excavators/350-p-tier-mid-size-excavator-me350mau.pdf | HD buckets 1.37-2.27 yd3
KOM-PC360 | Komatsu PC360LC-11 spec (dealer-hosted) | Komatsu | accessed Oct 2026 | https://www.companywrench.com/PDF/KOMATSU_PC360LC-11_SPECS.pdf | Buckets 0.89-2.56 yd3
ALLMACH-PC88 | AllMachines Komatsu PC88MR-11 (aggregator) | AllMachines | accessed Oct 2026 | https://www.allmachines.com/excavators/komatsu-pc88mr-11 | Bucket 0.26 yd3; 15 ft dig
DEERE-35G | Deere 35G compact excavator spec | Deere | accessed Oct 2026 | https://www.deere.com/assets/pdfs/common/products/sync/DKAXG35-35G-compact-excavator.pdf | Spec-basis bucket 0.11 m3 (0.15 yd3); 10 ft dig
DEERE-RENT | Deere rental product comparison | Deere | accessed Oct 2026 | https://www.deere.com/assets/pdfs/common/products/sync/DKCOMPREN-rental-product-comparison.pdf | Dig depths; backhoe/dozer specs
DEERE-FLEET | Deere construction equipment fleet sheet | Deere | accessed Oct 2026 | https://www.deere.com/assets/pdfs/common/industries/construction/john-deere-construction-equipment-fleet-sheet-dkeceflt.pdf | Loader buckets; ROC; ADT heaped
CAT-EXC-PG | cat.com / Ziegler excavator pages (303.5 CR, 305 CR, 320, 336, 352, 374, 395) | Caterpillar | accessed Oct 2026 | https://www.cat.com/en_US/products/new/equipment/excavators/large-excavators/126440.html | Dig depths; example SD buckets 374 4.32 / 395 6.8 yd3
CAT-DOZ-PG | cat.com dozer pages D1-D11 (+ Western States D2) | Caterpillar | accessed Oct 2026 | https://www.cat.com/en_US/products/new/equipment/dozers/large-dozers/115080.html | SAE J1265 blade capacities; gear speeds D9-D11; D1-D3 max speeds
CAT-420 | cat.com Cat 420 backhoe loader | Caterpillar | accessed Oct 2026 | https://www.cat.com/en_US/products/new/equipment/backhoe-loaders/center-pivot-backhoe-loaders/101260.html | Loader MP bucket 1.25 yd3; 14 ft dig; speeds
CAT-WL-PG | Cat wheel loader pages (906 Cleveland Bros, 950 GC, 950, 980 GC, 988) | Caterpillar | accessed Oct 2026 | https://cat.com/en_US/products/new/equipment/wheel-loaders/medium-wheel-loaders/1000029532.html | Bucket ranges; gear speeds
CARLETON-BKT | Carleton Equipment Bobcat heavy-duty bucket | Carleton Equipment | accessed Oct 2026 | https://carletonequipment.com/products/bucket-heavy-duty-bobcat | SSL/CTL bucket heaped yd3 by width
CAT-SCR-PG | cat.com scraper pages (621, 623, 631, 637, 657) | Caterpillar | accessed Oct 2026 | https://www.cat.com/en_US/products/new/equipment/wheel-tractor-scrapers/open-bowl-scrapers/125862.html | Heaped yd3, rated load lb, loaded top speed
CAT-TRK-PG | Cat 725 (Cleveland Bros), 745, 772, 773, 777 pages | Caterpillar | accessed Oct 2026 | https://www.cat.com/en_US/products/new/equipment/articulated-trucks/three-axle-articulated-trucks/1000032934.html | Payload, heaped SAE 2:1, top speed
VOLVO-ADT | Volvo A25G guide, A35G/A40G brochure, US hauler lineup | Volvo CE | accessed Oct 2026 | https://volvoce.com/united-states/en-us/products/articulated-haulers | Payload and heaped yd3
CTOS-DUMP | Custom Truck One Source tandem-axle dump | Custom Truck One Source | accessed Oct 2026 | https://www.customtruck.com/rental/vocational-trucks/dump-trucks/tandem-axle-16-cu-yd-rear-dump-truck/751-0200 | Tandem dumps 10-16 yd3
TRUXNOW | TruxNow dump truck fuel blog (low reliability) | TruxNow | accessed Oct 2026 | https://www.truxnow.com/blog/dump-truck-fuel-consumption | Class 8 dump ~3.2 / 6.2 gal/hr
CAT-GR-PG | Cat 140 (cat.com), 160 (Milton Cat), 16 (cat.com) grader pages | Caterpillar | accessed Oct 2026 | https://www.cat.com/en_US/products/new/equipment/motor-graders/motor-graders/18346813.html | Moldboard, weight, gear speeds
CAT-CMP-PG | Cat compactor pages (CS34 Toromont, CS44B, CS56B Cleveland Bros, CP56B, CS10 GC, CB2.7, CB10, CW34) | Caterpillar | accessed Oct 2026 | https://www.cat.com/en_US/products/new/equipment/compactors/vibratory-soil-compactors/18558720.html | Drum widths, weights, max speeds
RB-HMA | Roads & Bridges: Compacting HMA pavements Part II | Roads & Bridges | accessed Oct 2026 | https://www.roadsbridges.com/compacting-hot-mix-asphalt-pavements-part-ii | HMA roller working speeds 2.5-4 mph
WN-WP1550 | Wacker Neuson WP1550AW plate (Cleveland Bros) | Wacker Neuson | accessed Oct 2026 | https://www.clevelandbrothers.com/products/753750-wp-1550aw | 19.5 in, 100 ft/min, 9,750 ft2/hr, 194 lb
WN-BS60 | Wacker Neuson BS60-4As rammer data sheet | Wacker Neuson | accessed Oct 2026 | https://wackerneuson.com/media/contentserv/464010.pdf | 28.9 ft/min, ~1,590 ft2/hr, 0.26 gal/hr, 159 lb
GEN-SHEETS | Generator spec sheets: Atlas Copco QAS 25-45/150-200/250-330/625; Generac MDG75/100/150/250 | Atlas Copco; Generac | accessed Oct 2026 | https://www.atlascopco.com/content/dam/atlas-copco/local-countries/united-states/documents/ptna-usa/generators/QAS%20150-200%20JD%20T4F%20Product%20Reference.pdf?.html | gal/hr at 25/50/75/100% load
COMP-SHEETS | Compressor spec sheets: Sullair 185/375/1600H-900XHH; Doosan XHP750/1170; Leppo P185/HP1600 | Sullair; Doosan | accessed Oct 2026 | https://america.sullair.com/sites/default/files/2026-08/LIT_185%20Brochure_en.pdf | Full-load gal/hr
LT-SHEETS | Light tower specs: Generac MLT6SMDS; Allmand NLV | Generac; Allmand | accessed Oct 2026 | https://apelectric.com/content/PDF/Generac/mlt6smds_spec_sheet.pdf | gal/hr lights-only to 100%
AMT-5588 | AMT/Depco 5588-D6 6 in diesel trash pump spec | Depco/AMT | accessed Oct 2026 | https://www.depcopump.com/datasheets/amt/5588-D6_Spec_Sheet.pdf | 20 gal tank / 12 hr = ~1.7 gal/hr (derived)
CAT-PM620 | Cat PM620 key features | Caterpillar | 2021 | https://www.zeppelin.cz/fileadmin/helios_files/JPG/ToM/Cold_Planer_PM/PM620/PM620-02B_QEHQ2722-01_Key_Features_2021.pdf | 79.1 in width, 630 hp
SUNBELT-LLA | Sunbelt Rentals electric scissor size bins (incl. Low-Level Access) | Sunbelt Rentals | accessed Oct 2026 | https://www.sunbeltrentals.com/equipment-rental/0070025/19-electric-scissor-lift/ | LLA 1-5, 6-10, 11-15 ft bins

## Gaps
# | Area | Gap / weakness | Impact on catalog | Recommended way to close | Priority
1 | Production | Cat Performance Handbook dozer push curves; D4 blade capacity; D5-D8 gear speeds and Komatsu dozer specs | Dozer push/strip/spread rows are first-principles (C) using Cat SAE blade capacities; D4, D6 XE, wheel dozers stay D | License Cat PHB Ed. 50 (s.16) or Komatsu Specs & Application Handbook | High
2 | Production | Average haul road speeds (truck, ADT, scraper); Cat rimpull/retarder curves; Cat PHB s.8 fixed times | All haul and scraper production rows blank until Settings B22-B27 are entered (capacities now filled) | Cat PHB s.21 charts, Volvo application guides, or contractor GPS telematics; or estimator default speeds | High
3 | Production | Mini (1-2, 5-6 t) and 9-10 t, 45-50 t bucket ranges; Cat 320/336/352 bucket tables; hoe bucket for backhoes; Peurifoy swing-depth table; Cat cycle charts; cycle time above 2.5 CY | Those rows stay D; large-bucket rows use the 15 s FM cycle (optimistic) | Dealer bucket charts; Cat spec PDFs; license Peurifoy / Cat PHB s.5 | High
4 | Production | Trencher LF/hr, saw-cut LF/hr, breaker CY/hr, drilling ft/hr, buggy, laser screed, proof-roll, sweeper, rammer | Those rows are D | RSMeans crew daily outputs (license); manufacturer data; IntelCost historical jobs | Medium
5 | Production | RSMeans daily outputs; TxDOT CTR 0-4416-1 measured rates (blocked) | No crew-level cross-check beyond DOT tables | RSMeans license; retrieve CTR 0-4416-1 | Medium
6 | Owned rates | USACE EP 1110-1-8 regional dollar tables (12 regions) and Local Area Factors | No ownership/operating split; no regional owned rates | Download EP 1110-1-8 Vols 1-12 from nww.usace.army.mil when reachable | High
7 | Owned rates | EquipmentWatch / Blue Book (subscription) | No owned rates for classes FEMA lacks (scissors, telescopic booms, ADTs, rigid trucks, many attachments) | EquipmentWatch subscription | High
8 | Owned rates | FEMA rows not reliably extracted (8573 Cat 450, water trucks 8780/8781/8614, trash pumps 8465-8468, distributors 8580-8583, sweepers, welders, hydroseeders, trenchers 8650-8653, many codes listed as 'Rate not captured') | Those rows carry FEMA_code with blank rate (D) | Open the official FEMA 2025 PDF/XLSX and key the missing rows | High
9 | Owned rates | FEMA ⚠ suspect values (generators 17-45 kW non-monotonic; pickups non-monotonic; BW120 < BW100; 13 CY mixer 3x 11 CY; pumps $3.86-5.35/hr; 12 in pump $4.75; 125 ft boom; V120 trencher $286; 19 in chipper < 15 in; 130 CFM > 175 CFM) | Kept as published and flagged | Verify each against the FEMA PDF before loading to production | High
10 | Owned rates | Caltrans 2026-27 dollar rates (columns separated in extraction) | Second owned-rate source not used | Re-extract Caltrans book with a table-aware PDF tool | Medium
11 | Rental | Coastal / Sun Belt coverage: no TX, CA, FL 2025-2026 bare earthwork rate sheets; nationals behind login | Rental medians lean Midwest/Mountain West | Quote survey (URI, Sunbelt, Herc, H&E, EquipmentShare) in 3-4 coastal metros | High
12 | Rental | Scrapers, D7-D11 (D9+ quote only), 65 t+ excavators, graders (Wheeler only), rigid trucks, bare dump trucks, carry-deck cranes, 47-63 m boom pumps, bucket trucks, welders >300 A, message boards, scaffolding systems, spider lifts (COSTARS 'atrium' only) | Single-source (B) or blank (D) | Dealer quotes; ARA/Rouse data | Medium
13 | Rental | Aerial lift rates partly 2022-2024 (BigRentz Dec 2022; COSTARS 2023-24 contract caps) | Aerial medians likely understate 2026 rates | 2026 quotes from 2+ national renters | Medium
14 | Rental | Damage waiver % for Sunbelt/Herc/H&E not confirmed; 10-16% rests on DOZR + Wheeler | Add-on % is indicative | Read current rental contracts | Low
15 | Fuel | No gal/hr for highway dump trucks (only a low-reliability blog 3.2/6.2), 2-4 in trash pumps, aerial lifts, RT forklifts, cranes, concrete pumps, cold planers, many compact machines; generators >500 kW and <20 kW; compressor part-load | Fuel blank, HP-derived (C) or load-fraction assumption | Manufacturer spec sheets; telematics | Medium
16 | Fuel | Cat VisionLink oddities: 308 CR below 305 CR; TL1255 below TL642; scraper low/high inverted (627K, 637K, 657) | Kept as published; flagged | Cross-check Cat PHB Ed. 50 fuel tables | Low
17 | Fuel | FEMA embedded diesel price not published; EIA 2025 avg assumed | Ex-fuel rates depend on assumption (<1% sensitivity per notes) | Ask FEMA/EquipmentWatch for fuel basis | Low
18 | Taxonomy | Specs missing: blade capacities, many operating weights/widths (wheel dozers, ADTs, rigid trucks, scrapers, cranes), tower/spider/knuckle crane classes, hammer energy classes, drill rig classes, HDD/vac-ex/pipe-burst sizes, heaters/dehumidifiers/barricades, trench box depth ratings | Transport class often defaulted; some rows lack defining spec values | OEM spec sheets (Cat, Komatsu, Deere, Volvo, JLG/Genie, Manitowoc/Liebherr) | Medium
19 | Taxonomy | Caltrans size bands after LEADS section truncated; USACE category list not verified | Some band labels unverified | Re-extract Caltrans 26v3; obtain USACE EP | Low
20 | Mob/Demob | No load/unload hours, truck+driver $/hr, tractor+lowboy tare weights, crane assembly hours/truckloads, verified rental delivery fees by size | Mob default excludes load/unload; legal-vs-permit split for 20-30 t is 'maybe' | Hauler and crane-rental quotes; OEM transport manuals | Medium
21 | Mob/Demob | Haul rates from one trade publisher (OTrucking) with internal inconsistencies; permits verified only for Texas | Per-mile defaults indicative | 2-3 hauler quotes per transport class; state permit schedules | Medium
22 | Location | RSMeans 015433 equipment index for one state only (secondary copy); Blue Book table undated; no ARA/Rouse regional data | 0.85-1.15 band is inference | License RSMeans CCI; EquipmentWatch regional table | Medium
23 | Duration | No sourced minimum rental periods for most non-crane classes; no dewatering pump-hour guidance; no AWP lift-days norms | Duration norms are partly inference (C) | Rental contracts; IntelCost historical jobs | Low
Live counts (from Equipment / Production)
| Equipment rows with rental confidence D | 341
| Equipment rows with owned confidence D | 449
| Equipment rows with any 'Needs rate' flag | 564
| Equipment rows flagged FEMA ⚠ | 26
| Equipment rows needing fuel gal/hr | 289
| Equipment rows flagged non-monotonic | 29
| Production rows at D (no value yet) | 228

## Settings
Settings - every derived formula in this workbook reads these cells. Blue = editable input.
Edit only column B. Leaving a 'NOT IN NOTES' cell blank keeps the dependent rows blank (confidence D) rather than inventing a value.
Setting | Value | Source / note
Fuel price, diesel, user/job ($/gal) | 6.276 | EIA US avg on-highway diesel, week of Oct 19 2026 (EIA-GDU). Replace with local/off-road price. [EIA-GDU]
Diesel price used for FEMA fuel back-out ($/gal) | 3.66 | EIA 2025 annual avg US No.2 diesel retail. FEMA does not publish its fuel basis; 2024 avg 3.760 is the sensitivity. [EIA-HIST]
Default mob/demob distance (one-way miles) | 50 | Design default chosen by the user. Drives Default_mob/demob on Equipment.
Job efficiency E (50-min hour) | 0.83 | FM 5-434 well-managed job 50/60 = 0.83. Calculated production rows multiply by this cell. [FM5434]
Equipment location factor (bare rate) | 1 | Default 1.00; suggested clamp 0.85-1.15 lower 48 (inference). See Location sheet. Do NOT use the labor factor.
Fuel price, gasoline, user/job ($/gal) | 4.284 | EIA US avg regular gasoline, week of Oct 19 2026. [EIA-GDU]
Gasoline price used for FEMA back-out ($/gal) |  | NOT IN NOTES (no 2025 gasoline annual avg gathered). Left blank, so gas-fuelled FEMA rows show no ex-fuel rate. Enter a value to activate.
Diesel fuel factor, full load (gal per bhp-hr) | 0.0486 | USACE EP 1110-1-8: 0.34 lb/bhp-hr / 7 lb/gal. [USACE-EP]
Gasoline fuel factor, full load (gal per bhp-hr) | 0.0917 | USACE EP 1110-1-8: 0.55 lb/bhp-hr / 6 lb/gal. [USACE-EP]
Load factor - low | 0.35 | Low end of 0.35-0.60 typical (owned_rates notes, derived from Cat tables). [USACE-EP; CATFUEL22]
Load factor - medium | 0.46 | Implied D6 average: Cat D6 medium 4.82 gal/hr / (215 hp x 0.0486) = 0.46. [CATFUEL22; USACE-EP]
Load factor - high | 0.6 | High end of 0.35-0.60 typical.
Week / day rental multiplier (derivation default) | 3 | Catalog default: week = 3.0 x day (Cat/Alta dealer formula pricing observed 2.9-3.0). [W25; B25]
4-week / week rental multiplier (derivation default) | 2.9 | Catalog default: 4-week = 2.9 x week (dealer sheets 2.9-3.0; Columbus 2.5). [W25; B25; C25]
Demob / mob factor | 1 | Demob defaults to the same haul as mob; stored separately so it can differ. [OTR-LOW]
Permit states crossed (default) | 1 | Used by Mob_Demob permit term.
Production speed inputs
Haul speed, on-road dump truck LOADED (mph) |  | NOT SOURCED - enter. specs_fill gives only top speeds (Cat 725 34 mph etc.) and one rimpull worked example (loaded +2% -> 31 mph max x 0.65-1.19 average factor); no average haul speed basis. Blank = haul rows show D.
Haul speed, on-road dump truck EMPTY (mph) |  | NOT IN NOTES - enter.
Haul speed, ADT / rigid LOADED (mph) |  | NOT SOURCED - enter. Cat PHB s.21 rimpull charts not retrieved; top speeds 34-49 mph are maxima, not averages.
Haul speed, ADT / rigid EMPTY (mph) |  | NOT IN NOTES - enter.
Scraper haul speed LOADED (mph) |  | NOT SOURCED - enter. Cat loaded top speeds 33-34.7 mph are maxima, not cycle averages; empty speed not published.
Scraper return speed EMPTY (mph) |  | NOT IN NOTES - enter.
Dozer forward (dozing) speed (mph) | 2.49 | KSU CE419 Ch4.2 Example 4-6: 4.0 km/h = 2.49 mph. [KSU-4]
Dozer return (reverse) speed (mph) | 4.97 | KSU CE419 Ch4.2 Example 4-6: 8 km/h = 4.97 mph. [KSU-4]
Dozer fixed time per cycle (min) | 0.05 | KSU CE419 Ch4.2 Example 4-6. [KSU-4]
Compressor fuel: low as fraction of full-load gal/hr | 0.5 | Assumption: notes say typical jobsite load ~50-70% of full-load gal/hr (not published). [COMP-SHEETS inference]
Compressor fuel: medium as fraction of full-load gal/hr | 0.6 | Assumption within the 50-70% band (midpoint).
Compressor fuel: high as fraction of full-load gal/hr | 1 | Full load as published (upper bound).
Scraper LCY per heaped yd3 of bowl | 0.833 | FM 5-434 Cat 621B example: 20 LCY per load from a 24 yd3 heaped bowl = 0.833 (USMC caps 621-class at 22 CY). [FM5434; USMC-PE]
Material weight for payload limit (lb per LCY) | 2300 | FM 5-434 standard material weight behind the dozer curves. Change for heavy material. [FM5434]
Truck/ADT loading: LCY per loader pass | 2.7 | Open Exam Prep example: 3 LCY bucket x 0.90 fill = 2.7 LCY per pass. [OEP]
Truck/ADT loading: minutes per pass | 0.5 | Open Exam Prep example: 0.5 min excavator cycle. [OEP]